## TASK
task_code | status_code | wbs_id | actv_code_pho_sd_supervisor_3901_id | actv_code_gls_area_id | user_field_1850 | user_field_1844 | user_field_1848 | task_name | drtn_complete_pct | task_type | base_start_date | base_end_date | user_field_195 | total_float_hr_cnt | remain_drtn_hr_cnt | target_drtn_hr_cnt | target_work_qty | remain_work_qty | act_work_qty | act_start_date | act_end_date | start_date | end_date | resource_list | user_field_1852 | delete_record_flag
Activity ID | Activity Status | WBS Code | PHO SD - Supervisor | GLS_Area | PHO SD - WO Header | PHO SD - Order | PHO SD - Operation | Activity Name | (*)Duration % Complete(%) | (*)Activity Type | (*)BL Project Start | (*)BL Project Finish | Comments | (*)Total Float(h) | Remaining Duration(h) | Original Duration(h) | (*)Budgeted Labor Units(h) | (*)Remaining Labor Units(h) | (*)Actual Labor Units(h) | Actual Start | Actual Finish | (*)Start | (*)Finish | (*)Resources | PHO SD - Revision
Activity ID | Activity Status | WBS Code | Supervisor | Area | Work Order Description | Work Order Number | Operation Number | Activity Name | % Complete | Activity Type | Baseline Start | Baseline Finish | Comments | Total Float | Remaining Duration | Original Duration | Budgeted Labor Units | Remaining Labor Units | Actual Labor Units | Actual Start | Actual Finish | Planned Start | Planned Finish | Resources | Project Name
GFOFF | Not Started | GLSTest-01.MLSTN.GRAN | GRAN |  | Key Dates |  |  | Granulation Feed Off | 0 | Start Milestone | 2023-07-12 06:00 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-12 06:00 |  |  | 22SD1
GRAN.MS.1000 | Not Started | GLSTest-01.MLSTN.GRAN | GRAN |  | Key Dates |  |  | Granulation Isolation Start | 0 | Start Milestone | 2023-07-12 07:00 |  |  | 87.5 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-12 07:00 |  |  | 22SD1
GRAN.MS.1090 | Not Started | GLSTest-01.MLSTN.GRAN | GRAN |  | Key Dates |  |  | Granulation Isolations Removed | 0 | Finish Milestone |  | 2023-07-15 18:30 |  | 4 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-07-15 18:30 |  | 22SD1
GFON | Not Started | GLSTest-01.MLSTN.GRAN | GRAN |  | Key Dates |  |  | Granulation Feed On | 0 | Finish Milestone |  | 2023-07-15 22:30 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-07-15 22:30 |  | 22SD1
GRAN.MS.1060 | Not Started | GLSTest-01.MLSTN.GRAN | GRAN |  | Key Dates |  |  | Granulation Isolations Finish | 0 | Finish Milestone |  | 2023-07-15 11:30 |  | 11 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-07-15 11:30 |  | 22SD1
GRAN.MS.2000 | Not Started | GLSTest-01.MLSTN.GRAN | GRAN |  | Key Durations |  |  | Granulation Shut Duration | 0 | Level of Effort | 2023-07-12 06:00 | 2023-07-15 22:30 |  | 0 | 88.5 | 88.5 | 0 | 0 | 0 |  |  | 2023-07-12 06:00 | 2023-07-15 22:30 |  | 22SD1
GRAN.MS.1020 | Not Started | GLSTest-01.MLSTN.GRAN | GRAN |  | Key Dates |  |  | Granulation Maintenance Start | 0 | Start Milestone | 2023-07-12 09:00 |  |  | 75.5 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-12 09:00 |  |  | 22SD1
GRAN.MS.2020 | Not Started | GLSTest-01.MLSTN.GRAN | GRAN |  | Key Durations |  |  | Granulation Maintenance Duration | 0 | Level of Effort | 2023-07-12 09:00 | 2023-07-15 15:30 |  | 7 | 78.5 | 78.5 | 0 | 0 | 0 |  |  | 2023-07-12 09:00 | 2023-07-15 15:30 |  | 22SD1
GRAN.MS.1070 | Not Started | GLSTest-01.MLSTN.GRAN | GRAN |  | Key Dates |  |  | Granulation Maintenance Finish | 0 | Finish Milestone |  | 2023-07-15 15:30 |  | 7 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-07-15 15:30 |  | 22SD1
GRAN.MS.2010 | Not Started | GLSTest-01.MLSTN.GRAN | GRAN |  | Key Durations |  |  | Granulation Ramp Down Duration | 0 | Level of Effort | 2023-07-12 06:00 | 2023-07-12 22:00 |  | 0 | 16 | 16 | 0 | 0 | 0 |  |  | 2023-07-12 06:00 | 2023-07-12 22:00 |  | 22SD1
GRAN.MS.2030 | Not Started | GLSTest-01.MLSTN.GRAN | GRAN |  | Key Durations |  |  | Granulation Ramp Up Duration | 0 | Level of Effort | 2023-07-15 15:30 | 2023-07-15 22:30 |  | 0 | 7 | 7 | 0 | 0 | 0 |  |  | 2023-07-15 15:30 | 2023-07-15 22:30 |  | 22SD1
GRAN.MS.1080 | Not Started | GLSTest-01.MLSTN.GRAN | GRAN |  | Key Dates |  |  | Granulation Level Milestone | 0 | Finish Milestone |  | 2023-07-15 16:30 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-07-15 16:30 |  | 22SD1
GRAN.MS.1040 | Not Started | GLSTest-01.MLSTN.GRAN | GRAN |  | Key Dates |  |  | Granulation Contractor Maintenance Start | 0 | Start Milestone | 2023-07-13 |  |  | 13 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-13 |  |  | 22SD1
BENE.MS.1030 | Not Started | GLSTest-01.MLSTN.BENE | BENE |  | Key Dates |  |  | Bene Maintenance Finish | 0 | Finish Milestone |  | 2023-07-16 20:00 |  | 6 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-07-16 20:00 |  | 22SD1
BFOFF | Not Started | GLSTest-01.MLSTN.BENE | BENE |  | Key Dates |  |  | Bene Feed Off | 0 | Start Milestone | 2023-07-14 |  |  | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-14 |  |  | 22SD1
BENE.MS.1040 | Not Started | GLSTest-01.MLSTN.BENE | BENE |  | Key Dates |  |  | Bene De-Isolations Finish | 0 | Finish Milestone |  | 2023-07-16 21:00 |  | 5 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-07-16 21:00 |  | 22SD1
BENE.MS.1020 | Not Started | GLSTest-01.MLSTN.BENE | BENE |  | Key Dates |  |  | Bene Isolations Finish | 0 | Finish Milestone |  | 2023-07-15 21:00 |  | 66 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-07-15 21:00 |  | 22SD1
BFON | Not Started | GLSTest-01.MLSTN.BENE | BENE |  | Key Dates |  |  | Bene Feed On | 0 | Finish Milestone |  | 2023-07-17 02:00 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-07-17 02:00 |  | 22SD1
BENE.MS.2000 | Not Started | GLSTest-01.MLSTN.BENE | BENE |  | Key Durations |  |  | Bene Total Shut Duration | 0 | Level of Effort | 2023-07-14 | 2023-07-17 02:00 |  | 0 | 74 | 74 | 0 | 0 | 0 |  |  | 2023-07-14 | 2023-07-17 02:00 |  | 22SD1
BENE.MS.2020 | Not Started | GLSTest-01.MLSTN.BENE | BENE |  | Key Durations |  |  | Bene Maintenance Window | 0 | Level of Effort | 2023-07-14 05:30 | 2023-07-16 20:00 |  | 6 | 62.5 | 62.5 | 0 | 0 | 0 |  |  | 2023-07-14 05:30 | 2023-07-16 20:00 |  | 22SD1
BENE.MS.1010 | Not Started | GLSTest-01.MLSTN.BENE | BENE |  | Key Dates |  |  | Bene Maintenance Start | 0 | Start Milestone | 2023-07-14 05:30 |  |  | 105.5 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-14 05:30 |  |  | 22SD1
BENE.MS.1000 | Not Started | GLSTest-01.MLSTN.BENE | BENE |  | Key Dates |  |  | Bene Isolations Start | 0 | Start Milestone | 2023-07-14 01:30 |  |  | 109.5 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-14 01:30 |  |  | 22SD1
BENE.MS.2010 | Not Started | GLSTest-01.MLSTN.BENE | BENE |  | Key Durations |  |  | Bene Ramp Down | 0 | Level of Effort | 2023-07-14 | 2023-07-15 17:00 |  | 2 | 41 | 41 | 0 | 0 | 0 |  |  | 2023-07-14 | 2023-07-15 17:00
BENE.MS.2030 | Not Started | GLSTest-01.MLSTN.BENE | BENE |  | Key Durations |  |  | Bene Ramp Up | 0 | Level of Effort | 2023-07-16 16:00 | 2023-07-17 02:00 |  | 0 | 10 | 10 | 0 | 0 | 0 |  |  | 2023-07-16 16:00 | 2023-07-17 02:00
PHOS.MS.1090 | Not Started | GLSTest-01.MLSTN.PHOS | PHOS |  | Key Dates |  |  | Phos Acid Maintenance Finish | 0 | Finish Milestone |  | 2023-07-18 02:00 |  | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-07-18 02:00 |  | 22SD1
PHOS.MS.1000 | Not Started | GLSTest-01.MLSTN.PHOS | PHOS |  | Key Dates |  |  | Phos Rampdown Start | 0 | Start Milestone | 2023-07-13 06:00 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-13 06:00 |  |  | 22SD1
EVOFF | Not Started | GLSTest-01.MLSTN.PHOS | PHOS |  | Key Dates |  |  | Evaporator Feed Off | 0 | Start Milestone | 2023-07-14 |  |  | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-14 |  |  | 22SD1
PHOS.MS.1050 | Not Started | GLSTest-01.MLSTN.PHOS | PHOS |  | Key Dates |  |  | Phos Isolations Finish | 0 | Finish Milestone |  | 2023-07-16 09:30 |  | 41.5 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-07-16 09:30 |  | 22SD1
PAFON-100 | Not Started | GLSTest-01.MLSTN.PHOS | PHOS |  | Key Dates |  |  | Phos Feed @ 100% Rates | 0 | Finish Milestone |  | 2023-07-18 03:00 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-07-18 03:00 |  | 22SD1
PHOS.MS.1010 | Not Started | GLSTest-01.MLSTN.PHOS | PHOS |  | Key Dates |  |  | Phos Isolation Start | 0 | Start Milestone | 2023-07-14 18:00 |  |  | 93 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-14 18:00 |  |  | 22SD1
PAFOFF | Not Started | GLSTest-01.MLSTN.PHOS | PHOS |  | Key Dates |  |  | Phos Acid Feed Off | 0 | Start Milestone | 2023-07-14 18:00 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-14 18:00 |  |  | 22SD1
PHOS.MS.2020 | Not Started | GLSTest-01.MLSTN.PHOS | PHOS |  | Key Durations |  |  | Phos Acid Shut Duration - 50% Rates | 0 | Level of Effort | 2023-07-14 18:00 | 2023-07-17 15:00 |  | 0 | 69 | 69 | 0 | 0 | 0 |  |  | 2023-07-14 18:00 | 2023-07-17 15:00 |  | 22SD1
PHOS.MS.1020 | Not Started | GLSTest-01.MLSTN.PHOS | PHOS |  | Key Dates |  |  | Process Engineer to Review Ramp Down Conditions | 0 | Finish Milestone |  | 2023-07-14 18:00 |  | 93 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-07-14 18:00 |  | 22SD1
PAFON-50 | Not Started | GLSTest-01.MLSTN.PHOS | PHOS |  | Key Dates |  |  | Phos Feed @ 50% Rates | 0 | Finish Milestone |  | 2023-07-17 15:00 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-07-17 15:00 |  | 22SD1
PHOS.MS.2030 | Not Started | GLSTest-01.MLSTN.PHOS | PHOS |  | Key Durations |  |  | Phos Acid Maintenance Duration | 0 | Level of Effort | 2023-07-14 18:00 | 2023-07-18 02:00 |  | 1 | 80 | 80 | 0 | 0 | 0 |  |  | 2023-07-14 18:00 | 2023-07-18 02:00 |  | 22SD1
PHOS.MS.1100 | Not Started | GLSTest-01.MLSTN.PHOS | PHOS |  | Key Dates |  |  | Phos De-Isolations Complete | 0 | Finish Milestone |  | 2023-07-18 03:00 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-07-18 03:00 |  | 22SD1
PHOS.MS.1030 | Not Started | GLSTest-01.MLSTN.PHOS | PHOS |  | Key Dates |  |  | Phos Rampdown Finish | 0 | Finish Milestone |  | 2023-07-14 21:00 |  | 41 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-07-14 21:00 |  | 22SD1
PHOS.MS.2040 | Not Started | GLSTest-01.MLSTN.PHOS | PHOS |  | Key Durations |  |  | Phos Acid Shut Duration - 100% Rates | 0 | Level of Effort | 2023-07-14 18:00 | 2023-07-18 03:00 |  | 0 | 81 | 81 | 0 | 0 | 0 |  |  | 2023-07-14 18:00 | 2023-07-18 03:00 |  | 22SD1
PHOS.MS.2000 | Not Started | GLSTest-01.MLSTN.PHOS | PHOS |  | Key Durations |  |  | Phos Acid Ramp Down Duration | 0 | Level of Effort | 2023-07-13 06:00 | 2023-07-15 01:30 |  | 45 | 43.5 | 43.5 | 0 | 0 | 0 |  |  | 2023-07-13 06:00 | 2023-07-15 01:30
PHOS.MS.2050 | Not Started | GLSTest-01.MLSTN.PHOS | PHOS |  | Key Durations |  |  | Phos Acid Ramp Up Duration | 0 | Level of Effort | 2023-07-17 04:00 | 2023-07-17 15:00 |  | 0 | 11 | 11 | 0 | 0 | 0 |  |  | 2023-07-17 04:00 | 2023-07-17 15:00
PHOS.MS.1060 | Not Started | GLSTest-01.MLSTN.PHOS | PHOS |  | Key Dates |  |  | Phos Acid Level Milestone | 0 | Finish Milestone |  | 2023-07-16 22:00 |  | 13 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-07-16 22:00 |  | 22SD1
PHOS.MS.1080 | Not Started | GLSTest-01.MLSTN.PHOS | PHOS |  | Key Dates |  |  | Phos Acid 50% 12 hr Weather Contingency | 0 | Task Dependent | 2023-07-17 15:00 | 2023-07-18 03:00 |  | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 2023-07-17 15:00 | 2023-07-18 03:00
PHOS.MS.1110 | Not Started | GLSTest-01.MLSTN.PHOS | PHOS |  | Key Dates |  |  | Phos Acid 100% 12 hr Weather Contingency | 0 | Task Dependent | 2023-07-18 03:00 | 2023-07-18 15:00 |  | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 2023-07-18 03:00 | 2023-07-18 15:00
PAFON-100-WEATHER | Not Started | GLSTest-01.MLSTN.PHOS | PHOS |  | Key Dates |  |  | Phos Feed @ 100% Rates (w/ Weather Contingency) | 0 | Finish Milestone |  | 2023-07-18 15:00 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-07-18 15:00 |  | 22SD1
PAFON-50-WEATHER | Not Started | GLSTest-01.MLSTN.PHOS | PHOS |  | Key Dates |  |  | Phos Feed @ 50% Rates (w/ Weather Contingency) | 0 | Finish Milestone |  | 2023-07-18 03:00 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-07-18 03:00 |  | 22SD1
EVON | Not Started | GLSTest-01.MLSTN.PHOS | PHOS |  | Key Dates |  |  | Evaporator Feed On | 0 | Finish Milestone |  | 2023-07-17 12:00 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-07-17 12:00 |  | 22SD1
PHOS.MS.1040 | Not Started | GLSTest-01.MLSTN.PHOS | PHOS |  | Key Dates |  |  | Phos Acid Maintenance Start (Electrical Level) | 0 | Start Milestone | 2023-07-14 22:00 |  |  | 40 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-14 22:00 |  |  | 22SD1
PHOS.MS.1070 | Not Started | GLSTest-01.MLSTN.PHOS | PHOS |  | Key Dates |  |  | Evaporator 12 hr Weather Contingency | 0 | Task Dependent | 2023-07-17 12:00 | 2023-07-18 |  | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 2023-07-17 12:00 | 2023-07-18
EVON-WEATHER | Not Started | GLSTest-01.MLSTN.PHOS | PHOS |  | Key Dates |  |  | Evaporator Feed On (w/ Weather Contingency) | 0 | Finish Milestone |  | 2023-07-18 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-07-18 |  | 22SD1
PHOS.MS.2010 | Not Started | GLSTest-01.MLSTN.PHOS | PHOS |  | Key Durations |  |  | Evaporator Total Shut Duration | 0 | Level of Effort | 2023-07-14 | 2023-07-17 12:00 |  | 0 | 84 | 84 | 0 | 0 | 0 |  |  | 2023-07-14 | 2023-07-17 12:00
PWR.MS.1000 | Not Started | GLSTest-01.MLSTN.PWR | PWR |  | Key Dates |  |  | Train Maintenance Start | 0 | Start Milestone | 2023-07-13 |  |  | 48 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-13 |  |  | 22SD1
PSFON | Not Started | GLSTest-01.MLSTN.PWR | PWR |  | Key Dates |  |  | Power Station Maintenance Complete | 0 | Finish Milestone |  | 2023-07-16 17:00 |  | 46 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-07-16 17:00 |  | 22SD1
PWR.MS.2000 | Not Started | GLSTest-01.MLSTN.PWR | PWR |  | Key Durations |  |  | Power Station Total Shutdown Maintenance | 0 | Level of Effort | 2023-07-12 06:00 | 2023-07-16 17:00 |  | 46 | 107 | 107 | 0 | 0 | 0 |  |  | 2023-07-12 06:00 | 2023-07-16 17:00 |  | 22SD1
PWR.MS.2030 | Not Started | GLSTest-01.MLSTN.PWR | PWR |  | Key Durations |  |  | GT1 & OTSG 1 Maintenance | 0 | Level of Effort | 2023-07-16 10:00 | 2023-07-16 13:00 |  | 48 | 3 | 3 | 0 | 0 | 0 |  |  | 2023-07-16 10:00 | 2023-07-16 13:00 |  | 22SD1
PWR.MS.2020 | Not Started | GLSTest-01.MLSTN.PWR | PWR |  | Key Durations |  |  | GT2 & OTSG 2 Maintenance | 0 | Level of Effort | 2023-07-15 02:00 | 2023-07-16 04:00 |  | 48 | 26 | 26 | 0 | 0 | 0 |  |  | 2023-07-15 02:00 | 2023-07-16 04:00 |  | 22SD1
PWR.MS.2010 | Not Started | GLSTest-01.MLSTN.PWR | PWR |  | Key Durations |  |  | GT4 & OTSG 4 Maintenance | 0 | Level of Effort | 2023-07-13 02:00 | 2023-07-14 22:00 |  | 48 | 44 | 44 | 0 | 0 | 0 |  |  | 2023-07-13 02:00 | 2023-07-14 22:00 |  | 22SD1
GRAN.RD.1020 | Not Started | GLSTest-01.GRAN.RD | GRAN | Granulation | Ramp Down Activities |  |  | Spray Out PN | 0 | Task Dependent | 2023-07-12 07:00 | 2023-07-12 07:30 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 07:00 | 2023-07-12 07:30 | Gran Ops | 22SD3
GRAN.RD.1030 | Not Started | GLSTest-01.GRAN.RD | GRAN | Granulation | Ramp Down Activities |  |  | Lower Cooler Weirs | 0 | Task Dependent | 2023-07-12 07:00 | 2023-07-12 07:30 |  | 3.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 07:00 | 2023-07-12 07:30 | Gran Ops | 22SD3
GRAN.RD.1040 | Not Started | GLSTest-01.GRAN.RD | GRAN | Granulation | Ramp Down Activities |  |  | Open Dump Bay Diverter and Empty Dryside | 0 | Task Dependent | 2023-07-12 07:00 | 2023-07-12 07:30 |  | 3.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 07:00 | 2023-07-12 07:30 | Gran Ops | 22SD3
GRAN.RD.1050 | Not Started | GLSTest-01.GRAN.RD | GRAN | Granulation | Ramp Down Activities |  |  | Stop dryside once emptied | 0 | Task Dependent | 2023-07-12 07:00 | 2023-07-12 07:30 |  | 3.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 07:00 | 2023-07-12 07:30 | Gran Ops | 22SD3
GRAN.RD.1060 | Not Started | GLSTest-01.GRAN.RD | GRAN | Granulation | Ramp Down Activities |  |  | Open back of dryer discharge conveyor | 0 | Task Dependent | 2023-07-12 07:00 | 2023-07-12 07:30 |  | 3.5 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-12 07:00 | 2023-07-12 07:30 | Gran Ops | 22SD3
GRAN.RD.1090 | Not Started | GLSTest-01.GRAN.RD | GRAN | Granulation | Ramp Down Activities |  |  | (2nd Wash) Fill PN to 50% with Hot Wash | 0 | Task Dependent | 2023-07-12 10:30 | 2023-07-12 12:00 |  | 0 | 1.5 | 1.5 | 3 | 3 | 0 |  |  | 2023-07-12 10:30 | 2023-07-12 12:00 | Gran Ops | 22SD3
GRAN.RD.1110 | Not Started | GLSTest-01.GRAN.RD | GRAN | Granulation | Ramp Down Activities |  |  | Start offline acid wash system for scrubbers and ring mains | 0 | Task Dependent | 2023-07-12 14:00 | 2023-07-12 22:00 |  | 0 | 8 | 8 | 16 | 16 | 0 |  |  | 2023-07-12 14:00 | 2023-07-12 22:00 | Gran Ops | 22SD3
GRAN.RD.1010 | Not Started | GLSTest-01.GRAN.RD | GRAN | Granulation | Ramp Down Activities |  |  | Lower Vapouriser to Minimum level | 0 | Task Dependent | 2023-07-12 06:00 | 2023-07-12 07:00 |  | 0 | 1 | 1 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 06:00 | 2023-07-12 07:00 | Gran Ops | 22SD3
GRAN.RD.1070 | Not Started | GLSTest-01.GRAN.RD | GRAN | Granulation | Ramp Down Activities |  |  | Fill PN to 50% with Hot Wash | 0 | Task Dependent | 2023-07-12 07:30 | 2023-07-12 09:00 |  | 0 | 1.5 | 1.5 | 3 | 3 | 0 |  |  | 2023-07-12 07:30 | 2023-07-12 09:00 | Gran Ops | 22SD3
GRAN.RD.1080 | Not Started | GLSTest-01.GRAN.RD | GRAN | Granulation | Ramp Down Activities |  |  | Hot Wash Granulator | 0 | Task Dependent | 2023-07-12 09:00 | 2023-07-12 10:30 |  | 0 | 1.5 | 1.5 | 3 | 3 | 0 |  |  | 2023-07-12 09:00 | 2023-07-12 10:30 | Gran Ops | 22SD3
GRAN.RD.1130 | Not Started | GLSTest-01.GRAN.RD | GRAN | Granulation | Ramp Down Activities |  |  | Acid Wash PN Tank | 0 | Task Dependent | 2023-07-12 16:00 | 2023-07-12 22:00 |  | 0 | 6 | 6 | 12 | 12 | 0 |  |  | 2023-07-12 16:00 | 2023-07-12 22:00 | Gran Ops | 22SD3
GRAN.RD.1120 | Not Started | GLSTest-01.GRAN.RD | GRAN | Granulation | Ramp Down Activities |  |  | Purge NH3 to PN Headers | 0 | Task Dependent | 2023-07-12 14:00 | 2023-07-12 16:00 |  | 0 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-12 14:00 | 2023-07-12 16:00 | Gran Ops | 22SD3
GRAN.ISO.2000 | Not Started | GLSTest-01.GRAN.ISO | GRAN | Granulation | Isolations |  |  | Isolate Dryer Discharge | 0 | Task Dependent | 2023-07-12 07:00 | 2023-07-12 07:30 |  | 3.5 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-12 07:00 | 2023-07-12 07:30 | Gran Ops | 22SD3
GRAN.ISO.2030 | Not Started | GLSTest-01.GRAN.ISO | GRAN | Granulation | Isolations |  |  | Isolate G4 Dry Side | 0 | Task Dependent | 2023-07-12 08:00 | 2023-07-12 09:00 |  | 3.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-12 08:00 | 2023-07-12 09:00 | Gran Ops | 22SD3
GRAN.ISO.2040 | Not Started | GLSTest-01.GRAN.ISO | GRAN | Granulation | Isolations |  |  | Isolate G30 Product Screen Elevator Inch | 0 | Task Dependent | 2023-07-12 09:00 | 2023-07-12 10:00 |  | 82.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-12 09:00 | 2023-07-12 10:00 | Gran Ops | 22SD3
GRAN.ISO.2050 | Not Started | GLSTest-01.GRAN.ISO | GRAN | Granulation | Isolations |  |  | Isolate G24 Secondary Elevator Inch | 0 | Task Dependent | 2023-07-12 09:00 | 2023-07-12 10:00 |  | 41 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-12 09:00 | 2023-07-12 10:00 | Gran Ops | 22SD3
GRAN.ISO.2090 | Not Started | GLSTest-01.GRAN.ISO | GRAN | Granulation | Isolations |  |  | Isolate G3 Total Wet-Side/Scrubbers | 0 | Task Dependent | 2023-07-12 20:30 | 2023-07-13 00:30 |  | 0 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-12 20:30 | 2023-07-13 00:30 | Gran Ops | 22SD3
GRAN.ISO.2060 | Not Started | GLSTest-01.GRAN.ISO | GRAN | Granulation | Isolations |  |  | Isolate G2, G8 & G9 Granulator/Dryer | 0 | Task Dependent | 2023-07-12 09:00 | 2023-07-12 11:00 |  | 23 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-12 09:00 | 2023-07-12 11:00 | Gran Ops | 22SD3
GRAN.ISO.2110 | Not Started | GLSTest-01.GRAN.ISO | GRAN | Granulation | Isolations |  |  | Insert spade for CS entry to Granulator | 0 | Task Dependent | 2023-07-12 22:30 | 2023-07-13 |  | 70.5 | 1.5 | 1.5 | 4.5 | 4.5 | 0 |  |  | 2023-07-12 22:30 | 2023-07-13 | Gran Ops, Fitter | 22SD3
GRAN.ISO.2120 | Not Started | GLSTest-01.GRAN.ISO | GRAN | Granulation | Isolations |  |  | Isolate G6 Tail Gas / G7 Vaporiser as required | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 02:30 |  | 14 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 02:30 | Gran Ops | 22SD3
GRAN.ISO.2020 | Not Started | GLSTest-01.GRAN.ISO | GRAN | Granulation | Isolations |  |  | Isolate Surge Hopper For Cleaning | 0 | Task Dependent | 2023-07-12 07:30 | 2023-07-12 08:00 |  | 3.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 07:30 | 2023-07-12 08:00 | Gran Ops | 22SD3
GRAN.ISO.2070 | Not Started | GLSTest-01.GRAN.ISO | GRAN | Granulation | Isolations |  |  | Isolate G23 Primary Elevator Inch | 0 | Task Dependent | 2023-07-12 09:00 | 2023-07-12 10:00 |  | 81.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-12 09:00 | 2023-07-12 10:00 | Gran Ops | 22SD3
GRAN.ISO.2100 | Not Started | GLSTest-01.GRAN.ISO | GRAN | Granulation | Isolations |  |  | Isolate Wetside Sump | 0 | Task Dependent | 2023-07-12 22:00 | 2023-07-12 22:30 |  | 44.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 22:00 | 2023-07-12 22:30 | Gran Ops | 22SD3
GRAN.ISO.2010 | Not Started | GLSTest-01.GRAN.ISO | GRAN | Granulation | Isolations |  |  | Isolate Ammonia to Chiller | 0 | Task Dependent | 2023-07-12 07:00 | 2023-07-12 07:30 |  | 87 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 07:00 | 2023-07-12 07:30 | Gran Ops | 22SD3
GRAN.DEISO.5050 | Not Started | GLSTest-01.GRAN.DE-ISO | GRAN | Granulation | De-Isolations |  |  | De-Isolate G2, G8 & G9 Granulator/Dryer | 0 | Task Dependent | 2023-07-15 10:30 | 2023-07-15 12:30 |  | 10 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-15 10:30 | 2023-07-15 12:30 | Gran Ops, Elec | 22SD1
GRAN.DEISO.5040 | Not Started | GLSTest-01.GRAN.DE-ISO | GRAN | Granulation | De-Isolations |  |  | Remove spade for CS entry to Granulator | 0 | Task Dependent | 2023-07-15 03:30 | 2023-07-15 05:00 |  | 13 | 1.5 | 1.5 | 3 | 3 | 0 |  |  | 2023-07-15 03:30 | 2023-07-15 05:00 | Gran Ops, Fitter | 22SD1
GRAN.DEISO.5110 | Not Started | GLSTest-01.GRAN.DE-ISO | GRAN | Granulation | De-Isolations |  |  | De-Isolate G3 Total Wet-Side/Scrubbers | 0 | Task Dependent | 2023-07-15 12:30 | 2023-07-15 15:30 |  | 0 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-15 12:30 | 2023-07-15 15:30 | Gran Ops | 22SD1
GRAN.DEISO.5060 | Not Started | GLSTest-01.GRAN.DE-ISO | GRAN | Granulation | De-Isolations |  |  | De-Isolate G4 Dry Side & Shed conveyor, Move tripper & run belts | 0 | Task Dependent | 2023-07-15 08:00 | 2023-07-15 10:00 |  | 10 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-15 08:00 | 2023-07-15 10:00 | Gran Ops | 22SD1
GRAN.DEISO.5080 | Not Started | GLSTest-01.GRAN.DE-ISO | GRAN | Granulation | De-Isolations |  |  | De-isolate Product Screens Internals | 0 | Task Dependent | 2023-07-15 10:30 | 2023-07-15 11:00 |  | 9 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 10:30 | 2023-07-15 11:00 | Gran Ops | 22SD1
GRAN.DEISO.5100 | Not Started | GLSTest-01.GRAN.DE-ISO | GRAN | Granulation | De-Isolations |  |  | De-isolate G30 Product Screen Elevator Inch | 0 | Task Dependent | 2023-07-15 11:30 | 2023-07-15 12:30 |  | 9 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-15 11:30 | 2023-07-15 12:30 | Gran Ops | 22SD1
GRAN.DEISO.5120 | Not Started | GLSTest-01.GRAN.DE-ISO | GRAN | Granulation | De-Isolations |  |  | De-isolate G24 Secondary Elevator Inch | 0 | Task Dependent | 2023-07-15 12:30 | 2023-07-15 13:30 |  | 9 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-15 12:30 | 2023-07-15 13:30 | Gran Ops | 22SD1
GRAN.DEISO.5070 | Not Started | GLSTest-01.GRAN.DE-ISO | GRAN | Granulation | De-Isolations |  |  | De-Isolate G6 Tail Gas / G7 Vaporiser | 0 | Task Dependent | 2023-07-15 08:30 | 2023-07-15 10:30 |  | 5 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-15 08:30 | 2023-07-15 10:30 | Gran Ops | 22SD1
GRAN.DEISO.5030 | Not Started | GLSTest-01.GRAN.DE-ISO | GRAN | Granulation | De-Isolations |  |  | De-Isolate Wetside Sump | 0 | Task Dependent | 2023-07-14 13:30 | 2023-07-14 14:00 |  | 32.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 13:30 | 2023-07-14 14:00 | Gran Ops | 22SD1
GRAN.DEISO.5090 | Not Started | GLSTest-01.GRAN.DE-ISO | GRAN | Granulation | De-Isolations |  |  | De-Isolate G23 Primary Elevator | 0 | Task Dependent | 2023-07-15 11:00 | 2023-07-15 11:30 |  | 9 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 11:00 | 2023-07-15 11:30 | Gran Ops | 22SD1
GRAN.DEISO.5130 | Not Started | GLSTest-01.GRAN.DE-ISO | GRAN | Granulation | De-Isolations |  |  | De-isolate G88 Dryer Discharge | 0 | Task Dependent | 2023-07-15 17:30 | 2023-07-15 18:30 |  | 4 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-15 17:30 | 2023-07-15 18:30 | Gran Ops | 22SD1
GRAN.RU.6000 | Not Started | GLSTest-01.GRAN.RU | GRAN | Granulation | Ramp Up Activites |  |  | Fill the tailgas and restart tailgas pumps | 0 | Task Dependent | 2023-07-15 15:30 | 2023-07-15 16:30 |  | 0 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-15 15:30 | 2023-07-15 16:30 | Gran Ops | 22SD1
GRAN.RU.6010 | Not Started | GLSTest-01.GRAN.RU | GRAN | Granulation | Ramp Up Activites |  |  | Start RGV fan | 0 | Task Dependent | 2023-07-15 16:30 | 2023-07-15 17:00 |  | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 16:30 | 2023-07-15 17:00 | Gran Ops | 22SD1
GRAN.RU.6030 | Not Started | GLSTest-01.GRAN.RU | GRAN | Granulation | Ramp Up Activites |  |  | Run the dryer out | 0 | Task Dependent | 2023-07-15 17:00 | 2023-07-15 17:30 |  | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 17:00 | 2023-07-15 17:30 | Gran Ops | 22SD1
GRAN.RU.6090 | Not Started | GLSTest-01.GRAN.RU | GRAN | Granulation | Ramp Up Activites |  |  | Set scrubbers up for production (MAP or DAP) | 0 | Task Dependent | 2023-07-15 20:30 | 2023-07-15 21:00 |  | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 20:30 | 2023-07-15 21:00 | Gran Ops | 22SD1
GRAN.RU.6040 | Not Started | GLSTest-01.GRAN.RU | GRAN | Granulation | Ramp Up Activites |  |  | Flush 40% & 52% acid ring mains | 0 | Task Dependent | 2023-07-15 17:00 | 2023-07-15 17:30 |  | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 17:00 | 2023-07-15 17:30 | Gran Ops | 22SD1
GRAN.RU.6020 | Not Started | GLSTest-01.GRAN.RU | GRAN | Granulation | Ramp Up Activites |  |  | Fill Wetside with water and leak test | 0 | Task Dependent | 2023-07-15 16:30 | 2023-07-15 18:30 |  | 0 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-15 16:30 | 2023-07-15 18:30 | Gran Ops | 22SD1
GRAN.RU.6050 | Not Started | GLSTest-01.GRAN.RU | GRAN | Granulation | Ramp Up Activites |  |  | Fill Wetside with Acid | 0 | Task Dependent | 2023-07-15 18:30 | 2023-07-15 20:00 |  | 0 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-15 18:30 | 2023-07-15 20:00 | Gran Ops | 22SD1
GRAN.RU.6060 | Not Started | GLSTest-01.GRAN.RU | GRAN | Granulation | Ramp Up Activites |  |  | Start & Re-seed dryside | 0 | Task Dependent | 2023-07-15 20:00 | 2023-07-15 22:30 |  | 0 | 2.5 | 2.5 | 2.5 | 2.5 | 0 |  |  | 2023-07-15 20:00 | 2023-07-15 22:30 | Gran Ops | 22SD1
GRAN.RU.6070 | Not Started | GLSTest-01.GRAN.RU | GRAN | Granulation | Ramp Up Activites |  |  | Fill PN | 0 | Task Dependent | 2023-07-15 20:00 | 2023-07-15 20:30 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 20:00 | 2023-07-15 20:30 | Gran Ops | 22SD1
GRAN.RU.6100 | Not Started | GLSTest-01.GRAN.RU | GRAN | Granulation | Ramp Up Activites |  |  | Refill Vaporiser with Ammonia | 0 | Task Dependent | 2023-07-15 20:30 | 2023-07-15 22:30 |  | 0 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-15 20:30 | 2023-07-15 22:30 | Gran Ops | 22SD1
GRAN.RU.6110 | Not Started | GLSTest-01.GRAN.RU | GRAN | Granulation | Ramp Up Activites |  |  | Charge PN | 0 | Task Dependent | 2023-07-15 20:30 | 2023-07-15 22:30 |  | 0 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-15 20:30 | 2023-07-15 22:30 | Gran Ops | 22SD1
GRAN.RU.6120 | Not Started | GLSTest-01.GRAN.RU | GRAN | Granulation | Ramp Up Activites |  |  | Start Burner | 0 | Task Dependent | 2023-07-15 20:30 | 2023-07-15 21:00 |  | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 20:30 | 2023-07-15 21:00 | Gran Ops | 22SD1
BENE.RD.1030 | Not Started | GLSTest-01.BENE.RD | PHOS | Beneficiation | Ramp Down Activities |  |  | Run out Flocc holding tank product | 0 | Task Dependent | 2023-07-14 18:00 | 2023-07-14 20:00 |  | 23 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-14 18:00 | 2023-07-14 20:00 | Bene Ops | 22SD1
BENE.RD.1000 | Not Started | GLSTest-01.BENE.RD | PHOS | Beneficiation | Ramp Down Activities |  |  | Feed off to Primary Crusher & empty ROM bin | 0 | Task Dependent | 2023-07-14 | 2023-07-14 00:30 |  | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 | 2023-07-14 00:30 | Bene Ops | 22SD1
BENE.RD.1020 | Not Started | GLSTest-01.BENE.RD | PHOS | Beneficiation | Ramp Down Activities |  |  | Run out Ball Mill & rest of plant | 0 | Task Dependent | 2023-07-14 00:30 | 2023-07-14 01:30 |  | 1 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-14 00:30 | 2023-07-14 01:30 | Bene Ops | 22SD1
BENE.RD.1050 | Not Started | GLSTest-01.BENE.RD | PHOS | Beneficiation | Ramp Down Activities |  |  | Drain thickener | 0 | Task Dependent | 2023-07-14 19:00 | 2023-07-15 01:00 |  | 2 | 6 | 6 | 6 | 6 | 0 |  |  | 2023-07-14 19:00 | 2023-07-15 01:00 | Bene Ops | 22SD1
BENE.RD.1060 | Not Started | GLSTest-01.BENE.RD | PHOS | Beneficiation | Ramp Down Activities |  |  | Hose Out Thickener Pad for Scaffold | 0 | Task Dependent | 2023-07-15 01:00 | 2023-07-15 05:00 |  | 2 | 4 | 4 | 4 | 4 | 0 |  |  | 2023-07-15 01:00 | 2023-07-15 05:00 | Bene Ops | 22SD1
BENE.RD.1070 | Not Started | GLSTest-01.BENE.RD | PHOS | Beneficiation | Ramp Down Activities |  |  | Hose Out Thickener to Cone | 0 | Task Dependent | 2023-07-15 05:00 | 2023-07-15 17:00 |  | 2 | 12 | 12 | 12 | 12 | 0 |  |  | 2023-07-15 05:00 | 2023-07-15 17:00 | Bene Ops | 22SD1
BENE.RD.1040 | Not Started | GLSTest-01.BENE.RD | PHOS | Beneficiation | Ramp Down Activities |  |  | Raise Thickener Rakes | 0 | Task Dependent | 2023-07-14 18:00 | 2023-07-14 19:00 |  | 2 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-14 18:00 | 2023-07-14 19:00 | Bene Ops | 22SD1
BENE.RD.1010 | Not Started | GLSTest-01.BENE.RD | PHOS | Beneficiation | Ramp Down Activities |  |  | Drain Rock Slurry Tank 2 | 0 | Task Dependent | 2023-07-14 | 2023-07-14 12:00 |  | 6 | 12 | 12 | 12 | 12 | 0 |  |  | 2023-07-14 | 2023-07-14 12:00 | Bene Ops | 22SD1
BENE.ISO.2000 | Not Started | GLSTest-01.BENE.ISO | PHOS | Beneficiation | Isolations |  |  | Isolate Feeder - ROM | 0 | Task Dependent | 2023-07-14 01:30 | 2023-07-14 02:30 |  | 1 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-14 01:30 | 2023-07-14 02:30 | Bene Ops | 22SD1
BENE.ISO.2010 | Not Started | GLSTest-01.BENE.ISO | PHOS | Beneficiation | Isolations |  |  | Isolate Coarse Ore & Stockpiling | 0 | Task Dependent | 2023-07-14 02:30 | 2023-07-14 03:00 |  | 1 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-14 02:30 | 2023-07-14 03:00 | Bene Ops | 22SD1
BENE.ISO.2020 | Not Started | GLSTest-01.BENE.ISO | PHOS | Beneficiation | Isolations |  |  | Isolate Tertiary Crusher | 0 | Task Dependent | 2023-07-14 03:00 | 2023-07-14 03:30 |  | 1 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-14 03:00 | 2023-07-14 03:30 | Bene Ops | 22SD1
BENE.ISO.2030 | Not Started | GLSTest-01.BENE.ISO | PHOS | Beneficiation | Isolations |  |  | Isolate Ball Mill and Milling Circuit - (HV) | 0 | Task Dependent | 2023-07-14 03:30 | 2023-07-14 05:30 |  | 1 | 2 | 2 | 6 | 6 | 0 |  |  | 2023-07-14 03:30 | 2023-07-14 05:30 | Bene Ops, HV Elec | 22SD1
BENE.ISO.2050 | Not Started | GLSTest-01.BENE.ISO | PHOS | Beneficiation | Isolations |  |  | Isolate Agitator Slurry Storage | 0 | Task Dependent | 2023-07-14 12:00 | 2023-07-14 12:30 |  | 49.5 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-14 12:00 | 2023-07-14 12:30 | Bene Ops | 22SD1
BENE.ISO.2070 | Not Started | GLSTest-01.BENE.ISO | PHOS | Beneficiation | Isolations |  |  | Isolate Thickener | 0 | Task Dependent | 2023-07-15 17:00 | 2023-07-15 18:00 |  | 2 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-15 17:00 | 2023-07-15 18:00 | Bene Ops | 22SD1
BENE.ISO.2080 | Not Started | GLSTest-01.BENE.ISO | PHOS | Beneficiation | Isolations |  |  | Isolate Deslime Cyclone Overflow Pump | 0 | Task Dependent | 2023-07-15 18:00 | 2023-07-15 19:00 |  | 15 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-15 18:00 | 2023-07-15 19:00 | Bene Ops | 22SD1
BENE.ISO.2100 | Not Started | GLSTest-01.BENE.ISO | PHOS | Beneficiation | Isolations |  |  | Isolate Process Water Tank | 0 | Task Dependent | 2023-07-15 19:00 | 2023-07-15 21:00 |  | 15 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-15 19:00 | 2023-07-15 21:00 | Bene Ops | 22SD1
BENE.ISO.2090 | Not Started | GLSTest-01.BENE.ISO | PHOS | Beneficiation | Isolations |  |  | Isolate Slurry Storage Fd Pumps | 0 | Task Dependent | 2023-07-15 18:00 | 2023-07-15 18:30 |  | 23.5 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-15 18:00 | 2023-07-15 18:30 | Bene Ops | 22SD1
BENE.ISO.2060 | Not Started | GLSTest-01.BENE.ISO | PHOS | Beneficiation | Isolations |  |  | Isolate Floc Plant | 0 | Task Dependent | 2023-07-14 20:00 | 2023-07-14 21:00 |  | 23 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-14 20:00 | 2023-07-14 21:00 | Bene Ops | 22SD1
BENE.ISO.2040 | Not Started | GLSTest-01.BENE.ISO | PHOS | Beneficiation | Isolations |  |  | Isolate Scrubber Circuit | 0 | Task Dependent | 2023-07-14 05:30 | 2023-07-14 06:00 |  | 1 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-14 05:30 | 2023-07-14 06:00 | Bene Ops | 22SD1
BENE.DEISO.5060 | Not Started | GLSTest-01.BENE.DE-ISO | PHOS | Beneficiation | De-Isolations |  |  | De-Isolate Process Water tank and Fill | 0 | Task Dependent | 2023-07-16 18:00 | 2023-07-16 20:00 |  | 5 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-16 18:00 | 2023-07-16 20:00 | Bene Ops | 22SD1
BENE.DEISO.5030 | Not Started | GLSTest-01.BENE.DE-ISO | PHOS | Beneficiation | De-Isolations |  |  | De-Isolate Thickener | 0 | Task Dependent | 2023-07-16 16:00 | 2023-07-16 17:00 |  | 3 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-16 16:00 | 2023-07-16 17:00 | Bene Ops | 22SD1
BENE.DEISO.5040 | Not Started | GLSTest-01.BENE.DE-ISO | PHOS | Beneficiation | De-Isolations |  |  | De-Isolate Ball Mill and Milling Circuit - (HV) | 0 | Task Dependent | 2023-07-16 17:00 | 2023-07-16 20:00 |  | 2 | 3 | 3 | 9 | 9 | 0 |  |  | 2023-07-16 17:00 | 2023-07-16 20:00 | Bene Ops, HV Elec | 22SD1
BENE.DEISO.5080 | Not Started | GLSTest-01.BENE.DE-ISO | PHOS | Beneficiation | De-Isolations |  |  | De Isolate Scrubbing, Tertiary, Secondary and Primary Circuits | 0 | Task Dependent | 2023-07-16 22:00 | 2023-07-16 23:00 |  | 0 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-16 22:00 | 2023-07-16 23:00 | Bene Ops | 22SD1
BENE.DEISO.5000 | Not Started | GLSTest-01.BENE.DE-ISO | PHOS | Beneficiation | De-Isolations |  |  | De-Isolate Floc Plant | 0 | Task Dependent | 2023-07-15 15:30 | 2023-07-15 16:30 |  | 30.5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-15 15:30 | 2023-07-15 16:30 | Bene Ops | 22SD1
BENE.RU.6020 | Not Started | GLSTest-01.BENE.RU | PHOS | Beneficiation | Ramp Up |  |  | Bar Ball Mill over | 0 | Task Dependent | 2023-07-16 20:00 | 2023-07-16 21:00 |  | 5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-16 20:00 | 2023-07-16 21:00 | Bene Ops | 22SD1
BENE.RU.6000 | Not Started | GLSTest-01.BENE.RU | PHOS | Beneficiation | Ramp Up |  |  | Batch Floc | 0 | Task Dependent | 2023-07-15 16:30 | 2023-07-15 19:30 |  | 30.5 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-15 16:30 | 2023-07-15 19:30 | Bene Ops | 22SD1
BENE.RU.6010 | Not Started | GLSTest-01.BENE.RU | PHOS | Beneficiation | Ramp Up |  |  | Fill Thickener | 0 | Task Dependent | 2023-07-16 17:00 | 2023-07-16 23:00 |  | 3 | 6 | 6 | 6 | 6 | 0 |  |  | 2023-07-16 17:00 | 2023-07-16 23:00 | Bene Ops | 22SD1
PHOS.RD.1010 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Acid Water |  |  | Set up diesel pump at Hot well basin | 0 | Task Dependent | 2023-07-13 06:00 | 2023-07-13 09:00 |  | 30 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-13 06:00 | 2023-07-13 09:00 | Phos Ops | 22SD1
PHOS.RD.1030 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Acid Water |  |  | Set up diesel pump at Cold well basin | 0 | Task Dependent | 2023-07-13 09:00 | 2023-07-13 12:00 |  | 30 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-13 09:00 | 2023-07-13 12:00 | Phos Ops | 22SD1
PHOS.RD.1020 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Hemihydrate Reaction |  |  | Raise P2o5 levels to 43% * | 0 | Task Dependent | 2023-07-13 06:00 | 2023-07-14 18:00 |  | 0 | 36 | 36 | 36 | 36 | 0 |  |  | 2023-07-13 06:00 | 2023-07-14 18:00 | Phos Ops | 22SD1
PHOS.RD.1130 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Hemihydrate Reaction |  |  | P2O5 to be at 43% prior to long shut | 0 | Finish Milestone |  | 2023-07-14 18:00 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-07-14 18:00 |  | 22SD1
PHOS.RD.1080 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Product Filtration |  |  | Emergency Dumping | 0 | Task Dependent | 2023-07-14 06:00 | 2023-07-14 18:00 |  | 0 | 12 | 12 | 12 | 12 | 0 |  |  | 2023-07-14 06:00 | 2023-07-14 18:00 | Phos Ops | 22SD1
PHOS.RD.1190 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Product Filtration |  |  | Pack up offline Filters - B Train | 0 | Task Dependent | 2023-07-14 21:00 | 2023-07-15 |  | 35.5 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-14 21:00 | 2023-07-15 | Phos Ops | 22SD1
PHOS.RD.1140 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Hemihydrate Reaction |  |  | Establish Long Shut Conditions | 0 | Task Dependent | 2023-07-14 18:00 | 2023-07-14 21:00 |  | 0 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-14 18:00 | 2023-07-14 21:00 | Phos Ops | 22SD1
PHOS.RD.1230 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Product Filtration |  |  | Pack up Filters used for Filtering off, hose out fumehoods | 0 | Task Dependent | 2023-07-15 | 2023-07-15 01:30 |  | 0 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-15 | 2023-07-15 01:30 | Phos Ops | 22SD1
PHOS.RD.1240 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Scrubber & Fume Fans |  |  | Turn on temp fans | 0 | Start Milestone | 2023-07-15 01:30 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-15 01:30 |  |  | 22SD1
PHOS.RD.1250 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Scrubber & Fume Fans |  |  | Turn on Temp Gland Water Lines - 40%, 52% & 8001 | 0 | Start Milestone | 2023-07-15 01:30 |  |  | 45 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-15 01:30 |  |  | 22SD1
PHOS.RD.1150 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Hemihydrate Reaction |  |  | Flush Flash Cooler B Pump | 0 | Task Dependent | 2023-07-14 18:00 | 2023-07-14 18:30 |  | 0 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-14 18:00 | 2023-07-14 18:30 | Phos Ops | 22SD1
PHOS.RD.1040 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Evaporator |  |  | Steam off to Evaporator | 0 | Task Dependent | 2023-07-14 | 2023-07-14 00:30 |  | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 | 2023-07-14 00:30 | Phos Ops | 22SD1
PHOS.RD.1050 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Evaporator |  |  | Drain acid from Evaporator | 0 | Task Dependent | 2023-07-14 00:30 | 2023-07-14 02:00 |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-14 00:30 | 2023-07-14 02:00 | Phos Ops | 22SD1
PHOS.RD.1060 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Evaporator |  |  | Fill Evaporator with Plantwash & Heat | 0 | Task Dependent | 2023-07-14 02:00 | 2023-07-14 04:30 |  | 1.5 | 2.5 | 2.5 | 2.5 | 2.5 | 0 |  |  | 2023-07-14 02:00 | 2023-07-14 04:30 | Phos Ops | 22SD1
PHOS.RD.1070 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Evaporator |  |  | Wash Evaporator | 0 | Task Dependent | 2023-07-14 04:30 | 2023-07-14 16:30 |  | 1.5 | 12 | 12 | 12 | 12 | 0 |  |  | 2023-07-14 04:30 | 2023-07-14 16:30 | Phos Ops | 22SD1
PHOS.RD.1120 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Evaporator |  |  | Flush Evaporator & drain | 0 | Task Dependent | 2023-07-14 16:30 | 2023-07-14 21:00 |  | 17.5 | 4.5 | 4.5 | 4.5 | 4.5 | 0 |  |  | 2023-07-14 16:30 | 2023-07-14 21:00 | Phos Ops | 22SD1
PHOS.RD.1090 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Reslurry |  |  | Reduce Reslurry Tank to 50% & Flush | 0 | Task Dependent | 2023-07-14 06:00 | 2023-07-14 12:00 |  | 20 | 6 | 6 | 6 | 6 | 0 |  |  | 2023-07-14 06:00 | 2023-07-14 12:00 | Phos Ops | 22SD1
PHOS.RD.1110 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Reslurry |  |  | Drain Reslurry Tank | 0 | Task Dependent | 2023-07-14 12:00 | 2023-07-14 15:00 |  | 20 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-14 12:00 | 2023-07-14 15:00 | Phos Ops | 22SD1
PHOS.RD.1220 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Hemihydrate Reaction |  |  | Lower R2 to 60% Level | 0 | Task Dependent | 2023-07-14 23:00 | 2023-07-15 |  | 0 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-14 23:00 | 2023-07-15 | Phos Ops | 22SD1
PHOS.RD.1160 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Hemihydrate Reaction |  |  | Flush Flash Cooler A Pump | 0 | Task Dependent | 2023-07-14 18:30 | 2023-07-14 19:00 |  | 11.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 18:30 | 2023-07-14 19:00 | Phos Ops | 22SD1
PHOS.RD.1180 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Hemihydrate Reaction |  |  | Flush Reactor Sump Pump | 0 | Task Dependent | 2023-07-14 19:30 | 2023-07-14 20:00 |  | 41.5 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-14 19:30 | 2023-07-14 20:00 | Phos Ops | 22SD1
PHOS.ISO.2050 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Hemihydrate Reaction |  |  | Isolate Flash Cooler B | 0 | Task Dependent | 2023-07-14 18:30 | 2023-07-14 19:30 |  | 0 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-14 18:30 | 2023-07-14 19:30 | Phos Acid Isolator | 22SD1
PHOS.ISO.2140 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Scrubber & Fume Fans |  |  | Isolate Gas Scrubber Fan & Fume Fan | 0 | Task Dependent | 2023-07-15 01:30 | 2023-07-15 03:00 |  | 0 | 1.5 | 1.5 | 3 | 3 | 0 |  |  | 2023-07-15 01:30 | 2023-07-15 03:00 | Phos Acid Isolator | 22SD1
PHOS.ISO.2030 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Rock Filters |  |  | Isolate Rock Filter 1 & 2 | 0 | Task Dependent | 2023-07-14 18:00 | 2023-07-14 19:30 |  | 14 | 1.5 | 1.5 | 3 | 3 | 0 |  |  | 2023-07-14 18:00 | 2023-07-14 19:30 | Phos Acid Isolator | 22SD1
PHOS.ISO.2060 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Rock Filters |  |  | Isolate Reactor Feed Conveyor | 0 | Task Dependent | 2023-07-14 19:30 | 2023-07-14 20:00 |  | 27 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-14 19:30 | 2023-07-14 20:00 | Phos Acid Isolator | 22SD1
PHOS.ISO.2040 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Rock Filters |  |  | Isolate Clothwash, Clothwash Sump & Area Sump Pumps | 0 | Task Dependent | 2023-07-14 18:00 | 2023-07-14 19:00 |  | 39 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-14 18:00 | 2023-07-14 19:00 | Phos Acid Isolator | 22SD1
PHOS.ISO.2120 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Hemihydrate Reaction |  |  | Isolate and Pack Up Acid Mixers | 0 | Task Dependent | 2023-07-14 23:00 | 2023-07-15 02:00 |  | 28.5 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-14 23:00 | 2023-07-15 02:00 | Phos Acid Isolator | 22SD1
PHOS.ISO.2090 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Hemihydrate Reaction |  |  | Isolate HH Recirculation Pump | 0 | Task Dependent | 2023-07-14 21:00 | 2023-07-14 22:00 |  | 32.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-14 21:00 | 2023-07-14 22:00 | Phos Acid Isolator | 22SD1
PHOS.ISO.2190 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Acid Water |  |  | Isolate Hot & Cold Well Pumps | 0 | Task Dependent | 2023-07-15 03:00 | 2023-07-15 06:00 |  | 13.5 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-15 03:00 | 2023-07-15 06:00 | Phos Acid Isolator | 22SD1
PHOS.ISO.2210 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Acid Water |  |  | Isolate & pump out Hotwell w/ diesel pump & Hotwell Pumps | 0 | Task Dependent | 2023-07-15 06:00 | 2023-07-15 09:00 |  | 25.5 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-15 06:00 | 2023-07-15 09:00 | Phos Acid Isolator | 22SD1
PHOS.ISO.2220 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Services |  |  | Isolate Booster Pumps | 0 | Task Dependent | 2023-07-15 06:00 | 2023-07-15 07:00 |  | 52 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-15 06:00 | 2023-07-15 07:00 | Phos Acid Isolator | 22SD1
PHOS.ISO.2100 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Evaporator |  |  | Isolate Evaporator | 0 | Task Dependent | 2023-07-14 21:00 | 2023-07-14 22:00 |  | 17.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-14 21:00 | 2023-07-14 22:00 | Phos Acid Isolator | 22SD1
PHOS.ISO.2160 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Product Filtration |  |  | Isolate Filter Collection Conveyor A | 0 | Task Dependent | 2023-07-15 02:00 | 2023-07-15 02:30 |  | 12 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-15 02:00 | 2023-07-15 02:30 | Phos Acid Isolator | 22SD1
PHOS.ISO.2150 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Product Filtration |  |  | Isolate Filter Collection Conveyor B | 0 | Task Dependent | 2023-07-15 01:30 | 2023-07-15 02:00 |  | 12 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-15 01:30 | 2023-07-15 02:00 | Phos Acid Isolator | 22SD1
PHOS.ISO.2350 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Services |  |  | Isolate Waste Water Tank | 0 | Task Dependent | 2023-07-15 21:00 | 2023-07-15 22:30 |  | 13.5 | 1.5 | 1.5 | 3 | 3 | 0 |  |  | 2023-07-15 21:00 | 2023-07-15 22:30 | Phos Acid Isolator | 22SD1
PHOS.ISO.2230 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Services |  |  | Isolate Steam at Battery Limits | 0 | Task Dependent | 2023-07-15 06:00 | 2023-07-15 06:30 |  | 40.5 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-15 06:00 | 2023-07-15 06:30 | Phos Acid Isolator | 22SD1
PHOS.ISO.2000 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Reslurry |  |  | Isolate OverLand CV | 0 | Task Dependent | 2023-07-14 06:00 | 2023-07-14 06:30 |  | 0 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-14 06:00 | 2023-07-14 06:30 | Phos Acid Isolator | 22SD1
PHOS.ISO.2320 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Services |  |  | Isolate Gland Water System and Tank Inlet Valve | 0 | Task Dependent | 2023-07-15 21:30 | 2023-07-15 23:00 |  | 25 | 1.5 | 1.5 | 3 | 3 | 0 |  |  | 2023-07-15 21:30 | 2023-07-15 23:00 | Phos Acid Isolator | 22SD1
PHOS.ISO.2170 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Hemihydrate Reaction |  |  | Isolate Reactors | 0 | Task Dependent | 2023-07-15 02:00 | 2023-07-15 03:00 |  | 28.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-15 02:00 | 2023-07-15 03:00 | Phos Acid Isolator | 22SD1
PHOS.ISO.2240 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Services |  |  | Isolate Process Water to Reactors | 0 | Task Dependent | 2023-07-15 06:00 | 2023-07-15 07:00 |  | 27.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-15 06:00 | 2023-07-15 07:00 | Phos Acid Isolator | 22SD1
PHOS.ISO.2250 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Product Filtration |  |  | Isolate Train C HH Filters | 0 | Task Dependent | 2023-07-15 06:00 | 2023-07-15 08:00 |  | 29.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-15 06:00 | 2023-07-15 08:00 | Phos Acid Isolator | 22SD1
PHOS.ISO.2070 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Hemihydrate Reaction |  |  | Isolate Flash Cooler A | 0 | Task Dependent | 2023-07-14 19:30 | 2023-07-14 20:30 |  | 11 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-14 19:30 | 2023-07-14 20:30 | Phos Acid Isolator | 22SD1
PHOS.ISO.2260 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Services |  |  | Isolate Steam to Reactors | 0 | Task Dependent | 2023-07-15 06:00 | 2023-07-15 06:30 |  | 40.5 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-15 06:00 | 2023-07-15 06:30 | Phos Acid Isolator | 22SD1
PHOS.ISO.2020 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Reslurry |  |  | Isolate Re-Slurry for Luki & Door Removal | 0 | Task Dependent | 2023-07-14 15:00 | 2023-07-14 16:30 |  | 20 | 1.5 | 1.5 | 3 | 3 | 0 |  |  | 2023-07-14 15:00 | 2023-07-14 16:30 | Phos Acid Isolator | 22SD1
PHOS.ISO.2180 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Reslurry |  |  | Isolate & Amend Reslurry Tk for CSE | 0 | Task Dependent | 2023-07-15 02:00 | 2023-07-15 03:00 |  | 22 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-15 02:00 | 2023-07-15 03:00 | Phos Acid Isolator | 22SD1
PHOS.ISO.2330 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Product Filtration |  |  | Isolate Cake Wash Tank A and Cloth Wash A tanks | 0 | Task Dependent | 2023-07-15 18:00 | 2023-07-15 18:30 |  | 28.5 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-15 18:00 | 2023-07-15 18:30 | Phos Acid Isolator | 22SD1
PHOS.ISO.2280 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Product Filtration |  |  | Isolate Train A HH Filters | 0 | Task Dependent | 2023-07-15 08:00 | 2023-07-15 10:00 |  | 29.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-15 08:00 | 2023-07-15 10:00 | Phos Acid Isolator | 22SD1
PHOS.ISO.2360 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Services |  |  | Isolate Instrument Air | 0 | Task Dependent | 2023-07-15 22:30 | 2023-07-15 23:00 |  | 37 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-15 22:30 | 2023-07-15 23:00 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5250 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Rock Filters |  |  | De-Isolate Rock Filter 1 & 2 | 0 | Task Dependent | 2023-07-16 21:30 | 2023-07-16 23:00 |  | 14 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-16 21:30 | 2023-07-16 23:00 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5270 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Hemihydrate Reaction |  |  | De-Isolate Reactor Feed Conveyor | 0 | Task Dependent | 2023-07-16 23:00 | 2023-07-16 23:30 |  | 14 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 23:00 | 2023-07-16 23:30 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5320 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Rock Filters |  |  | De-Isolate Clothwash, Clothwash Sump & Area Sump Pumps | 0 | Task Dependent | 2023-07-17 02:30 | 2023-07-17 03:30 |  | 11 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-17 02:30 | 2023-07-17 03:30 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5280 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Hemihydrate Reaction |  |  | De-Isolate Flash Cooler A | 0 | Task Dependent | 2023-07-16 23:30 | 2023-07-17 00:30 |  | 14 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-16 23:30 | 2023-07-17 00:30 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5290 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Hemihydrate Reaction |  |  | De-Isolate HH Recirculation Pump | 0 | Task Dependent | 2023-07-16 23:30 | 2023-07-17 00:30 |  | 14 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-16 23:30 | 2023-07-17 00:30 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5340 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Hemihydrate Reaction |  |  | De-Isolate Acid Mixers | 0 | Task Dependent | 2023-07-17 05:00 | 2023-07-17 06:00 |  | 8.5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-17 05:00 | 2023-07-17 06:00 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5060 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Services |  |  | De-Isolate Booster Pumps | 0 | Task Dependent | 2023-07-15 22:30 | 2023-07-15 23:30 |  | 36.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-15 22:30 | 2023-07-15 23:30 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5260 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Product Filtration |  |  | De-Isolate Filter Collection Conveyor A | 0 | Task Dependent | 2023-07-16 21:30 | 2023-07-16 22:00 |  | 16.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 21:30 | 2023-07-16 22:00 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5130 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Product Filtration |  |  | De-Isolate Filter Collection Conveyor B | 0 | Task Dependent | 2023-07-16 13:00 | 2023-07-16 13:30 |  | 37.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 13:00 | 2023-07-16 13:30 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5180 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Services |  |  | De-Isolate Waste Water Tank | 0 | Task Dependent | 2023-07-16 16:00 | 2023-07-16 17:30 |  | 20 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-16 16:00 | 2023-07-16 17:30 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5020 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Rock Filters |  |  | De-Isolate OverLand CV | 0 | Task Dependent | 2023-07-15 02:00 | 2023-07-15 02:30 |  | 59.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 02:00 | 2023-07-15 02:30 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5080 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Services |  |  | De-Isolate Gland Water System | 0 | Task Dependent | 2023-07-16 22:00 | 2023-07-16 23:30 |  | 37 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-16 22:00 | 2023-07-16 23:30 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5230 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Evaporator |  |  | De-Isolate Evaporator | 0 | Task Dependent | 2023-07-16 19:30 | 2023-07-16 21:00 |  | 9.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-16 19:30 | 2023-07-16 21:00 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5210 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Reslurry |  |  | De-Isolate Reslurry Tk after CSE | 0 | Task Dependent | 2023-07-16 17:00 | 2023-07-16 18:00 |  | 7 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-16 17:00 | 2023-07-16 18:00 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5140 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Acid Water |  |  | De-Isolate Hot & Cold Well Pumps | 0 | Task Dependent | 2023-07-16 15:00 | 2023-07-16 17:00 |  | 11 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-16 15:00 | 2023-07-16 17:00 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5330 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Scrubber System |  |  | De-Isolate Gas Scrubber & Fume Extraction Fans | 0 | Task Dependent | 2023-07-17 03:00 | 2023-07-17 04:00 |  | 0 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-17 03:00 | 2023-07-17 04:00 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5350 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Hemihydrate Reaction |  |  | De-Isolate Flash Cooler B | 0 | Task Dependent | 2023-07-18 02:00 | 2023-07-18 03:00 |  | 0 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-18 02:00 | 2023-07-18 03:00 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5040 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Hemihydrate Reaction |  |  | De-Isolate Reactors | 0 | Task Dependent | 2023-07-16 09:30 | 2023-07-16 10:30 |  | 26.5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-16 09:30 | 2023-07-16 10:30 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5310 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Reslurry |  |  | De-Isolate Reslurry Tank | 0 | Task Dependent | 2023-07-17 00:30 | 2023-07-17 02:30 |  | 7 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-17 00:30 | 2023-07-17 02:30 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5220 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Services |  |  | De-Isolate Process Water in Plant | 0 | Task Dependent | 2023-07-16 20:00 | 2023-07-16 21:00 |  | 18.5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-16 20:00 | 2023-07-16 21:00 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5190 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Product Filtration |  |  | De-Isolate Train C HH Filters | 0 | Task Dependent | 2023-07-16 16:00 | 2023-07-16 18:00 |  | 33 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-16 16:00 | 2023-07-16 18:00 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5090 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Services |  |  | De-Isolate Steam to Battery Limits | 0 | Task Dependent | 2023-07-16 04:00 | 2023-07-16 04:30 |  | 23 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 04:00 | 2023-07-16 04:30 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5110 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Product Filtration |  |  | De-Isolate Train A HH Filter A | 0 | Task Dependent | 2023-07-16 09:00 | 2023-07-16 11:00 |  | 27.5 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-16 09:00 | 2023-07-16 11:00 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5100 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Product Filtration |  |  | De-Isolate Cake Wash Tank A and Cloth Wash A tanks | 0 | Task Dependent | 2023-07-16 08:30 | 2023-07-16 09:00 |  | 27.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 08:30 | 2023-07-16 09:00 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5120 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Product Filtration |  |  | De-Isolate Product Tank A and Return Tank A | 0 | Task Dependent | 2023-07-16 09:00 | 2023-07-16 09:30 |  | 41.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 09:00 | 2023-07-16 09:30 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5070 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Services |  |  | De-Isolate Instrument Air | 0 | Task Dependent | 2023-07-15 23:00 | 2023-07-15 23:30 |  | 37 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 23:00 | 2023-07-15 23:30 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5300 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Services |  |  | De-Isolate Steam to Reactors | 0 | Task Dependent | 2023-07-16 23:30 | 2023-07-17 |  | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 23:30 | 2023-07-17 | Phos Acid Isolator | 22SD1
PHOS.RU.6000 | Not Started | GLSTest-01.PHOS.RU | PHOS | Phos Acid | Ramp Up - Hemihydrate Reaction |  |  | Increase Reactor Temp with Steam | 0 | Task Dependent | 2023-07-17 04:00 | 2023-07-17 14:00 |  | 0 | 10 | 10 | 10 | 10 | 0 |  |  | 2023-07-17 04:00 | 2023-07-17 14:00 | Phos Ops | 22SD1
PHOS.RU.6040 | Not Started | GLSTest-01.PHOS.RU | PHOS | Phos Acid | Ramp Up - Hemihydrate Reaction |  |  | Sample reactors for Pre-Feed | 0 | Task Dependent | 2023-07-17 14:00 | 2023-07-17 14:30 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-17 14:00 | 2023-07-17 14:30 | Phos Ops | 22SD1
PHOS.RU.6050 | Not Started | GLSTest-01.PHOS.RU | PHOS | Phos Acid | Ramp Up - Hemihydrate Reaction |  |  | Pre-Feed | 0 | Task Dependent | 2023-07-17 14:30 | 2023-07-17 15:00 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-17 14:30 | 2023-07-17 15:00 | Phos Ops | 22SD1
PHOS.RU.6020 | Not Started | GLSTest-01.PHOS.RU | PHOS | Phos Acid | Ramp Up Activities - Evaporator |  |  | Fill Evap | 0 | Task Dependent | 2023-07-17 06:30 | 2023-07-17 08:00 |  | 0 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-17 06:30 | 2023-07-17 08:00 | Phos Ops | 22SD1
PHOS.RU.6030 | Not Started | GLSTest-01.PHOS.RU | PHOS | Phos Acid | Ramp Up Activities - Evaporator |  |  | Heat Evap | 0 | Task Dependent | 2023-07-17 08:00 | 2023-07-17 12:00 |  | 0 | 4 | 4 | 4 | 4 | 0 |  |  | 2023-07-17 08:00 | 2023-07-17 12:00 | Phos Ops | 22SD1
ISOL4000 | Not Started | GLSTest-01.PWR.ISO | PWR | Power Station | Isolations |  |  | Isolate GT1 & OTSG 1 * | 0 | Task Dependent | 2023-07-16 08:00 | 2023-07-16 10:00 |  | 48 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-16 08:00 | 2023-07-16 10:00 | Pwr Ops | 22SD1
ISOL4010 | Not Started | GLSTest-01.PWR.ISO | PWR | Power Station | Isolations |  |  | Isolate GT2 & OTSG 2 * | 0 | Task Dependent | 2023-07-15 | 2023-07-15 02:00 |  | 48 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-15 | 2023-07-15 02:00 | Pwr Ops | 22SD1
ISOL4030 | Not Started | GLSTest-01.PWR.ISO | PWR | Power Station | Isolations |  |  | Isolate GT4 & OTSG 4 * | 0 | Task Dependent | 2023-07-13 | 2023-07-13 02:00 |  | 48 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-13 | 2023-07-13 02:00 | Pwr Ops | 22SD1
DE-ISOL4000 | Not Started | GLSTest-01.PWR.DE-ISO | PWR | Power Station | De-isolations |  |  | De-Isolate GT1 & OTSG 1 | 0 | Task Dependent | 2023-07-16 13:00 | 2023-07-16 15:00 |  | 40 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-16 13:00 | 2023-07-16 15:00 | Pwr Ops | 22SD1
DE-ISOL4010 | Not Started | GLSTest-01.PWR.DE-ISO | PWR | Power Station | De-isolations |  |  | De-Isolate GT2 & OTSG 2 | 0 | Task Dependent | 2023-07-16 04:00 | 2023-07-16 08:00 |  | 40 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-16 04:00 | 2023-07-16 08:00 | Pwr Ops | 22SD1
DE-ISOL4030 | Not Started | GLSTest-01.PWR.DE-ISO | PWR | Power Station | De-isolations |  |  | De-Isolate GT4 & OTSG 4 | 0 | Task Dependent | 2023-07-14 22:00 | 2023-07-15 |  | 40 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-14 22:00 | 2023-07-15 | Pwr Ops | 22SD1
10770043 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4626 | CLEAN 1 | Granulation | 10770043 - 60W HPWB Cln GranSD Coating Oil Tank | 10770043 | 0010 | 60W HPWB Cln Coating Oil Tank Shut | 0 | Task Dependent | 2023-07-13 21:30 | 2023-07-14 01:30 |  | 28 | 4 | 4 | 20 | 20 | 0 |  |  | 2023-07-13 21:30 | 2023-07-14 01:30 | Waterblast Truck, Vac Truck, Cleaning Ops | 23SD2
10785031 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10785031 - 15W HPWB Cln PhosSD 44CO4002 | 10785031 | 0010 | Issue Permit - 10785031 - 15W HPWB Cln PhosSD 44CO4002 | 0 | Task Dependent | 2023-07-16 08:00 | 2023-07-16 08:30 |  | 13 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 08:00 | 2023-07-16 08:30 | Phos Permit Issuer | 23SD2
10785031 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10785031 - 15W HPWB Cln PhosSD 44CO4002 | 10785031 | 0020 | Clean Scrubber | 0 | Task Dependent | 2023-07-16 08:30 | 2023-07-16 10:30 |  | 13 | 2 | 2 | 6 | 6 | 0 |  |  | 2023-07-16 08:30 | 2023-07-16 10:30 | Cleaning Ops, Waterblast Truck | 23SD2
10785031 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10785031 - 15W HPWB Cln PhosSD 44CO4002 | 10785031 | 0040 | Inspect After HPWB | 0 | Task Dependent | 2023-07-16 10:30 | 2023-07-16 11:30 |  | 13 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-16 10:30 | 2023-07-16 11:30 | Static Engineer | 23SD2
10785031 - 0050 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10785031 - 15W HPWB Cln PhosSD 44CO4002 | 10785031 | 0050 | Close Permit - 10785031 - 15W HPWB Cln PhosSD 44CO4002 | 0 | Task Dependent | 2023-07-16 11:30 | 2023-07-16 12:00 |  | 13 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 11:30 | 2023-07-16 12:00 | Phos Permit Issuer | 23SD2
10788561 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10788561 - 15W HPWB Cln PhosSD 44CO4001 | 10788561 | 0010 | Issue Permit - 10788561 - 15W HPWB Cln PhosSD 44CO4001 | 0 | Task Dependent | 2023-07-15 03:00 | 2023-07-15 03:30 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 03:00 | 2023-07-15 03:30 | Phos Permit Issuer | 23SD2
10788561 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10788561 - 15W HPWB Cln PhosSD 44CO4001 | 10788561 | 0020 | Clean Scrubber | 0 | Task Dependent | 2023-07-15 20:30 | 2023-07-16 08:30 |  | 0 | 10 | 10 | 30 | 30 | 0 |  |  | 2023-07-15 20:30 | 2023-07-16 08:30 | Cleaning Ops, Waterblast Truck | 23SD2
10788561 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10788561 - 15W HPWB Cln PhosSD 44CO4001 | 10788561 | 0040 | Close Permit - 10788561 - 15W HPWB Cln PhosSD 44CO4001 | 0 | Task Dependent | 2023-07-17 02:30 | 2023-07-17 03:00 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-17 02:30 | 2023-07-17 03:00 | Phos Permit Issuer | 23SD2
10789711 - 0005 | Not Started | GLSTest-01.GRAN.MAINT.4623 | CLEAN 1 | Granulation | 10789711 - 15W HPWB Cln GranSD 2ndry Elevator Chute | 10789711 | 0005 | Issue permit - 10789711 - 15W HPWB Cln GranSD 2ndry Elevator Chute | 0 | Task Dependent | 2023-07-12 21:00 | 2023-07-12 21:30 |  | 11 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 21:00 | 2023-07-12 21:30 | Gran Permit Issuer | 23SD2
10789711 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4623 | CLEAN 1 | Granulation | 10789711 - 15W HPWB Cln GranSD 2ndry Elevator Chute | 10789711 | 0020 | HPWB 2ndry Elevator Chute | 0 | Task Dependent | 2023-07-12 21:30 | 2023-07-12 22:30 |  | 11 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-12 21:30 | 2023-07-12 22:30 | Waterblast Truck, Cleaning Ops | 23SD2
10789711 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4623 | CLEAN 1 | Granulation | 10789711 - 15W HPWB Cln GranSD 2ndry Elevator Chute | 10789711 | 0040 | Close Permit - 10789711 - 15W HPWB Cln GranSD 2ndry Elevator Chute | 0 | Task Dependent | 2023-07-12 22:30 | 2023-07-12 23:00 |  | 56 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 22:30 | 2023-07-12 23:00 | Gran Permit Issuer | 23SD2
10789729 - 0005 | Not Started | GLSTest-01.GRAN.MAINT.4622 | CLEAN 1 | Granulation | 10789729 - 15W HPWB Cln GranSD Dryer Trunnions | 10789729 | 0005 | Issue permit - 10789729 - 15W HPWB Cln GranSD Dryer Trunnions | 0 | Task Dependent | 2023-07-13 15:00 | 2023-07-13 15:30 |  | 28 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 15:00 | 2023-07-13 15:30 | Gran Permit Issuer | 23SD2
10789729 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | CLEAN 1 | Granulation | 10789729 - 15W HPWB Cln GranSD Dryer Trunnions | 10789729 | 0020 | 15W HPWB Cln Dryer Trunnions Shut | 0 | Task Dependent | 2023-07-13 15:30 | 2023-07-13 21:30 |  | 28 | 4 | 4 | 12 | 12 | 0 |  |  | 2023-07-13 15:30 | 2023-07-13 21:30 | Waterblast Truck, Cleaning Ops | 23SD2
10789729 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4622 | CLEAN 1 | Granulation | 10789729 - 15W HPWB Cln GranSD Dryer Trunnions | 10789729 | 0040 | Close Permit - 10789729 - 15W HPWB Cln GranSD Dryer Trunnions | 0 | Task Dependent | 2023-07-13 21:30 | 2023-07-13 22:00 |  | 37 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 21:30 | 2023-07-13 22:00 | Gran Permit Issuer | 23SD2
10789868 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4475 | PHOS | Phos Acid | 10789868 - 15W HPWB Cln PhosSD 44MS3008 | 10789868 | 0010 | Issue Permit - 10789868 - 15W HPWB Cln PhosSD 44MS3008 | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 07:30 |  | 10.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 07:30 | Phos Permit Issuer | 23SD2
10789868 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4475 | PHOS | Phos Acid | 10789868 - 15W HPWB Cln PhosSD 44MS3008 | 10789868 | 0020 | Western Trenches - Mini Excavator Digout | 0 | Task Dependent | 2023-07-16 01:30 | 2023-07-16 10:00 |  | 10.5 | 6.5 | 6.5 | 13 | 13 | 0 |  |  | 2023-07-16 01:30 | 2023-07-16 10:00 | T/A, Phos Ops, Mini Excavator, Bobcat | 23SD2
10789868 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4475 | PHOS | Phos Acid | 10789868 - 15W HPWB Cln PhosSD 44MS3008 | 10789868 | 0030 | HPWB & Vac South Trenches (VacPump) | 0 | Task Dependent | 2023-07-16 03:30 | 2023-07-16 11:30 |  | 9 | 6 | 6 | 30 | 30 | 0 |  |  | 2023-07-16 03:30 | 2023-07-16 11:30 | Vac Truck, Cleaning Ops, Waterblast Truck | 23SD2
10789868 - 0050 | Not Started | GLSTest-01.PHOS.MAINT.4475 | PHOS | Phos Acid | 10789868 - 15W HPWB Cln PhosSD 44MS3008 | 10789868 | 0050 | Remove Scaff barrier | 0 | Task Dependent | 2023-07-16 11:30 | 2023-07-16 13:30 |  | 9 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-16 11:30 | 2023-07-16 13:30 | Scaffolder | 23SD2
10789868 - 0060 | Not Started | GLSTest-01.PHOS.MAINT.4475 | PHOS | Phos Acid | 10789868 - 15W HPWB Cln PhosSD 44MS3008 | 10789868 | 0060 | Reinstate Grating | 0 | Task Dependent | 2023-07-16 13:30 | 2023-07-16 14:30 |  | 9 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-16 13:30 | 2023-07-16 14:30 | Franna, Rigger, Crane Operator | 23SD2
10789868 - 0011 | Not Started | GLSTest-01.PHOS.MAINT.4475 | PHOS | Phos Acid | 10789868 - 15W HPWB Cln PhosSD 44MS3008 | 10789868 | 0070 | Remove Grating | 0 | Task Dependent | 2023-07-15 07:30 | 2023-07-15 08:30 |  | 10.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-15 07:30 | 2023-07-15 08:30 | Crane Operator, Rigger, Franna | 23SD2
10789868 - 0090 | Not Started | GLSTest-01.PHOS.MAINT.4475 | PHOS | Phos Acid | 10789868 - 15W HPWB Cln PhosSD 44MS3008 | 10789868 | 0090 | Close Permit - 10789868 - 15W HPWB Cln PhosSD 44MS3008 | 0 | Task Dependent | 2023-07-16 14:30 | 2023-07-16 15:00 |  | 9 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 14:30 | 2023-07-16 15:00 | Phos Permit Issuer | 23SD2
10789897 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10789897 - 15W HPWB Cln Scrb Dctng PhosSD 99SC01 | 10789897 | 0010 | Issue Permit - 10789897 - 15W HPWB Cln Scrb Dctng PhosSD 99SC01 | 0 | Task Dependent | 2023-07-15 07:30 | 2023-07-15 08:00 |  | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 07:30 | 2023-07-15 08:00 | Phos Permit Issuer | 23SD2
10789897 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10789897 - 15W HPWB Cln Scrb Dctng PhosSD 99SC01 | 10789897 | 0020 | Clean inside Scrubber ducting | 0 | Task Dependent | 2023-07-15 09:00 | 2023-07-15 17:00 |  | 4 | 8 | 8 | 16 | 16 | 0 |  |  | 2023-07-15 09:00 | 2023-07-15 17:00 | Waterblast Truck, Cleaning Ops | 23SD2
10789897 - 0015 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10789897 - 15W HPWB Cln Scrb Dctng PhosSD 99SC01 | 10789897 | 0030 | Open Hatches | 0 | Task Dependent | 2023-07-15 08:00 | 2023-07-15 09:00 |  | 4 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-15 08:00 | 2023-07-15 09:00 | Fitter | 23SD2
10789897 - 0050 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10789897 - 15W HPWB Cln Scrb Dctng PhosSD 99SC01 | 10789897 | 0050 | Close Permit - 10789897 - 15W HPWB Cln Scrb Dctng PhosSD 99SC01 | 0 | Task Dependent | 2023-07-15 20:00 | 2023-07-15 20:30 |  | 26.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 20:00 | 2023-07-15 20:30 | Phos Permit Issuer | 23SD2
10789898 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10789898 - 15W HPWB Cln PhosSD 44FC4002 | 10789898 | 0010 | Issue Permit - 10789898 - 15W HPWB Cln PhosSD 44FC4002 | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 07:30 |  | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 07:30 | Phos Permit Issuer | 23SD2
10789898 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10789898 - 15W HPWB Cln PhosSD 44FC4002 | 10789898 | 0020 | Sandblast Impeller | 0 | Task Dependent | 2023-07-16 | 2023-07-16 03:00 |  | 4 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-16 | 2023-07-16 03:00 | Sandblast, Cleaning Ops | 23SD2
10789898 - 0050 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10789898 - 15W HPWB Cln PhosSD 44FC4002 | 10789898 | 0050 | Vac Out Fan | 0 | Task Dependent | 2023-07-16 03:00 | 2023-07-16 04:00 |  | 4 | 1 | 1 | 3 | 3 | 0 |  |  | 2023-07-16 03:00 | 2023-07-16 04:00 | Cleaning Ops, Vac Truck | 23SD2
10789898 - 0070 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10789898 - 15W HPWB Cln PhosSD 44FC4002 | 10789898 | 0070 | Close Permit - 10789898 - 15W HPWB Cln PhosSD 44FC4002 | 0 | Task Dependent | 2023-07-16 19:30 | 2023-07-16 20:00 |  | 7 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 19:30 | 2023-07-16 20:00 | Phos Permit Issuer | 23SD2
10789899 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10789899 - 15W HPWB Cln PhosSD 44FC4001 | 10789899 | 0010 | Issue Permit - 10789899 - 15W HPWB Cln PhosSD 44FC4001 | 0 | Task Dependent | 2023-07-15 20:30 | 2023-07-15 21:00 |  | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 20:30 | 2023-07-15 21:00 | Phos Permit Issuer | 23SD2
10789899 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10789899 - 15W HPWB Cln PhosSD 44FC4001 | 10789899 | 0030 | Sandblast Impeller | 0 | Task Dependent | 2023-07-15 21:00 | 2023-07-16 |  | 4 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-15 21:00 | 2023-07-16 | Sandblast, Cleaning Ops | 23SD2
10789899 - 0060 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10789899 - 15W HPWB Cln PhosSD 44FC4001 | 10789899 | 0060 | Vac Out Fan | 0 | Task Dependent | 2023-07-16 | 2023-07-16 01:00 |  | 6 | 1 | 1 | 3 | 3 | 0 |  |  | 2023-07-16 | 2023-07-16 01:00 | Cleaning Ops, Vac Truck | 23SD2
10789899 - 0080 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10789899 - 15W HPWB Cln PhosSD 44FC4001 | 10789899 | 0080 | Close Permit - 10789899 - 15W HPWB Cln PhosSD 44FC4001 | 0 | Task Dependent | 2023-07-16 01:00 | 2023-07-16 01:30 |  | 21.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 01:00 | 2023-07-16 01:30 | Phos Permit Issuer | 23SD2
10793062 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4445 | DAWSON3 | Phos Acid | 10793062 - 15W HPWB Cln EvapSD 44HE4503 | 10793062 | 0010 | Remove Evap Spray Spool Pieces | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 10:00 |  | 9 | 3 | 3 | 18 | 18 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 10:00 | 55t Crane, Crane Operator, Rigger, Fitter | 23SD2
10793062 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4445 | DAWSON3 | Phos Acid | 10793062 - 15W HPWB Cln EvapSD 44HE4503 | 10793062 | 0020 | Inspect Evap Spray Spool Pieces | 0 | Task Dependent | 2023-07-15 10:00 | 2023-07-15 11:00 |  | 9 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-15 10:00 | 2023-07-15 11:00 | Maintenance Engineer | 23SD2
10793062 - 0060 | Not Started | GLSTest-01.PHOS.MAINT.4445 | DAWSON3 | Phos Acid | 10793062 - 15W HPWB Cln EvapSD 44HE4503 | 10793062 | 0060 | CS - Remove Evap Cond Sprays | 0 | Task Dependent | 2023-07-15 11:00 | 2023-07-15 17:00 |  | 9 | 6 | 6 | 12 | 12 | 0 |  |  | 2023-07-15 11:00 | 2023-07-15 17:00 | Fitter | 23SD2
10793062 - 0070 | Not Started | GLSTest-01.PHOS.MAINT.4445 | CLEAN 2 | Phos Acid | 10793062 - 15W HPWB Cln EvapSD 44HE4503 | 10793062 | 0070 | Clean Evap Cond Sprays | 0 | Task Dependent | 2023-07-15 19:00 | 2023-07-15 23:00 |  | 9 | 4 | 4 | 12 | 12 | 0 |  |  | 2023-07-15 19:00 | 2023-07-15 23:00 | Waterblast Truck, Cleaning Ops | 23SD2
10793062 - 0090 | Not Started | GLSTest-01.PHOS.MAINT.4445 | DAWSON3 | Phos Acid | 10793062 - 15W HPWB Cln EvapSD 44HE4503 | 10793062 | 0090 | CS - Re-instate Evap Cond Sprays | 0 | Task Dependent | 2023-07-15 23:00 | 2023-07-16 05:00 |  | 9 | 6 | 6 | 12 | 12 | 0 |  |  | 2023-07-15 23:00 | 2023-07-16 05:00 | Fitter | 23SD2
10793062 - 0100 | Not Started | GLSTest-01.PHOS.MAINT.4445 | DAWSON3 | Phos Acid | 10793062 - 15W HPWB Cln EvapSD 44HE4503 | 10793062 | 0100 | Reinstate Evap Spray Spools | 0 | Task Dependent | 2023-07-16 07:00 | 2023-07-16 10:00 |  | 9 | 3 | 3 | 12 | 12 | 0 |  |  | 2023-07-16 07:00 | 2023-07-16 10:00 | 55t Crane, Crane Operator, Rigger, Fitter | 23SD2
10793062 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4445 | DAWSON3 | Phos Acid | 10793062 - 15W HPWB Cln EvapSD 44HE4503 | 10793062 | 0140 | Issue Permit - 10793062 - 15W HPWB Cln EvapSD 44HE4503 | 0 | Task Dependent | 2023-07-15 04:30 | 2023-07-15 05:00 |  | 9 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 04:30 | 2023-07-15 05:00 | Phos Permit Issuer | 23SD2
10793062 - 0150 | Not Started | GLSTest-01.PHOS.MAINT.4445 | DAWSON3 | Phos Acid | 10793062 - 15W HPWB Cln EvapSD 44HE4503 | 10793062 | 0150 | Close Permit - 10793062 - 15W HPWB Cln EvapSD 44HE4503 | 0 | Task Dependent | 2023-07-16 10:00 | 2023-07-16 10:30 |  | 9 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 10:00 | 2023-07-16 10:30 | Phos Permit Issuer | 23SD2
10794307 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4425 | CLEAN 1 | Phos Acid | 10794307 - 15W HPWB Cln Lndr PhosSD 44TK0026 | 10794307 | 0010 | Issue Permit - 10794307 - 15W HPWB Cln Lndr PhosSD 44TK0026 | 0 | Task Dependent | 2023-07-15 02:30 | 2023-07-15 03:00 |  | 22.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 02:30 | 2023-07-15 03:00 | Phos Permit Issuer | 23SD2
10794307 - 0060 | Not Started | GLSTest-01.PHOS.MAINT.4425 | CLEAN 1 | Phos Acid | 10794307 - 15W HPWB Cln Lndr PhosSD 44TK0026 | 10794307 | 0060 | Inspect after Clean | 0 | Task Dependent | 2023-07-15 15:00 | 2023-07-15 15:30 |  | 22.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 15:00 | 2023-07-15 15:30 | Phos Acid Engineer | 23SD2
10794307 - 0080 | Not Started | GLSTest-01.PHOS.MAINT.4425 | CLEAN 1 | Phos Acid | 10794307 - 15W HPWB Cln Lndr PhosSD 44TK0026 | 10794307 | 0080 | Close Permit - 10794307 - 15W HPWB Cln Lndr PhosSD 44TK0026 | 0 | Task Dependent | 2023-07-15 19:30 | 2023-07-15 20:00 |  | 22.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 19:30 | 2023-07-15 20:00 | Phos Permit Issuer | 23SD2
10796630 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4625 | CLEAN 2 | Granulation | 10796630 - 15W HPWB Cln Elev GranSD 46CC2501 | 10796630 | 0010 | Issue Permit - 10796630 - 15W HPWB Cln Elev GranSD 46CC2501 | 0 | Task Dependent | 2023-07-12 09:00 | 2023-07-12 09:30 |  | 59 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 09:00 | 2023-07-12 09:30 | Gran Permit Issuer | 23SD2
10796630 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4625 | CLEAN 2 | Granulation | 10796630 - 15W HPWB Cln Elev GranSD 46CC2501 | 10796630 | 0020 | Water Blast Elevator Boot | 0 | Task Dependent | 2023-07-12 09:30 | 2023-07-12 11:30 |  | 59 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-12 09:30 | 2023-07-12 11:30 | Cleaning Ops, Waterblast Truck | 23SD2
10796630 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4625 | CLEAN 2 | Granulation | 10796630 - 15W HPWB Cln Elev GranSD 46CC2501 | 10796630 | 0040 | Close Permit - 10796630 - 15W HPWB Cln Elev GranSD 46CC2501 | 0 | Task Dependent | 2023-07-12 11:30 | 2023-07-12 12:00 |  | 65 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 11:30 | 2023-07-12 12:00 | Gran Permit Issuer | 23SD2
10796631 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4625 | CLEAN 1 | Granulation | 10796631 - 15W HPWB Cln GranSD 46FC2501 | 10796631 | 0010 | Issue Permit - 10796631 - 15W HPWB Cln GranSD 46FC2501 | 0 | Task Dependent | 2023-07-14 06:30 | 2023-07-14 07:00 |  | 7 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 06:30 | 2023-07-14 07:00 | Gran Permit Issuer | 23SD2
10796631 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4625 | CLEAN 1 | Granulation | 10796631 - 15W HPWB Cln GranSD 46FC2501 | 10796631 | 0030 | Sandblast Impeller (CSE) | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 10:00 |  | 7 | 3 | 3 | 9 | 9 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 10:00 | Sandblast, Cleaning Ops | 23SD2
10796631 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4625 | CLEAN 1 | Granulation | 10796631 - 15W HPWB Cln GranSD 46FC2501 | 10796631 | 0040 | Vac out Fans | 0 | Task Dependent | 2023-07-14 10:00 | 2023-07-14 11:00 |  | 21 | 1 | 1 | 3 | 3 | 0 |  |  | 2023-07-14 10:00 | 2023-07-14 11:00 | Cleaning Ops, Vac Truck | 23SD2
10796631 - 0070 | Not Started | GLSTest-01.GRAN.MAINT.4625 | CLEAN 1 | Granulation | 10796631 - 15W HPWB Cln GranSD 46FC2501 | 10796631 | 0070 | Close Permit - 10796631 - 15W HPWB Cln GranSD 46FC2501 | 0 | Task Dependent | 2023-07-14 11:00 | 2023-07-14 11:30 |  | 21 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 11:00 | 2023-07-14 11:30 | Gran Permit Issuer | 23SD2
10796691 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4623 | CLEAN 1 | Granulation | 10796691 - 15W HPWB Cln GranSD 46CB2401 | 10796691 | 0010 | Issue Permit - 10796691 - 15W HPWB Cln GranSD 46CB2401 | 0 | Task Dependent | 2023-07-12 21:30 | 2023-07-12 22:00 |  | 11 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 21:30 | 2023-07-12 22:00 | Gran Permit Issuer | 23SD2
10796691 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4623 | CLEAN 1 | Granulation | 10796691 - 15W HPWB Cln GranSD 46CB2401 | 10796691 | 0030 | Pre clean inspection | 0 | Task Dependent | 2023-07-12 22:00 | 2023-07-12 22:30 |  | 11 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 22:00 | 2023-07-12 22:30 | Granulation Engineer | 23SD2
10796691 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4623 | CLEAN 1 | Granulation | 10796691 - 15W HPWB Cln GranSD 46CB2401 | 10796691 | 0040 | Clean Fines Conveyor Discharge Chute | 0 | Task Dependent | 2023-07-12 22:30 | 2023-07-13 00:30 |  | 11 | 2 | 2 | 6 | 6 | 0 |  |  | 2023-07-12 22:30 | 2023-07-13 00:30 | Waterblast Truck, Cleaning Ops | 23SD2
10796691 - 0060 | Not Started | GLSTest-01.GRAN.MAINT.4623 | CLEAN 1 | Granulation | 10796691 - 15W HPWB Cln GranSD 46CB2401 | 10796691 | 0060 | Post clean inspection | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 01:00 |  | 53.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 01:00 | Granulation Engineer | 23SD2
10796691 - 0070 | Not Started | GLSTest-01.GRAN.MAINT.4623 | CLEAN 1 | Granulation | 10796691 - 15W HPWB Cln GranSD 46CB2401 | 10796691 | 0070 | Close Permit - 10796691 - 15W HPWB Cln GranSD 46CB2401 | 0 | Task Dependent | 2023-07-13 01:00 | 2023-07-13 01:30 |  | 53.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 01:00 | 2023-07-13 01:30 | Gran Permit Issuer | 23SD2
10796692 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4623 | CLEAN 2 | Granulation | 10796692 - 15W HPWB Cln Elev GranSD 46CC2401 | 10796692 | 0010 | Issue Permit - 10796692 - 15W HPWB Cln Elev GranSD 46CC2401 | 0 | Task Dependent | 2023-07-12 11:00 | 2023-07-12 11:30 |  | 59 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 11:00 | 2023-07-12 11:30 | Gran Permit Issuer | 23SD2
10796692 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4623 | CLEAN 2 | Granulation | 10796692 - 15W HPWB Cln Elev GranSD 46CC2401 | 10796692 | 0020 | Water Blast Elevator Boot | 0 | Task Dependent | 2023-07-12 11:30 | 2023-07-12 13:30 |  | 59 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-12 11:30 | 2023-07-12 13:30 | Cleaning Ops, Waterblast Truck | 23SD2
10796692 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4623 | CLEAN 2 | Granulation | 10796692 - 15W HPWB Cln Elev GranSD 46CC2401 | 10796692 | 0040 | Close Permit - 10796692 - 15W HPWB Cln Elev GranSD 46CC2401 | 0 | Task Dependent | 2023-07-12 13:30 | 2023-07-12 14:00 |  | 65.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 13:30 | 2023-07-12 14:00 | Gran Permit Issuer | 23SD2
10797868 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4621 | CLEAN 2 | Granulation | 10797868 - 15W HPWB Cln GranSD 46TK2101 | 10797868 | 0010 | Issue Permit - 10797868 - 15W HPWB Cln GranSD 46TK2101 | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 01:00 |  | 8 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 01:00 | Gran Permit Issuer | 23SD2
10797868 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4621 | CLEAN 2 | Granulation | 10797868 - 15W HPWB Cln GranSD 46TK2101 | 10797868 | 0020 | Clean PN Ammonia Spargers | 0 | Task Dependent | 2023-07-13 12:00 | 2023-07-13 14:00 |  | 0 | 2 | 2 | 6 | 6 | 0 |  |  | 2023-07-13 12:00 | 2023-07-13 14:00 | Waterblast Truck, Cleaning Ops | 23SD2
10797868 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4621 | CLEAN 2 | Granulation | 10797868 - 15W HPWB Cln GranSD 46TK2101 | 10797868 | 0030 | HPWB PN Vessel | 0 | Task Dependent | 2023-07-13 14:00 | 2023-07-13 22:00 |  | 0 | 6 | 6 | 18 | 18 | 0 |  |  | 2023-07-13 14:00 | 2023-07-13 22:00 | Waterblast Truck, Cleaning Ops | 23SD2
10797868 - 0060 | Not Started | GLSTest-01.GRAN.MAINT.4621 | CLEAN 2 | Granulation | 10797868 - 15W HPWB Cln GranSD 46TK2101 | 10797868 | 0060 | Remove Sparger Caps | 0 | Task Dependent | 2023-07-13 01:00 | 2023-07-13 02:00 |  | 8 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-13 01:00 | 2023-07-13 02:00 | Fitter | 23SD2
10797868 - 0070 | Not Started | GLSTest-01.GRAN.MAINT.4621 | CLEAN 2 | Granulation | 10797868 - 15W HPWB Cln GranSD 46TK2101 | 10797868 | 0070 | Inspection - Static & Process Engineers | 0 | Task Dependent | 2023-07-13 22:00 | 2023-07-13 22:30 |  | 28.5 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-13 22:00 | 2023-07-13 22:30 | Static Engineer, Granulation Engineer | 23SD2
10797868 - 0090 | Not Started | GLSTest-01.GRAN.MAINT.4621 | CLEAN 2 | Granulation | 10797868 - 15W HPWB Cln GranSD 46TK2101 | 10797868 | 0090 | Close Permit - 10797868 - 15W HPWB Cln GranSD 46TK2101 | 0 | Task Dependent | 2023-07-13 23:30 | 2023-07-14 |  | 30.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 23:30 | 2023-07-14 | Gran Permit Issuer | 23SD2
10797932 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | CLEAN 1 | Granulation | 10797932 - 15W HPWB Cln GranSD 46MX2201 | 10797932 | 0010 | Issue permit - 10797932 - 15W HPWB Cln GranSD 46MX2201 | 0 | Task Dependent | 2023-07-12 23:00 | 2023-07-12 23:30 |  | 11 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 23:00 | 2023-07-12 23:30 | Gran Permit Issuer | 23SD2
10797932 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | CLEAN 1 | Granulation | 10797932 - 15W HPWB Cln GranSD 46MX2201 | 10797932 | 0020 | Pre clean inspection | 0 | Task Dependent | 2023-07-12 23:30 | 2023-07-13 00:30 |  | 11 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-12 23:30 | 2023-07-13 00:30 | Granulation Engineer | 23SD2
10797932 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | CLEAN 1 | Granulation | 10797932 - 15W HPWB Cln GranSD 46MX2201 | 10797932 | 0030 | HPWB Granulator Internal | 0 | Task Dependent | 2023-07-13 02:30 | 2023-07-13 09:30 |  | 9 | 5 | 5 | 15 | 15 | 0 |  |  | 2023-07-13 02:30 | 2023-07-13 09:30 | Waterblast Truck, Cleaning Ops | 23SD2
10797932 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4622 | CLEAN 1 | Granulation | 10797932 - 15W HPWB Cln GranSD 46MX2201 | 10797932 | 0040 | Post clean internal inspection | 0 | Task Dependent | 2023-07-13 09:30 | 2023-07-13 10:30 |  | 9 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-13 09:30 | 2023-07-13 10:30 | Granulation Engineer | 23SD2
10797932 - 0050 | Not Started | GLSTest-01.GRAN.MAINT.4622 | CLEAN 1 | Granulation | 10797932 - 15W HPWB Cln GranSD 46MX2201 | 10797932 | 0050 | HPWB Floor Under Granulator | 0 | Task Dependent | 2023-07-13 09:30 | 2023-07-13 11:30 |  | 9 | 2 | 2 | 6 | 6 | 0 |  |  | 2023-07-13 09:30 | 2023-07-13 11:30 | Waterblast Truck, Cleaning Ops | 23SD2
10797932 - 0060 | Not Started | GLSTest-01.GRAN.MAINT.4622 | CLEAN 1 | Granulation | 10797932 - 15W HPWB Cln GranSD 46MX2201 | 10797932 | 0060 | Post clean under Granulator inspection | 0 | Task Dependent | 2023-07-13 11:30 | 2023-07-13 12:30 |  | 35 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-13 11:30 | 2023-07-13 12:30 | Granulation Engineer | 23SD2
10797932 - 0080 | Not Started | GLSTest-01.GRAN.MAINT.4622 | CLEAN 1 | Granulation | 10797932 - 15W HPWB Cln GranSD 46MX2201 | 10797932 | 0080 | Close Permit - 10797932 - 15W HPWB Cln GranSD 46MX2201 | 0 | Task Dependent | 2023-07-13 12:30 | 2023-07-13 13:00 |  | 35 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 12:30 | 2023-07-13 13:00 | Gran Permit Issuer | 23SD2
10797949 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | CLEAN 2 | Granulation | 10797949 - 15W HPWB Cln Elev GranSD 46CC2301 | 10797949 | 0010 | Issue Permit - 10797949 - 15W HPWB Cln Elev GranSD 46CC2301 | 0 | Task Dependent | 2023-07-12 13:00 | 2023-07-12 13:30 |  | 59 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 13:00 | 2023-07-12 13:30 | Gran Permit Issuer | 23SD2
10797949 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | CLEAN 2 | Granulation | 10797949 - 15W HPWB Cln Elev GranSD 46CC2301 | 10797949 | 0020 | Water Blast Elevator Boot | 0 | Task Dependent | 2023-07-12 13:30 | 2023-07-12 15:30 |  | 59 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-12 13:30 | 2023-07-12 15:30 | Cleaning Ops, Waterblast Truck | 23SD2
10797949 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4622 | CLEAN 2 | Granulation | 10797949 - 15W HPWB Cln Elev GranSD 46CC2301 | 10797949 | 0040 | Close Permit - 10797949 - 15W HPWB Cln Elev GranSD 46CC2301 | 0 | Task Dependent | 2023-07-12 15:30 | 2023-07-12 16:00 |  | 61 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 15:30 | 2023-07-12 16:00 | Gran Permit Issuer | 23SD2
10797950 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | CLEAN 1 | Granulation | 10797950 - 15W HPWB Cln GranSD 46CK2401 | 10797950 | 0010 | Issue Permit - 10797950 - 15W HPWB Cln GranSD 46CK2401 | 0 | Task Dependent | 2023-07-12 09:00 | 2023-07-12 09:30 |  | 3.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 09:00 | 2023-07-12 09:30 | Gran Permit Issuer | 23SD2
10797950 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | CLEAN 1 | Granulation | 10797950 - 15W HPWB Cln GranSD 46CK2401 | 10797950 | 0020 | HPWB Dryer Tophouse | 0 | Task Dependent | 2023-07-12 10:30 | 2023-07-12 14:30 |  | 3.5 | 4 | 4 | 12 | 12 | 0 |  |  | 2023-07-12 10:30 | 2023-07-12 14:30 | Waterblast Truck, Cleaning Ops | 23SD2
10797950 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4622 | CLEAN 1 | Granulation | 10797950 - 15W HPWB Cln GranSD 46CK2401 | 10797950 | 0040 | Close Permit - 10797950 - 15W HPWB Cln GranSD 46CK2401 | 0 | Task Dependent | 2023-07-13 03:30 | 2023-07-13 04:00 |  | 51 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 03:30 | 2023-07-13 04:00 | Gran Permit Issuer | 23SD2
10798043 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 1 | Granulation | 10798043 - 15W HPWB Cln GranSD SU0001 | 10798043 | 0010 | Issue Permit - 10798043 - 15W HPWB Cln GranSD SU0001 | 0 | Task Dependent | 2023-07-14 01:00 | 2023-07-14 01:30 |  | 28 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 01:00 | 2023-07-14 01:30 | Gran Permit Issuer | 23SD2
10798043 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 1 | Granulation | 10798043 - 15W HPWB Cln GranSD SU0001 | 10798043 | 0020 | Vac Out Sump | 0 | Task Dependent | 2023-07-14 01:30 | 2023-07-14 11:30 |  | 28 | 8 | 8 | 16 | 16 | 0 |  |  | 2023-07-14 01:30 | 2023-07-14 11:30 | Vac Truck, Cleaning Ops | 23SD2
10798043 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 1 | Granulation | 10798043 - 15W HPWB Cln GranSD SU0001 | 10798043 | 0040 | Close Permit - 10798043 - 15W HPWB Cln GranSD SU0001 | 0 | Task Dependent | 2023-07-14 11:30 | 2023-07-14 12:00 |  | 28 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 11:30 | 2023-07-14 12:00 | Gran Permit Issuer | 23SD2
10798071 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4624 | CLEAN 1 | Granulation | 10798071 - 15W HPWB Cln HpprCln GranSD 46TK2404 | 10798071 | 0010 | Issue Permit - 10798071 - 15W HPWB Cln HpprCln GranSD 46TK2404 | 0 | Task Dependent | 2023-07-13 11:00 | 2023-07-13 11:30 |  | 28 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 11:00 | 2023-07-13 11:30 | Gran Permit Issuer | 23SD2
10798071 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4624 | CLEAN 1 | Granulation | 10798071 - 15W HPWB Cln HpprCln GranSD 46TK2404 | 10798071 | 0020 | Clean Product Surge Hopper | 0 | Task Dependent | 2023-07-13 11:30 | 2023-07-13 15:30 |  | 28 | 4 | 4 | 12 | 12 | 0 |  |  | 2023-07-13 11:30 | 2023-07-13 15:30 | Waterblast Truck, Cleaning Ops | 23SD2
10798071 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4624 | CLEAN 1 | Granulation | 10798071 - 15W HPWB Cln HpprCln GranSD 46TK2404 | 10798071 | 0040 | Process Engineer inspection | 0 | Task Dependent | 2023-07-13 15:30 | 2023-07-13 16:00 |  | 40.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 15:30 | 2023-07-13 16:00 | Granulation Engineer | 23SD2
10798071 - 0050 | Not Started | GLSTest-01.GRAN.MAINT.4624 | CLEAN 1 | Granulation | 10798071 - 15W HPWB Cln HpprCln GranSD 46TK2404 | 10798071 | 0050 | Close Permit - 10798071 - 15W HPWB Cln HpprCln GranSD 46TK2404 | 0 | Task Dependent | 2023-07-13 16:00 | 2023-07-13 16:30 |  | 40.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 16:00 | 2023-07-13 16:30 | Gran Permit Issuer | 23SD2
10798072 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4624 | CLEAN 2 | Granulation | 10798072 - 15W HPWB Cln Elev GranSD 46CC2402 | 10798072 | 0010 | Issue Permit - 10798072 - 15W HPWB Cln Elev GranSD 46CC2402 | 0 | Task Dependent | 2023-07-12 15:00 | 2023-07-12 15:30 |  | 59 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 15:00 | 2023-07-12 15:30 | Gran Permit Issuer | 23SD2
10798072 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4624 | CLEAN 2 | Granulation | 10798072 - 15W HPWB Cln Elev GranSD 46CC2402 | 10798072 | 0020 | Water Blast Elevator Boot | 0 | Task Dependent | 2023-07-12 15:30 | 2023-07-12 19:30 |  | 59 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-12 15:30 | 2023-07-12 19:30 | Cleaning Ops, Waterblast Truck | 23SD2
10798072 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4624 | CLEAN 2 | Granulation | 10798072 - 15W HPWB Cln Elev GranSD 46CC2402 | 10798072 | 0040 | Close Permit - 10798072 - 15W HPWB Cln Elev GranSD 46CC2402 | 0 | Task Dependent | 2023-07-12 19:30 | 2023-07-12 20:00 |  | 59 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 19:30 | 2023-07-12 20:00 | Gran Permit Issuer | 23SD2
10798105 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 1 | Granulation | 10798105 - 15W HPWB Cln GranSD 46PC2701 | 10798105 | 0010 | Issue Permit - 10798105 - 15W HPWB Cln GranSD 46PC2701 | 0 | Task Dependent | 2023-07-13 02:00 | 2023-07-13 02:30 |  | 3.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 02:00 | 2023-07-13 02:30 | Gran Permit Issuer | 23SD2
10798105 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 1 | Granulation | 10798105 - 15W HPWB Cln GranSD 46PC2701 | 10798105 | 0030 | HPWB Pipe | 0 | Task Dependent | 2023-07-13 02:30 | 2023-07-13 04:30 |  | 3.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-13 02:30 | 2023-07-13 04:30 | Waterblast Truck, Cleaning Ops | 23SD2
10798105 - 0050 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 1 | Granulation | 10798105 - 15W HPWB Cln GranSD 46PC2701 | 10798105 | 0050 | Close Permit - 10798105 - 15W HPWB Cln GranSD 46PC2701 | 0 | Task Dependent | 2023-07-13 04:30 | 2023-07-13 05:00 |  | 45.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 04:30 | 2023-07-13 05:00 | Gran Permit Issuer | 23SD2
10798125 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 2 | Granulation | 10798125 - 15W HPWB Cln GranSD SU2802 | 10798125 | 0010 | Issue Permit - 10798125 - 15W HPWB Cln GranSD SU2802 | 0 | Task Dependent | 2023-07-13 03:30 | 2023-07-13 04:00 |  | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 03:30 | 2023-07-13 04:00 | Gran Permit Issuer | 23SD2
10798125 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 1 | Granulation | 10798125 - 15W HPWB Cln GranSD SU2802 | 10798125 | 0030 | Clean RGV Scrubber Tank | 0 | Task Dependent | 2023-07-13 09:00 | 2023-07-13 13:00 |  | 3 | 4 | 4 | 12 | 12 | 0 |  |  | 2023-07-13 09:00 | 2023-07-13 13:00 | Cleaning Ops, Waterblast Truck | 23SD2
10798125 - 0060 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 1 | Granulation | 10798125 - 15W HPWB Cln GranSD SU2802 | 10798125 | 0060 | Close Permit - 10798125 - 15W HPWB Cln GranSD SU2802 | 0 | Task Dependent | 2023-07-13 13:00 | 2023-07-13 13:30 |  | 39 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 13:00 | 2023-07-13 13:30 | Gran Permit Issuer | 23SD2
10798126 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 2 | Granulation | 10798126 - 15W HPWB Cln GranSD SU2801 | 10798126 | 0010 | Issue Permit - 10798126 - 15W HPWB Cln GranSD SU2801 | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 01:00 |  | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 01:00 | Gran Permit Issuer | 23SD2
10798126 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 1 | Granulation | 10798126 - 15W HPWB Cln GranSD SU2801 | 10798126 | 0030 | Clean Dryer Scrubber Tank | 0 | Task Dependent | 2023-07-13 13:00 | 2023-07-13 17:00 |  | 3 | 4 | 4 | 12 | 12 | 0 |  |  | 2023-07-13 13:00 | 2023-07-13 17:00 | Cleaning Ops, Waterblast Truck | 23SD2
10798126 - 0050 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 1 | Granulation | 10798126 - 15W HPWB Cln GranSD SU2801 | 10798126 | 0050 | Close Permit - 10798126 - 15W HPWB Cln GranSD SU2801 | 0 | Task Dependent | 2023-07-13 19:00 | 2023-07-13 19:30 |  | 35 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 19:00 | 2023-07-13 19:30 | Gran Permit Issuer | 23SD2
10798138 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 2 | Granulation | 10798138 - 15W HPWB Cln GranSD 46SU2701 | 10798138 | 0010 | Issue Permit - 10798138 - 15W HPWB Cln GranSD 46SU2701 | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 01:00 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 01:00 | Gran Permit Issuer | 23SD2
10798138 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 2 | Granulation | 10798138 - 15W HPWB Cln GranSD 46SU2701 | 10798138 | 0030 | 15W HPWB Cln Prescrubber Weir Shut | 0 | Task Dependent | 2023-07-13 09:00 | 2023-07-13 13:00 |  | 3 | 4 | 4 | 12 | 12 | 0 |  |  | 2023-07-13 09:00 | 2023-07-13 13:00 | Waterblast Truck, Cleaning Ops | 23SD2
10798138 - 0090 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 2 | Granulation | 10798138 - 15W HPWB Cln GranSD 46SU2701 | 10798138 | 0090 | Close Permit - 10798138 - 15W HPWB Cln GranSD 46SU2701 | 0 | Task Dependent | 2023-07-13 19:00 | 2023-07-13 19:30 |  | 35 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 19:00 | 2023-07-13 19:30 | Gran Permit Issuer | 23SD2
10798140 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 1 | Granulation | 10798140 - 15W HPWB Cln GranSD TK2801 | 10798140 | 0010 | Issue Permit - 10798140 - 15W HPWB Cln GranSD TK2801 | 0 | Task Dependent | 2023-07-13 16:30 | 2023-07-13 17:00 |  | 27.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 16:30 | 2023-07-13 17:00 | Gran Permit Issuer | 23SD2
10798140 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 1 | Granulation | 10798140 - 15W HPWB Cln GranSD TK2801 | 10798140 | 0040 | Clean Primary Scrubber Tank | 0 | Task Dependent | 2023-07-13 19:00 | 2023-07-13 23:00 |  | 27.5 | 4 | 4 | 12 | 12 | 0 |  |  | 2023-07-13 19:00 | 2023-07-13 23:00 | Waterblast Truck, 19ft Elec Scissor Lift, Cleaning Ops | 23SD2
10798140 - 0060 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 1 | Granulation | 10798140 - 15W HPWB Cln GranSD TK2801 | 10798140 | 0060 | Close Permit - 10798140 - 15W HPWB Cln GranSD TK2801 | 0 | Task Dependent | 2023-07-13 23:00 | 2023-07-13 23:30 |  | 31 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 23:00 | 2023-07-13 23:30 | Gran Permit Issuer | 23SD2
10798141 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 1 | Granulation | 10798141 - 15W HPWB Cln GranSD 46FC2802 | 10798141 | 0010 | Issue Permit - 10798141 - 15W HPWB Cln GranSD 46FC2802 | 0 | Task Dependent | 2023-07-14 12:30 | 2023-07-14 13:00 |  | 15 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 12:30 | 2023-07-14 13:00 | Gran Permit Issuer | 23SD2
10798141 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 1 | Granulation | 10798141 - 15W HPWB Cln GranSD 46FC2802 | 10798141 | 0030 | Sandblast Impeller (CSE) | 0 | Task Dependent | 2023-07-14 13:00 | 2023-07-14 16:00 |  | 15 | 3 | 3 | 9 | 9 | 0 |  |  | 2023-07-14 13:00 | 2023-07-14 16:00 | Sandblast, Cleaning Ops | 23SD2
10798141 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 1 | Granulation | 10798141 - 15W HPWB Cln GranSD 46FC2802 | 10798141 | 0040 | Vac Out Fan | 0 | Task Dependent | 2023-07-14 16:00 | 2023-07-14 17:00 |  | 15 | 1 | 1 | 3 | 3 | 0 |  |  | 2023-07-14 16:00 | 2023-07-14 17:00 | Cleaning Ops, Vac Truck | 23SD2
10798141 - 0070 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 1 | Granulation | 10798141 - 15W HPWB Cln GranSD 46FC2802 | 10798141 | 0070 | Close Permit - 10798141 - 15W HPWB Cln GranSD 46FC2802 | 0 | Task Dependent | 2023-07-14 19:00 | 2023-07-14 19:30 |  | 15 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 19:00 | 2023-07-14 19:30 | Gran Permit Issuer | 23SD2
10798144 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 1 | Granulation | 10798144 - 15W HPWB Cln GranSD 46FC2801 | 10798144 | 0010 | Issue Permit - 10798144 - 15W HPWB Cln GranSD 46FC2801 | 0 | Task Dependent | 2023-07-14 09:30 | 2023-07-14 10:00 |  | 15 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 09:30 | 2023-07-14 10:00 | Gran Permit Issuer | 23SD2
10798144 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 1 | Granulation | 10798144 - 15W HPWB Cln GranSD 46FC2801 | 10798144 | 0030 | Sandblast Impeller (CSE) | 0 | Task Dependent | 2023-07-14 10:00 | 2023-07-14 13:00 |  | 15 | 3 | 3 | 9 | 9 | 0 |  |  | 2023-07-14 10:00 | 2023-07-14 13:00 | Sandblast, Cleaning Ops | 23SD2
10798144 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 1 | Granulation | 10798144 - 15W HPWB Cln GranSD 46FC2801 | 10798144 | 0040 | Vac Out Fan | 0 | Task Dependent | 2023-07-14 13:00 | 2023-07-14 14:00 |  | 17 | 1 | 1 | 3 | 3 | 0 |  |  | 2023-07-14 13:00 | 2023-07-14 14:00 | Cleaning Ops, Vac Truck | 23SD2
10798144 - 0070 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 1 | Granulation | 10798144 - 15W HPWB Cln GranSD 46FC2801 | 10798144 | 0070 | Close Permit - 10798144 - 15W HPWB Cln GranSD 46FC2801 | 0 | Task Dependent | 2023-07-14 14:00 | 2023-07-14 14:30 |  | 17 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 14:00 | 2023-07-14 14:30 | Gran Permit Issuer | 23SD2
10799541 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4420 | CLEAN 1 | Phos Acid | 10799541 - 15W HPWB Cln PhosSD 41CB2001 | 10799541 | 0010 | Clean Conveyor | 0 | Task Dependent | 2023-07-14 23:30 | 2023-07-15 02:30 |  | 48 | 3 | 3 | 9 | 9 | 0 |  |  | 2023-07-14 23:30 | 2023-07-15 02:30 | Waterblast Truck, Cleaning Ops | 23SD2
10799541 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4420 | CLEAN 1 | Phos Acid | 10799541 - 15W HPWB Cln PhosSD 41CB2001 | 10799541 | 0030 | Issue Permit - 10799541 - 15W HPWB Cln PhosSD 41CB2001 | 0 | Task Dependent | 2023-07-14 23:00 | 2023-07-14 23:30 |  | 48 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 23:00 | 2023-07-14 23:30 | Phos Permit Issuer | 23SD2
10799541 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4420 | CLEAN 1 | Phos Acid | 10799541 - 15W HPWB Cln PhosSD 41CB2001 | 10799541 | 0040 | Close Permit - 10799541 - 15W HPWB Cln PhosSD 41CB2001 | 0 | Task Dependent | 2023-07-15 02:30 | 2023-07-15 03:00 |  | 48 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 02:30 | 2023-07-15 03:00 | Phos Permit Issuer | 23SD2
10801356 - 0010 | Not Started | GLSTest-01.BENE.MAINT.9999 | CLEAN 1 | Beneficiation | 10801356 - 15W HPWB Cln BeneSD 20PP99FL01 | 10801356 | 0010 | Issue permit - 10801356 - 15W HPWB Cln BeneSD 20PP99FL01 | 0 | Task Dependent | 2023-07-14 22:00 | 2023-07-14 22:30 |  | 19 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 22:00 | 2023-07-14 22:30 | Bene Permit Issuer | 23SD2
10801356 - 0020 | Not Started | GLSTest-01.BENE.MAINT.9999 | CLEAN 1 | Beneficiation | 10801356 - 15W HPWB Cln BeneSD 20PP99FL01 | 10801356 | 0020 | Disconnect floc lines for cleaning | 0 | Task Dependent | 2023-07-14 22:30 | 2023-07-15 01:30 |  | 19 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-14 22:30 | 2023-07-15 01:30 | Fitter | 23SD2
10801356 - 0030 | Not Started | GLSTest-01.BENE.MAINT.9999 | CLEAN 1 | Beneficiation | 10801356 - 15W HPWB Cln BeneSD 20PP99FL01 | 10801356 | 0030 | Pre-clean Inspection | 0 | Task Dependent | 2023-07-15 01:30 | 2023-07-15 02:00 |  | 28 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 01:30 | 2023-07-15 02:00 | Beneficiation Engineer | 23SD2
10801356 - 0040 | Not Started | GLSTest-01.BENE.MAINT.9999 | CLEAN 1 | Beneficiation | 10801356 - 15W HPWB Cln BeneSD 20PP99FL01 | 10801356 | 0040 | 15W HPWB Cln Bene Flocculant Lines Shut | 0 | Task Dependent | 2023-07-15 02:00 | 2023-07-15 05:00 |  | 28 | 3 | 3 | 9 | 9 | 0 |  |  | 2023-07-15 02:00 | 2023-07-15 05:00 | Waterblast Truck, Cleaning Ops | 23SD2
10801356 - 0060 | Not Started | GLSTest-01.BENE.MAINT.9999 | CLEAN 1 | Beneficiation | 10801356 - 15W HPWB Cln BeneSD 20PP99FL01 | 10801356 | 0060 | Post-clean Inspection | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 07:30 |  | 28 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 07:30 | Beneficiation Engineer | 23SD2
10801356 - 0070 | Not Started | GLSTest-01.BENE.MAINT.9999 | CLEAN 1 | Beneficiation | 10801356 - 15W HPWB Cln BeneSD 20PP99FL01 | 10801356 | 0070 | Reinstate floc lines after clean | 0 | Task Dependent | 2023-07-15 11:00 | 2023-07-15 15:00 |  | 24.5 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-15 11:00 | 2023-07-15 15:00 | Fitter | 23SD2
10801356 - 0080 | Not Started | GLSTest-01.BENE.MAINT.9999 | CLEAN 1 | Beneficiation | 10801356 - 15W HPWB Cln BeneSD 20PP99FL01 | 10801356 | 0080 | Close permit - 10801356 - 15W HPWB Cln BeneSD 20PP99FL01 | 0 | Task Dependent | 2023-07-15 15:00 | 2023-07-15 15:30 |  | 24.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 15:00 | 2023-07-15 15:30 | Bene Permit Issuer | 23SD2
10802429 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 1 | Granulation | 10802429 - 30W HPWB Cln GranSD 46PC2702 | 10802429 | 0010 | Issue Permit - 10802429 - 30W HPWB Cln GranSD 46PC2702 | 0 | Task Dependent | 2023-07-13 04:00 | 2023-07-13 04:30 |  | 3.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 04:00 | 2023-07-13 04:30 | Gran Permit Issuer | 23SD2
10802429 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 1 | Granulation | 10802429 - 30W HPWB Cln GranSD 46PC2702 | 10802429 | 0030 | HPWB Pipe | 0 | Task Dependent | 2023-07-13 04:30 | 2023-07-13 08:30 |  | 3.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-13 04:30 | 2023-07-13 08:30 | Waterblast Truck, Cleaning Ops | 23SD2
10802429 - 0050 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 1 | Granulation | 10802429 - 30W HPWB Cln GranSD 46PC2702 | 10802429 | 0050 | Close Permit - 10802429 - 30W HPWB Cln GranSD 46PC2702 | 0 | Task Dependent | 2023-07-13 08:30 | 2023-07-13 09:00 |  | 43.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 08:30 | 2023-07-13 09:00 | Gran Permit Issuer | 23SD2
10804307 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10804307 - 15W HPWB Cln PhosSD 44TK4001 | 10804307 | 0010 | Issue Permit - 10804307 - 15W HPWB Cln PhosSD 44TK4001 | 0 | Task Dependent | 2023-07-15 16:00 | 2023-07-15 16:30 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 16:00 | 2023-07-15 16:30 | Phos Permit Issuer | 23SD2
10804307 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10804307 - 15W HPWB Cln PhosSD 44TK4001 | 10804307 | 0020 | Remove Floor and Rotate Downleg | 0 | Task Dependent | 2023-07-15 16:30 | 2023-07-15 20:30 |  | 0 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-15 16:30 | 2023-07-15 20:30 | Fitter | 23SD2
10804307 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10804307 - 15W HPWB Cln PhosSD 44TK4001 | 10804307 | 0030 | Erect Scaffold Access | 0 | Task Dependent | 2023-07-15 20:30 | 2023-07-15 21:30 |  | 9 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-15 20:30 | 2023-07-15 21:30 | Scaffolder | 23SD2
10804307 - 0060 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10804307 - 15W HPWB Cln PhosSD 44TK4001 | 10804307 | 0060 | HPWB & Vac out Sump | 0 | Task Dependent | 2023-07-15 21:30 | 2023-07-16 03:30 |  | 9 | 6 | 6 | 30 | 30 | 0 |  |  | 2023-07-15 21:30 | 2023-07-16 03:30 | Vac Truck, Waterblast Truck, Cleaning Ops | 23SD2
10804307 - 0070 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10804307 - 15W HPWB Cln PhosSD 44TK4001 | 10804307 | 0070 | Remove Scaffold | 0 | Task Dependent | 2023-07-16 03:30 | 2023-07-16 04:30 |  | 12 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-16 03:30 | 2023-07-16 04:30 | Scaffolder | 23SD2
10804307 - 0080 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10804307 - 15W HPWB Cln PhosSD 44TK4001 | 10804307 | 0080 | Reinstate Floor and Rotate Downleg | 0 | Task Dependent | 2023-07-16 04:30 | 2023-07-16 08:30 |  | 12 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-16 04:30 | 2023-07-16 08:30 | Fitter | 23SD2
10804307 - 0090 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10804307 - 15W HPWB Cln PhosSD 44TK4001 | 10804307 | 0090 | Close Permit - 10804307 - 15W HPWB Cln PhosSD 44TK4001 | 0 | Task Dependent | 2023-07-16 08:30 | 2023-07-16 09:00 |  | 16 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 08:30 | 2023-07-16 09:00 | Phos Permit Issuer | 23SD2
10804322 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4480 | CLEAN 2 | Phos Acid | 10804322 - 15W HPWB Cln PhosSD 44CB8003 | 10804322 | 0010 | Clean Shuttle Interior | 0 | Task Dependent | 2023-07-15 02:30 | 2023-07-15 08:30 |  | 11.5 | 4 | 4 | 12 | 12 | 0 |  |  | 2023-07-15 02:30 | 2023-07-15 08:30 | Waterblast Truck, Cleaning Ops | 23SD2
10804345 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4485 | DAWSON3 | Phos Acid | 10804345 - 15W HPWB Cln PhosSD 48TK1201 | 10804345 | 0010 | Issue Permit - 10804345 - 15W HPWB Cln PhosSD 48TK1201 | 0 | Task Dependent | 2023-07-14 16:30 | 2023-07-14 17:00 |  | 16 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 16:30 | 2023-07-14 17:00 | Phos Permit Issuer | 23SD2
10804345 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4485 | DAWSON3 | Phos Acid | 10804345 - 15W HPWB Cln PhosSD 48TK1201 | 10804345 | 0020 | Sentry Luki valve Inspection | 0 | Task Dependent | 2023-07-16 16:00 | 2023-07-16 20:00 |  | 5 | 2 | 2 | 6 | 6 | 0 |  |  | 2023-07-16 16:00 | 2023-07-16 20:00 | Fitter, T/A | 23SD2
10804345 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4485 | DAWSON3 | Phos Acid | 10804345 - 15W HPWB Cln PhosSD 48TK1201 | 10804345 | 0040 | Remove Tank Door and Install Spade to Luki 1 | 0 | Task Dependent | 2023-07-14 19:00 | 2023-07-14 23:00 |  | 16 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-14 19:00 | 2023-07-14 23:00 | Fitter | 23SD2
10804345 - 0060 | Not Started | GLSTest-01.PHOS.MAINT.4485 | DAWSON3 | Phos Acid | 10804345 - 15W HPWB Cln PhosSD 48TK1201 | 10804345 | 0060 | Remove Door | 0 | Task Dependent | 2023-07-14 19:00 | 2023-07-14 21:00 |  | 18 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-14 19:00 | 2023-07-14 21:00 | Rigger, Franna, Crane Operator | 23SD2
10804345 - 0080 | Not Started | GLSTest-01.PHOS.MAINT.4485 | CLEAN 2 | Phos Acid | 10804345 - 15W HPWB Cln PhosSD 48TK1201 | 10804345 | 0080 | HPWB Cut Door | 0 | Task Dependent | 2023-07-14 23:00 | 2023-07-15 05:00 |  | 16 | 6 | 6 | 18 | 18 | 0 |  |  | 2023-07-14 23:00 | 2023-07-15 05:00 | Cleaning Ops, Waterblast Truck | 23SD2
10804345 - 0100 | Not Started | GLSTest-01.PHOS.MAINT.4485 | DAWSON3 | Phos Acid | 10804345 - 15W HPWB Cln PhosSD 48TK1201 | 10804345 | 0100 | Inspect tank for damage after cleaning. | 0 | Task Dependent | 2023-07-16 16:00 | 2023-07-16 17:00 |  | 5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-16 16:00 | 2023-07-16 17:00 | T/A, Static Engineer | 23SD2
10804345 - 0110 | Not Started | GLSTest-01.PHOS.MAINT.4485 | PHOS | Phos Acid | 10804345 - 15W HPWB Cln PhosSD 48TK1201 | 10804345 | 0110 | Dig out slurry with bobcat | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-16 03:00 |  | 16 | 18 | 18 | 18 | 18 | 0 |  |  | 2023-07-15 07:00 | 2023-07-16 03:00 | Bobcat, Phos Ops | 23SD2
10804345 - 0145 | Not Started | GLSTest-01.PHOS.MAINT.4485 | DAWSON3 | Phos Acid | 10804345 - 15W HPWB Cln PhosSD 48TK1201 | 10804345 | 0130 | Re-Instate Tank Door | 0 | Task Dependent | 2023-07-16 19:00 | 2023-07-16 21:00 |  | 6 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-16 19:00 | 2023-07-16 21:00 | Rigger | 23SD2
10804345 - 0140 | Not Started | GLSTest-01.PHOS.MAINT.4485 | DAWSON3 | Phos Acid | 10804345 - 15W HPWB Cln PhosSD 48TK1201 | 10804345 | 0140 | Re-Instate Tank Door and Remove Spade | 0 | Task Dependent | 2023-07-16 20:00 | 2023-07-17 |  | 5 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-16 20:00 | 2023-07-17 | Fitter | 23SD2
10804345 - 0150 | Not Started | GLSTest-01.PHOS.MAINT.4485 | DAWSON3 | Phos Acid | 10804345 - 15W HPWB Cln PhosSD 48TK1201 | 10804345 | 0150 | Close Permit - 10804345 - 15W HPWB Cln PhosSD 48TK1201 | 0 | Task Dependent | 2023-07-17 | 2023-07-17 00:30 |  | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-17 | 2023-07-17 00:30 | Phos Permit Issuer | 23SD2
10804483 - 0010 | Not Started | GLSTest-01.BENE.MAINT.2142 | CLEAN 2 | Beneficiation | 10804483 - 15W HPWB Cln BeneSD 21TK4204 | 10804483 | 0010 | Issue Permit - 10804483 - 15W HPWB Cln BeneSD 21TK4204 | 0 | Task Dependent | 2023-07-14 21:00 | 2023-07-14 21:30 |  | 19 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 21:00 | 2023-07-14 21:30 | Bene Permit Issuer | 23SD2
10804483 - 0020 | Not Started | GLSTest-01.BENE.MAINT.2142 | CLEAN 2 | Beneficiation | 10804483 - 15W HPWB Cln BeneSD 21TK4204 | 10804483 | 0020 | Open hatches for cleaning | 0 | Task Dependent | 2023-07-14 21:30 | 2023-07-14 22:30 |  | 19 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-14 21:30 | 2023-07-14 22:30 | Fitter | 23SD2
10804483 - 0040 | Not Started | GLSTest-01.BENE.MAINT.2142 | CLEAN 1 | Beneficiation | 10804483 - 15W HPWB Cln BeneSD 21TK4204 | 10804483 | 0040 | HPWB and Vac Floc Tank | 0 | Task Dependent | 2023-07-14 22:30 | 2023-07-15 01:30 |  | 28.5 | 3 | 3 | 15 | 15 | 0 |  |  | 2023-07-14 22:30 | 2023-07-15 01:30 | Vac Truck, Cleaning Ops, Waterblast Truck | 23SD2
10804483 - 0060 | Not Started | GLSTest-01.BENE.MAINT.2142 | CLEAN 2 | Beneficiation | 10804483 - 15W HPWB Cln BeneSD 21TK4204 | 10804483 | 0060 | Close Permit - 10804483 - 15W HPWB Cln BeneSD 21TK4204 | 0 | Task Dependent | 2023-07-15 11:00 | 2023-07-15 11:30 |  | 28.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 11:00 | 2023-07-15 11:30 | Bene Permit Issuer | 23SD2
10805519 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4425 | CLEAN 2 | Phos Acid | 10805519 - 15W HPWB Cln PhosSD 44HE2501 | 10805519 | 0010 | Issue Permit - 10805519 - 15W HPWB Cln PhosSD 44HE2501 | 0 | Task Dependent | 2023-07-15 09:30 | 2023-07-15 10:00 |  | 26 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 09:30 | 2023-07-15 10:00 | Phos Permit Issuer | 23SD2
10805519 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4425 | CLEAN 2 | Phos Acid | 10805519 - 15W HPWB Cln PhosSD 44HE2501 | 10805519 | 0020 | Open Y piece hatches | 0 | Task Dependent | 2023-07-15 10:00 | 2023-07-15 11:00 |  | 26 | 1 | 1 | 3 | 3 | 0 |  |  | 2023-07-15 10:00 | 2023-07-15 11:00 | Crane Operator, 45ft EWP, Fitter | 23SD2
10805519 - 0050 | Not Started | GLSTest-01.PHOS.MAINT.4425 | CLEAN 2 | Phos Acid | 10805519 - 15W HPWB Cln PhosSD 44HE2501 | 10805519 | 0050 | HPWB clean downleg through Y piece | 0 | Task Dependent | 2023-07-16 08:00 | 2023-07-16 11:00 |  | 9 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-16 08:00 | 2023-07-16 11:00 | Phos Cleaning MWC, Waterblast Truck | 23SD2
10805519 - 0070 | Not Started | GLSTest-01.PHOS.MAINT.4425 | CLEAN 2 | Phos Acid | 10805519 - 15W HPWB Cln PhosSD 44HE2501 | 10805519 | 0070 | Close Permit - 10805519 - 15W HPWB Cln PhosSD 44HE2501 | 0 | Task Dependent | 2023-07-16 12:00 | 2023-07-16 12:30 |  | 21 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 12:00 | 2023-07-16 12:30 | Phos Permit Issuer | 23SD2
10795474 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | CLEAN 1 | Granulation | 10795474 - 30W HPWB Cln GranSD 46PP99DD01 | 10809912 | 0010 | Issue Permit - 10795474 - 30W HPWB Cln GranSD 46PP99DD01 | 0 | Task Dependent | 2023-07-12 14:00 | 2023-07-12 14:30 |  | 3.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 14:00 | 2023-07-12 14:30 | Gran Permit Issuer | 23SD2
10795474 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | CLEAN 1 | Granulation | 10795474 - 30W HPWB Cln GranSD 46PP99DD01 | 10809912 | 0020 | HPWB Dryer Cyclone | 0 | Task Dependent | 2023-07-12 14:30 | 2023-07-12 22:30 |  | 3.5 | 6 | 6 | 18 | 18 | 0 |  |  | 2023-07-12 14:30 | 2023-07-12 22:30 | Waterblast Truck, Cleaning Ops | 23SD2
10795474 - 0050 | Not Started | GLSTest-01.GRAN.MAINT.9999 | CLEAN 2 | Granulation | 10795474 - 30W HPWB Cln GranSD 46PP99DD01 | 10809912 | 0050 | Close Permit - 10795474 - 30W HPWB Cln GranSD 46PP99DD01 | 0 | Task Dependent | 2023-07-13 12:00 | 2023-07-13 12:30 |  | 44.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 12:00 | 2023-07-13 12:30 | Gran Permit Issuer | 23SD2
10797868 - 0065 | Not Started | GLSTest-01.GRAN.MAINT.4621 | CLEAN 2 | Granulation | 10797868 - 15W HPWB Cln GranSD 46TK2101 | 10797868 | 0060 | Install Sparger Caps | 0 | Task Dependent | 2023-07-13 22:30 | 2023-07-13 23:30 |  | 30.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-13 22:30 | 2023-07-13 23:30 | Fitter | 23SD2
10770043 - 0005 | Not Started | GLSTest-01.GRAN.MAINT.4626 | CLEAN 1 | Granulation | 10770043 - 60W HPWB Cln GranSD Coating Oil Tank | 10770043 | 0010 | Issue Permit - 10770043 - Coating Oil Tank | 0 | Task Dependent | 2023-07-13 21:00 | 2023-07-13 21:30 |  | 28 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 21:00 | 2023-07-13 21:30 | Gran Permit Issuer | 23SD2
10770043 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4626 | CLEAN 1 | Granulation | 10770043 - 60W HPWB Cln GranSD Coating Oil Tank | 10770043 | 0020 | Close Permit - 10770043 - Coating Oil Tank | 0 | Task Dependent | 2023-07-14 01:30 | 2023-07-14 02:00 |  | 35.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 01:30 | 2023-07-14 02:00 | Gran Permit Issuer | 23SD2
10798138 - 0050 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 2 | Granulation | 10798138 - 15W HPWB Cln GranSD 46SU2701 | 10798138 | 0060 | 15W HPWB Cln Pre Scrubber Tank 1 Shut | 0 | Task Dependent | 2023-07-13 13:00 | 2023-07-13 17:00 |  | 3 | 4 | 4 | 12 | 12 | 0 |  |  | 2023-07-13 13:00 | 2023-07-13 17:00 | Waterblast Truck, Cleaning Ops | 23SD2
10805519 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4425 | CLEAN 2 | Phos Acid | 10805519 - 15W HPWB Cln PhosSD 44HE2501 | 10805519 | 0020 | Close Y piece hatches | 0 | Task Dependent | 2023-07-16 11:00 | 2023-07-16 12:00 |  | 9 | 1 | 1 | 3 | 3 | 0 |  |  | 2023-07-16 11:00 | 2023-07-16 12:00 | Crane Operator, 45ft EWP, Fitter | 23SD2
10794307 - 0025 | Not Started | GLSTest-01.PHOS.MAINT.4425 | CLEAN 1 | Phos Acid | 10794307 - 15W HPWB Cln Lndr PhosSD 44TK0026 | 10794307 | 0020 | Open R1A Foam Shield | 0 | Task Dependent | 2023-07-15 03:00 | 2023-07-15 05:00 |  | 22.5 | 2 | 2 | 8 | 8 | 0 |  |  | 2023-07-15 03:00 | 2023-07-15 05:00 | Crane Operator, Rigger, 55t Crane, Fitter | 23SD2
10794307 - 0045 | Not Started | GLSTest-01.PHOS.MAINT.4425 | CLEAN 1 | Phos Acid | 10794307 - 15W HPWB Cln Lndr PhosSD 44TK0026 | 10794307 | 0030 | Clean R1A Foam Shield | 0 | Task Dependent | 2023-07-15 09:00 | 2023-07-15 15:00 |  | 22.5 | 6 | 6 | 18 | 18 | 0 |  |  | 2023-07-15 09:00 | 2023-07-15 15:00 | Waterblast Truck, Cleaning Ops | 23SD2
10794307 - 0075 | Not Started | GLSTest-01.PHOS.MAINT.4425 | CLEAN 1 | Phos Acid | 10794307 - 15W HPWB Cln Lndr PhosSD 44TK0026 | 10794307 | 0070 | Close R1A Foam Shield | 0 | Task Dependent | 2023-07-15 15:30 | 2023-07-15 19:30 |  | 22.5 | 2 | 2 | 8 | 8 | 0 |  |  | 2023-07-15 15:30 | 2023-07-15 19:30 | Crane Operator, Rigger, 55t Crane, Fitter | 23SD2
10788561 - 0011 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10788561 - 15W HPWB Cln PhosSD 44CO4001 | 10788561 | 0010 | Remove Hatches & Discharge Spool | 0 | Task Dependent | 2023-07-15 03:30 | 2023-07-15 08:30 |  | 0 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-15 03:30 | 2023-07-15 08:30 | Fitter | 23SD2
10788561 - 0012 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10788561 - 15W HPWB Cln PhosSD 44CO4001 | 10788561 | 0010 | Remove Inlet Spool | 0 | Task Dependent | 2023-07-15 08:30 | 2023-07-15 12:30 |  | 0 | 4 | 4 | 16 | 16 | 0 |  |  | 2023-07-15 08:30 | 2023-07-15 12:30 | Franna, Rigger, Crane Operator, Fitter | 23SD2
10788561 - 0013 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10788561 - 15W HPWB Cln PhosSD 44CO4001 | 10788561 | 0040 | Pre-Clean Inspection | 0 | Task Dependent | 2023-07-15 12:30 | 2023-07-15 13:00 |  | 5.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 12:30 | 2023-07-15 13:00 | Static Engineer | 23SD2
10788561 - 0035 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10788561 - 15W HPWB Cln PhosSD 44CO4001 | 10788561 | 0040 | Post-Clean Inspection & Repair Mark-Up | 0 | Task Dependent | 2023-07-16 08:30 | 2023-07-16 09:00 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 08:30 | 2023-07-16 09:00 | Static Engineer | 23SD2
10788561 - 0036 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10788561 - 15W HPWB Cln PhosSD 44CO4001 | 10788561 | 0040 | CS - Rubber Repair Scope | 0 | Task Dependent | 2023-07-16 09:00 | 2023-07-16 17:00 |  | 0 | 8 | 8 | 8 | 8 | 0 |  |  | 2023-07-16 09:00 | 2023-07-16 17:00 | Rubber | 23SD2
10788561 - 0037 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10788561 - 15W HPWB Cln PhosSD 44CO4001 | 10788561 | 0040 | CS - Post Repair Inspection | 0 | Task Dependent | 2023-07-16 19:00 | 2023-07-16 19:30 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 19:00 | 2023-07-16 19:30 | Static Engineer | 23SD2
10788561 - 0038 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10788561 - 15W HPWB Cln PhosSD 44CO4001 | 10788561 | 0010 | Re-instate Hatches & Discharge Spool | 0 | Task Dependent | 2023-07-16 19:30 | 2023-07-16 22:30 |  | 0 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-16 19:30 | 2023-07-16 22:30 | Fitter | 23SD2
10788561 - 0039 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10788561 - 15W HPWB Cln PhosSD 44CO4001 | 10788561 | 0010 | Re-instate Inlet Spool | 0 | Task Dependent | 2023-07-16 22:30 | 2023-07-17 02:30 |  | 0 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-16 22:30 | 2023-07-17 02:30 | Fitter | 23SD2
10789898 - 0015 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10789898 - 15W HPWB Cln PhosSD 44FC4002 | 10789898 | 0020 | Un-Box Fan | 0 | Task Dependent | 2023-07-15 07:30 | 2023-07-15 08:00 |  | 4 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-15 07:30 | 2023-07-15 08:00 | Fitter | 23SD2
10789898 - 0065 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10789898 - 15W HPWB Cln PhosSD 44FC4002 | 10789898 | 0020 | Box Up Fan | 0 | Task Dependent | 2023-07-16 19:00 | 2023-07-16 19:30 |  | 4 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-16 19:00 | 2023-07-16 19:30 | Fitter | 23SD2
10789868 - 0012 | Not Started | GLSTest-01.PHOS.MAINT.4475 | PHOS | Phos Acid | 10789868 - 15W HPWB Cln PhosSD 44MS3008 | 10789868 | 0050 | Erect Scaff barrier | 0 | Task Dependent | 2023-07-15 08:30 | 2023-07-15 10:30 |  | 10.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-15 08:30 | 2023-07-15 10:30 | Scaffolder | 23SD2
10804345 - 0015 | Not Started | GLSTest-01.PHOS.MAINT.4485 | CLEAN 2 | Phos Acid | 10804345 - 15W HPWB Cln PhosSD 48TK1201 | 10804345 | 0080 | HPWB Perimeter 'Donut' from Above | 0 | Task Dependent | 2023-07-14 08:00 | 2023-07-14 14:00 |  | 23 | 6 | 6 | 18 | 18 | 0 |  |  | 2023-07-14 08:00 | 2023-07-14 14:00 | Cleaning Ops, Waterblast Truck | 23SD2
10789897 - 0045 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10789897 - 15W HPWB Cln Scrb Dctng PhosSD 99SC01 | 10789897 | 0030 | Close Hatches | 0 | Task Dependent | 2023-07-15 19:00 | 2023-07-15 20:00 |  | 14 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-15 19:00 | 2023-07-15 20:00 | Fitter | 23SD2
10646452 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4629 | DAWSON3 | Granulation | 10646452 - Replace nozzle bolting | 10646452 | 0010 | Issue Permit - 10646452 - Replace nozzle bolting | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 08:00 |  | 27.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 08:00 | Gran Permit Issuer | 23SD2
10646452 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4629 | DAWSON3 | Granulation | 10646452 - Replace nozzle bolting | 10646452 | 0020 | Replace nozzle bolting | 0 | Task Dependent | 2023-07-13 08:00 | 2023-07-13 12:00 |  | 27.5 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-13 08:00 | 2023-07-13 12:00 | Fitter | 23SD2
10646452 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4629 | DAWSON3 | Granulation | 10646452 - Replace nozzle bolting | 10646452 | 0030 | Close Permit - 10646452 - Replace nozzle bolting | 0 | Task Dependent | 2023-07-13 12:00 | 2023-07-13 12:30 |  | 27.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 12:00 | 2023-07-13 12:30 | Gran Permit Issuer | 23SD2
10672798 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON1 | Phos Acid | 10672798 - Replace Flash Cooler A Pump Base | 10672798 | 0010 | Issue Permit - 10672798 - Replace Flash Cooler A Pump Base | 0 | Task Dependent | 2023-07-14 20:30 | 2023-07-14 21:00 |  | 9 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 20:30 | 2023-07-14 21:00 | Phos Permit Issuer | 23SD2
10672798 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON1 | Phos Acid | 10672798 - Replace Flash Cooler A Pump Base | 10672798 | 0020 | Remove pump, guard and belts | 0 | Task Dependent | 2023-07-14 21:00 | 2023-07-15 03:00 |  | 9 | 6 | 6 | 12 | 12 | 0 |  |  | 2023-07-14 21:00 | 2023-07-15 03:00 | Fitter | 23SD2
10672798 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON1 | Phos Acid | 10672798 - Replace Flash Cooler A Pump Base | 10672798 | 0030 | Remove pump, guard and belts | 0 | Task Dependent | 2023-07-14 21:00 | 2023-07-15 |  | 12 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-14 21:00 | 2023-07-15 | Franna, Rigger, Crane Operator | 23SD2
10672798 - 0060 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON1 | Phos Acid | 10672798 - Replace Flash Cooler A Pump Base | 10672798 | 0060 | Disconnect Motor | 0 | Task Dependent | 2023-07-14 21:00 | 2023-07-14 23:00 |  | 13 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-14 21:00 | 2023-07-14 23:00 | Elec | 23SD2
10672798 - 0070 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON1 | Phos Acid | 10672798 - Replace Flash Cooler A Pump Base | 10672798 | 0070 | Remove motor | 0 | Task Dependent | 2023-07-15 03:00 | 2023-07-15 05:00 |  | 9 | 2 | 2 | 8 | 8 | 0 |  |  | 2023-07-15 03:00 | 2023-07-15 05:00 | Franna, Rigger, Crane Operator, Fitter | 23SD2
10672798 - 0110 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON1 | Phos Acid | 10672798 - Replace Flash Cooler A Pump Base | 10672798 | 0110 | Remove base, may require bolts cut | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 10:00 |  | 9 | 3 | 3 | 12 | 12 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 10:00 | Franna, Rigger, Crane Operator, Fitter | 23SD2
10672798 - 0150 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON1 | Phos Acid | 10672798 - Replace Flash Cooler A Pump Base | 10672798 | 0150 | Remove base, may require bolts cut | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 12:00 |  | 9 | 5 | 5 | 5 | 5 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 12:00 | BMW | 23SD2
10672798 - 0160 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON1 | Phos Acid | 10672798 - Replace Flash Cooler A Pump Base | 10672798 | 0160 | HPWB under base and prep for install | 0 | Task Dependent | 2023-07-15 12:00 | 2023-07-15 14:00 |  | 9 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-15 12:00 | 2023-07-15 14:00 | Waterblast Truck, Cleaning Ops | 23SD2
10672798 - 0180 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON1 | Phos Acid | 10672798 - Replace Flash Cooler A Pump Base | 10672798 | 0180 | Reinstate new base to plinth | 0 | Task Dependent | 2023-07-15 14:00 | 2023-07-15 17:00 |  | 9 | 3 | 3 | 12 | 12 | 0 |  |  | 2023-07-15 14:00 | 2023-07-15 17:00 | Franna, Rigger, Crane Operator, Fitter | 23SD2
10672798 - 0220 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON1 | Phos Acid | 10672798 - Replace Flash Cooler A Pump Base | 10672798 | 0220 | Grouting required | 0 | Task Dependent | 2023-07-16 03:00 | 2023-07-16 08:00 |  | 9 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-16 03:00 | 2023-07-16 08:00 | Fitter | 23SD2
10672798 - 0230 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON1 | Phos Acid | 10672798 - Replace Flash Cooler A Pump Base | 10672798 | 0230 | Refit motor | 0 | Task Dependent | 2023-07-15 19:00 | 2023-07-15 21:00 |  | 9 | 2 | 2 | 10 | 10 | 0 |  |  | 2023-07-15 19:00 | 2023-07-15 21:00 | Rigger, Crane Operator, Fitter, Elec | 23SD2
10672798 - 0270 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON1 | Phos Acid | 10672798 - Replace Flash Cooler A Pump Base | 10672798 | 0270 | Refit motor | 0 | Task Dependent | 2023-07-15 19:00 | 2023-07-15 20:00 |  | 10 | 1 | 1 | 0 | 0 | 0 |  |  | 2023-07-15 19:00 | 2023-07-15 20:00 | Franna | 23SD2
10672798 - 0280 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON1 | Phos Acid | 10672798 - Replace Flash Cooler A Pump Base | 10672798 | 0280 | Refit pump and new Pulleys,Belts | 0 | Task Dependent | 2023-07-15 21:00 | 2023-07-16 03:00 |  | 9 | 6 | 6 | 24 | 24 | 0 |  |  | 2023-07-15 21:00 | 2023-07-16 03:00 | Franna, Rigger, Crane Operator, Fitter | 23SD2
10672798 - 0320 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON1 | Phos Acid | 10672798 - Replace Flash Cooler A Pump Base | 10672798 | 0320 | Close Permit - 10672798 - Replace Flash Cooler A Pump Base | 0 | Task Dependent | 2023-07-16 08:00 | 2023-07-16 08:30 |  | 25 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 08:00 | 2023-07-16 08:30 | Phos Permit Issuer | 23SD2
10676127 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4623 | DAWSON2 | Granulation | 10676127 - 60W Mech Serv Gran Sdry Elev | 10676127 | 0010 | Issue Permit - 10676127 - 60W Mech Serv Gran Sdry Elev | 0 | Task Dependent | 2023-07-13 02:30 | 2023-07-13 03:00 |  | 21.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 02:30 | 2023-07-13 03:00 | Gran Permit Issuer | 23SD2
10676127 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4623 | DAWSON2 | Granulation | 10676127 - 60W Mech Serv Gran Sdry Elev | 10676127 | 0020 | Inspect Inching Drive | 0 | Task Dependent | 2023-07-13 03:00 | 2023-07-13 03:30 |  | 21.5 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-13 03:00 | 2023-07-13 03:30 | Fitter | 23SD2
10676127 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4623 | DAWSON2 | Granulation | 10676127 - 60W Mech Serv Gran Sdry Elev | 10676127 | 0030 | Close Permit - 10676127 - 60W Mech Serv Gran Sdry Elev | 0 | Task Dependent | 2023-07-13 03:30 | 2023-07-13 04:00 |  | 21.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 03:30 | 2023-07-13 04:00 | Gran Permit Issuer | 23SD2
10677226 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4411 | ELEC | Phos Acid | 10677226 - Investigate indication lamp fault | 10677226 | 0010 | Investigate indication lamp fault | 0 | Task Dependent | 2023-07-15 07:30 | 2023-07-15 11:30 |  | 17 | 4 | 4 | 4 | 4 | 0 |  |  | 2023-07-15 07:30 | 2023-07-15 11:30 | Elec 3 | 23SD2
10692425 - 0010 | Not Started | GLSTest-01.BENE.MAINT.2122 | DAWSON2 | Beneficiation | 10692425 - cyclone cluster product downleg holed | 10692425 | 0010 | Issue Permit - 10692425 - cyclone cluster product downleg holed | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 07:30 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 07:30 | Bene Permit Issuer | 23SD2
10692425 - 0020 | Not Started | GLSTest-01.BENE.MAINT.2122 | DAWSON2 | Beneficiation | 10692425 - cyclone cluster product downleg holed | 10692425 | 0020 | Rig up downleg and mining hose and unbol | 0 | Task Dependent | 2023-07-14 07:30 | 2023-07-14 10:00 |  | 0 | 2.5 | 2.5 | 7.5 | 7.5 | 0 |  |  | 2023-07-14 07:30 | 2023-07-14 10:00 | 45ft EWP, Rigger, Fitter | 23SD2
10692425 - 0050 | Not Started | GLSTest-01.BENE.MAINT.2122 | DAWSON2 | Beneficiation | 10692425 - cyclone cluster product downleg holed | 10692425 | 0050 | Remove downleg spool | 0 | Task Dependent | 2023-07-14 10:00 | 2023-07-14 13:00 |  | 0 | 3 | 3 | 12 | 12 | 0 |  |  | 2023-07-14 10:00 | 2023-07-14 13:00 | 55t Crane, Crane Operator, Rigger, Fitter | 23SD2
10692425 - 0090 | Not Started | GLSTest-01.BENE.MAINT.2122 | DAWSON2 | Beneficiation | 10692425 - cyclone cluster product downleg holed | 10692425 | 0090 | Remove mining hose | 0 | Task Dependent | 2023-07-14 13:00 | 2023-07-14 15:00 |  | 0 | 2 | 2 | 8 | 8 | 0 |  |  | 2023-07-14 13:00 | 2023-07-14 15:00 | 55t Crane, Crane Operator, Rigger, Fitter | 23SD2
10692425 - 0130 | Not Started | GLSTest-01.BENE.MAINT.2122 | DAWSON2 | Beneficiation | 10692425 - cyclone cluster product downleg holed | 10692425 | 0130 | Install new downleg spool | 0 | Task Dependent | 2023-07-16 15:30 | 2023-07-16 20:30 |  | 0 | 3 | 3 | 12 | 12 | 0 |  |  | 2023-07-16 15:30 | 2023-07-16 20:30 | 55t Crane, Crane Operator, Rigger, Fitter | 23SD2
10692425 - 0170 | Not Started | GLSTest-01.BENE.MAINT.2122 | DAWSON2 | Beneficiation | 10692425 - cyclone cluster product downleg holed | 10692425 | 0170 | Remove rigging gear | 0 | Task Dependent | 2023-07-16 20:30 | 2023-07-16 21:30 |  | 0 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-16 20:30 | 2023-07-16 21:30 | 45ft EWP, Rigger | 23SD2
10699857 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4430 | CLEAN 1 | Phos Acid | 10699857 - 210W SEng Insp PhosSD DrnSmpA Phos | 10699857 | 0010 | Issue Permit - 10699857 - 210W SEng Insp PhosSD DrnSmpA Phos | 0 | Task Dependent | 2023-07-15 10:30 | 2023-07-15 11:00 |  | 33 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 10:30 | 2023-07-15 11:00 | Phos Permit Issuer | 23SD2
10699857 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4430 | CLEAN 1 | Phos Acid | 10699857 - 210W SEng Insp PhosSD DrnSmpA Phos | 10699857 | 0030 | Vac out Sump | 0 | Task Dependent | 2023-07-15 11:00 | 2023-07-15 16:00 |  | 33 | 5 | 5 | 10 | 10 | 0 |  |  | 2023-07-15 11:00 | 2023-07-15 16:00 | Vac Truck, Cleaning Ops | 23SD2
10699857 - 0050 | Not Started | GLSTest-01.PHOS.MAINT.4430 | CLEAN 1 | Phos Acid | 10699857 - 210W SEng Insp PhosSD DrnSmpA Phos | 10699857 | 0050 | Inspect Sump Structure | 0 | Task Dependent | 2023-07-15 16:00 | 2023-07-15 17:00 |  | 33 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-15 16:00 | 2023-07-15 17:00 | Static Engineer | 23SD2
10699857 - 0060 | Not Started | GLSTest-01.PHOS.MAINT.4430 | CLEAN 1 | Phos Acid | 10699857 - 210W SEng Insp PhosSD DrnSmpA Phos | 10699857 | 0060 | Close Permit - 10699857 - 210W SEng Insp PhosSD DrnSmpA Phos | 0 | Task Dependent | 2023-07-15 19:00 | 2023-07-15 19:30 |  | 33 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 19:00 | 2023-07-15 19:30 | Phos Permit Issuer | 23SD2
10704219 - 0010 | Not Started | GLSTest-01.PWR.MAINT.5422 | PWR | Power Station | 10704219 - 3.5Y Mech Srv SDN Gas Fuel Cntrl Valve | 10704219 | 0010 | Issue Permit - 10704219 - 3.5Y Mech Srv SDN Gas Fuel Cntrl Valve | 0 | Task Dependent | 2023-07-15 22:00 | 2023-07-15 22:30 |  | 40 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 22:00 | 2023-07-15 22:30 | Pwr Ops | 23SD2
10704219 - 0020 | Not Started | GLSTest-01.PWR.MAINT.5422 | PWR | Power Station | 10704219 - 3.5Y Mech Srv SDN Gas Fuel Cntrl Valve | 10704219 | 0020 | Isolate Turbine | 0 | Task Dependent | 2023-07-15 22:30 | 2023-07-16 |  | 40 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-15 22:30 | 2023-07-16 | Pwr Elec | 23SD2
10704219 - 0030 | Not Started | GLSTest-01.PWR.MAINT.5422 | PWR | Power Station | 10704219 - 3.5Y Mech Srv SDN Gas Fuel Cntrl Valve | 10704219 | 0030 | 3.5Y Mech Srv Gas Fuel Cntrl Valve Shut | 0 | Task Dependent | 2023-07-16 | 2023-07-16 02:00 |  | 40 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-16 | 2023-07-16 02:00 | Pwr Fitter | 23SD2
10704219 - 0040 | Not Started | GLSTest-01.PWR.MAINT.5422 | PWR | Power Station | 10704219 - 3.5Y Mech Srv SDN Gas Fuel Cntrl Valve | 10704219 | 0040 | De-isolate Turbine | 0 | Task Dependent | 2023-07-16 02:00 | 2023-07-16 03:30 |  | 40 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-16 02:00 | 2023-07-16 03:30 | Pwr Elec | 23SD2
10704219 - 0050 | Not Started | GLSTest-01.PWR.MAINT.5422 | PWR | Power Station | 10704219 - 3.5Y Mech Srv SDN Gas Fuel Cntrl Valve | 10704219 | 0050 | Close Permit - 10704219 - 3.5Y Mech Srv SDN Gas Fuel Cntrl Valve | 0 | Task Dependent | 2023-07-16 03:30 | 2023-07-16 04:00 |  | 40 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 03:30 | 2023-07-16 04:00 | Pwr Ops | 23SD2
10709365 - 0010 | Not Started | GLSTest-01.BENE.MAINT.2122 | DAWSON2 | Beneficiation | 10709365 - Hole in feed line at base of cluster. | 10709365 | 0010 | Issue Permit - 10709365 - Hole in feed line at base of cluster. | 0 | Task Dependent | 2023-07-14 14:30 | 2023-07-14 15:00 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 14:30 | 2023-07-14 15:00 | Bene Permit Issuer | 23SD2
10709365 - 0050 | Not Started | GLSTest-01.BENE.MAINT.2122 | DAWSON2 | Beneficiation | 10709365 - Hole in feed line at base of cluster. | 10709365 | 0050 | Rig up and unbolt pipework cluster - ove | 0 | Task Dependent | 2023-07-14 15:00 | 2023-07-14 20:00 |  | 0 | 3 | 3 | 9 | 9 | 0 |  |  | 2023-07-14 15:00 | 2023-07-14 20:00 | 45ft EWP, Rigger, Fitter | 23SD2
10709365 - 0080 | Not Started | GLSTest-01.BENE.MAINT.2122 | DAWSON2 | Beneficiation | 10709365 - Hole in feed line at base of cluster. | 10709365 | 0080 | Remove valves and pipework from cluster | 0 | Task Dependent | 2023-07-14 20:00 | 2023-07-14 22:00 |  | 0 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-14 20:00 | 2023-07-14 22:00 | Fitter | 23SD2
10709365 - 0090 | Not Started | GLSTest-01.BENE.MAINT.2122 | DAWSON2 | Beneficiation | 10709365 - Hole in feed line at base of cluster. | 10709365 | 0090 | Remove cyclone cluster | 0 | Task Dependent | 2023-07-14 22:00 | 2023-07-15 03:00 |  | 0 | 5 | 5 | 20 | 20 | 0 |  |  | 2023-07-14 22:00 | 2023-07-15 03:00 | 55t Crane, Crane Operator, Rigger, Fitter | 23SD2
10709365 - 0130 | Not Started | GLSTest-01.BENE.MAINT.2122 | DAWSON2 | Beneficiation | 10709365 - Hole in feed line at base of cluster. | 10709365 | 0130 | Install hard barricading | 0 | Task Dependent | 2023-07-15 03:00 | 2023-07-15 04:30 |  | 0 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-15 03:00 | 2023-07-15 04:30 | Scaffolder | 23SD2
10709365 - 0140 | Not Started | GLSTest-01.BENE.MAINT.2122 | DAWSON2 | Beneficiation | 10709365 - Hole in feed line at base of cluster. | 10709365 | 0140 | Install new cluster | 0 | Task Dependent | 2023-07-15 23:30 | 2023-07-16 07:30 |  | 0 | 6 | 6 | 24 | 24 | 0 |  |  | 2023-07-15 23:30 | 2023-07-16 07:30 | 55t Crane, Crane Operator, Rigger, Fitter | 23SD2
10709365 - 0210 | Not Started | GLSTest-01.BENE.MAINT.2122 | DAWSON2 | Beneficiation | 10709365 - Hole in feed line at base of cluster. | 10709365 | 0210 | Reinstate cluster valves | 0 | Task Dependent | 2023-07-16 07:30 | 2023-07-16 10:30 |  | 0 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-16 07:30 | 2023-07-16 10:30 | Fitter | 23SD2
10709365 - 0220 | Not Started | GLSTest-01.BENE.MAINT.2122 | DAWSON2 | Beneficiation | 10709365 - Hole in feed line at base of cluster. | 10709365 | 0220 | Reinstate pipework cluster - overflow | 0 | Task Dependent | 2023-07-16 10:30 | 2023-07-16 13:30 |  | 0 | 3 | 3 | 9 | 9 | 0 |  |  | 2023-07-16 10:30 | 2023-07-16 13:30 | Rigger, Fitter | 23SD2
10709365 - 0250 | Not Started | GLSTest-01.BENE.MAINT.2122 | DAWSON2 | Beneficiation | 10709365 - Hole in feed line at base of cluster. | 10709365 | 0250 | Close Permit - 10709365 - Hole in feed line at base of cluster. | 0 | Task Dependent | 2023-07-16 13:30 | 2023-07-16 14:00 |  | 6 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 13:30 | 2023-07-16 14:00 | Bene Permit Issuer | 23SD2
10715829 - 0010 | Not Started | GLSTest-01.PWR.MAINT.5422 | PWR | Power Station | 10715829 - GT2- Install Vent fan Vibration sensor | 10715829 | 0010 | GT2- Install Vent fan Vibration sensor | 0 | Task Dependent | 2023-07-15 22:30 | 2023-07-16 00:30 |  | 40 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-15 22:30 | 2023-07-16 00:30 | Pwr Fitter | 23SD2
10715830 - 0010 | Not Started | GLSTest-01.PWR.MAINT.5422 | PWR | Power Station | 10715830 - GT2- Install Lube oil cooler VIB Sensor | 10715830 | 0010 | GT2- Install Lube oil cooler VIB Sensor | 0 | Task Dependent | 2023-07-16 01:30 | 2023-07-16 03:30 |  | 40 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-16 01:30 | 2023-07-16 03:30 | Pwr Fitter | 23SD2
10715834 - 0010 | Not Started | GLSTest-01.PWR.MAINT.5442 | PWR | Power Station | 10715834 - GT4- Install Vent fan Vibration sensor | 10715834 | 0010 | GT4- Install Vent fan Vibration sensor | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 09:00 |  | 50.5 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 09:00 | Pwr Fitter | 23SD2
10715835 - 0010 | Not Started | GLSTest-01.PWR.MAINT.5442 | PWR | Power Station | 10715835 - GT4- Install Lube oil Cooler VIB sensor | 10715835 | 0010 | GT4- Install Lube oil Cooler VIB sensor | 0 | Task Dependent | 2023-07-13 02:30 | 2023-07-13 04:30 |  | 73 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-13 02:30 | 2023-07-13 04:30 | Pwr Fitter | 23SD2
10735951 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4440 | FG | Phos Acid | 10735951 - Filter b fume duct hatch | 10735951 | 0010 | filter b fume duct hatch | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 17:00 |  | 28 | 10 | 10 | 10 | 10 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 17:00 | Fibreglasser | 23SD2
10748609 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4430 | DAWSON3 | Phos Acid | 10748609 - A side clothwash tk steam valve | 10748609 | 0010 | Change-out steam valve | 0 | Task Dependent | 2023-07-16 01:30 | 2023-07-16 02:30 |  | 19 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-16 01:30 | 2023-07-16 02:30 | Fitter | 23SD2
10748609 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4430 | DAWSON3 | Phos Acid | 10748609 - A side clothwash tk steam valve | 10748609 | 0020 | Disconnect Electrical | 0 | Task Dependent | 2023-07-16 00:30 | 2023-07-16 01:30 |  | 19 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-16 00:30 | 2023-07-16 01:30 | Elec 1 | 23SD2
10750364 - 0010 | Not Started | GLSTest-01.BENE.MAINT.2211 | ELEC | Beneficiation | 10750364 - 1Y Elec Insp Slurry Tank 2 Agi Mtr Shut | 10750364 | 0010 | Issue Permit - 10750364 - 1Y Elec Insp Slurry Tank 2 Agi Mtr Shut | 0 | Task Dependent | 2023-07-14 16:30 | 2023-07-14 17:00 |  | 17.5 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 2023-07-14 16:30 | 2023-07-14 17:00 | Phos Permit Issuer | 23SD2
10750364 - 0020 | Not Started | GLSTest-01.BENE.MAINT.2211 | ELEC | Beneficiation | 10750364 - 1Y Elec Insp Slurry Tank 2 Agi Mtr Shut | 10750364 | 0020 | Critical motor terminal box inspection | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 09:00 |  | 21.5 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 09:00 | Elec 2 | 23SD2
10750364 - 0030 | Not Started | GLSTest-01.BENE.MAINT.2211 | ELEC | Beneficiation | 10750364 - 1Y Elec Insp Slurry Tank 2 Agi Mtr Shut | 10750364 | 0030 | Close Permit - 10750364 - 1Y Elec Insp Slurry Tank 2 Agi Mtr Shut | 0 | Task Dependent | 2023-07-15 09:00 | 2023-07-15 09:30 |  | 21.5 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 2023-07-15 09:00 | 2023-07-15 09:30 | Phos Permit Issuer | 23SD2
10763534 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON3 | Granulation | 10763534 - 30W MFit Insp GranSD Cmbt Air Fan | 10763534 | 0010 | Issue Permit - 10763534 - 30W MFit Insp GranSD Cmbt Air Fan | 0 | Task Dependent | 2023-07-13 | 2023-07-13 00:30 |  | 32.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 | 2023-07-13 00:30 | Gran Permit Issuer | 23SD2
10763534 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON3 | Granulation | 10763534 - 30W MFit Insp GranSD Cmbt Air Fan | 10763534 | 0020 | Remove guard | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 01:00 |  | 32.5 | 0.5 | 0.5 | 2 | 2 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 01:00 | Franna, Rigger, Crane Operator, Fitter | 23SD2
10763534 - 0060 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON3 | Granulation | 10763534 - 30W MFit Insp GranSD Cmbt Air Fan | 10763534 | 0060 | Inspect Fan Belt | 0 | Task Dependent | 2023-07-13 08:30 | 2023-07-13 10:30 |  | 32.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-13 08:30 | 2023-07-13 10:30 | Fitter | 23SD2
10763534 - 0070 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON3 | Granulation | 10763534 - 30W MFit Insp GranSD Cmbt Air Fan | 10763534 | 0070 | Replace guard | 0 | Task Dependent | 2023-07-13 21:00 | 2023-07-13 21:30 |  | 32.5 | 0.5 | 0.5 | 2 | 2 | 0 |  |  | 2023-07-13 21:00 | 2023-07-13 21:30 | Franna, Rigger, Crane Operator, Fitter | 23SD2
10763534 - 0110 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON3 | Granulation | 10763534 - 30W MFit Insp GranSD Cmbt Air Fan | 10763534 | 0110 | Close Permit - 10763534 - 30W MFit Insp GranSD Cmbt Air Fan | 0 | Task Dependent | 2023-07-13 21:30 | 2023-07-13 22:00 |  | 32.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 21:30 | 2023-07-13 22:00 | Gran Permit Issuer | 23SD2
10764498 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4420 | DAWSON3 | Phos Acid | 10764498 - Install New Poly Line | 10764498 | 0010 | Install New Poly Line | 0 | Task Dependent | 2023-07-16 20:00 | 2023-07-17 02:00 |  | 9 | 6 | 6 | 12 | 12 | 0 |  |  | 2023-07-16 20:00 | 2023-07-17 02:00 | Fitter | 23SD2
10766816 - 0010 | Not Started | GLSTest-01.PWR.MAINT.MISC | PWR | Power Station | 10766816 - Generator Elec Stat Testing | 10766816 | 0010 | Generator Elec Stat Testing - Day 1 | 0 | Task Dependent | 2023-07-13 13:00 | 2023-07-13 16:00 |  | 89.5 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-13 13:00 | 2023-07-13 16:00 | Pwr Elec | 23SD2
10767555 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4629 | DAWSON3 | Granulation | 10767555 - 5Y MFit Repr GranSD Tail Gas Scbr | 10767555 | 0010 | Issue Permit - 10767555 - 5Y MFit Repr GranSD Tail Gas Scbr | 0 | Task Dependent | 2023-07-13 21:30 | 2023-07-13 22:00 |  | 27.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 21:30 | 2023-07-13 22:00 | Gran Permit Issuer | 23SD2
10767555 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4629 | DAWSON3 | Granulation | 10767555 - 5Y MFit Repr GranSD Tail Gas Scbr | 10767555 | 0020 | Replace NRV | 0 | Task Dependent | 2023-07-13 22:00 | 2023-07-14 02:00 |  | 27.5 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-13 22:00 | 2023-07-14 02:00 | Fitter | 23SD2
10767555 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4629 | DAWSON3 | Granulation | 10767555 - 5Y MFit Repr GranSD Tail Gas Scbr | 10767555 | 0030 | Close Permit - 10767555 - 5Y MFit Repr GranSD Tail Gas Scbr | 0 | Task Dependent | 2023-07-14 02:00 | 2023-07-14 02:30 |  | 27.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 02:00 | 2023-07-14 02:30 | Gran Permit Issuer | 23SD2
10767944 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4623 | DAWSON2 | Granulation | 10767944 - Change sprocket on inching drive | 10767944 | 0010 | Issue Permit - 10767944 - Change sprocket on inching drive | 0 | Task Dependent | 2023-07-13 02:00 | 2023-07-13 02:30 |  | 21 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 02:00 | 2023-07-13 02:30 | Gran Permit Issuer | 23SD2
10767944 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4623 | DAWSON2 | Granulation | 10767944 - Change sprocket on inching drive | 10767944 | 0020 | FI-Change sprocket on inching drive | 0 | Task Dependent | 2023-07-13 02:30 | 2023-07-13 04:00 |  | 21 | 1.5 | 1.5 | 3 | 3 | 0 |  |  | 2023-07-13 02:30 | 2023-07-13 04:00 | Fitter | 23SD2
10767944 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4623 | DAWSON2 | Granulation | 10767944 - Change sprocket on inching drive | 10767944 | 0030 | Close Permit - 10767944 - Change sprocket on inching drive | 0 | Task Dependent | 2023-07-13 04:00 | 2023-07-13 04:30 |  | 21 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 04:00 | 2023-07-13 04:30 | Gran Permit Issuer | 23SD2
10770157 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4626 | DAWSON1 | Granulation | 10770157 - 30W MFit Srv GranSD Ovhl Polish Scrn 2 | 10770157 | 0010 | Issue Permit - 10770157 - 30W MFit Srv GranSD Ovhl Polish Scrn 2 | 0 | Task Dependent | 2023-07-13 19:30 | 2023-07-13 20:00 |  | 25.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 19:30 | 2023-07-13 20:00 | Gran Permit Issuer | 23SD2
10770157 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4626 | DAWSON1 | Granulation | 10770157 - 30W MFit Srv GranSD Ovhl Polish Scrn 2 | 10770157 | 0020 | Inspect Screen | 0 | Task Dependent | 2023-07-13 20:00 | 2023-07-14 |  | 25.5 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-13 20:00 | 2023-07-14 | Fitter | 23SD2
10770157 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4626 | DAWSON1 | Granulation | 10770157 - 30W MFit Srv GranSD Ovhl Polish Scrn 2 | 10770157 | 0030 | Close Permit - 10770157 - 30W MFit Srv GranSD Ovhl Polish Scrn 2 | 0 | Task Dependent | 2023-07-14 | 2023-07-14 00:30 |  | 25.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 | 2023-07-14 00:30 | Gran Permit Issuer | 23SD2
10770163 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4626 | DAWSON1 | Granulation | 10770163 - 30W MFit Srv GranSD Ovhl Polish Scrn 1 | 10770163 | 0010 | Issue Permit - 10770163 - 30W MFit Srv GranSD Ovhl Polish Scrn 1 | 0 | Task Dependent | 2023-07-13 12:30 | 2023-07-13 13:00 |  | 25.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 12:30 | 2023-07-13 13:00 | Gran Permit Issuer | 23SD2
10770163 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4626 | DAWSON1 | Granulation | 10770163 - 30W MFit Srv GranSD Ovhl Polish Scrn 1 | 10770163 | 0020 | Inspect Screen | 0 | Task Dependent | 2023-07-13 13:00 | 2023-07-13 17:00 |  | 25.5 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-13 13:00 | 2023-07-13 17:00 | Fitter | 23SD2
10770163 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4626 | DAWSON1 | Granulation | 10770163 - 30W MFit Srv GranSD Ovhl Polish Scrn 1 | 10770163 | 0030 | Close Permit - 10770163 - 30W MFit Srv GranSD Ovhl Polish Scrn 1 | 0 | Task Dependent | 2023-07-13 19:00 | 2023-07-13 19:30 |  | 25.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 19:00 | 2023-07-13 19:30 | Gran Permit Issuer | 23SD2
10770310 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4410 | ELEC | Phos Acid | 10770310 - 60W Elec OLL Prog GldWtrInst 44TK1001 | 10770310 | 0010 | Inspect/Service Gland Water Instruments | 0 | Task Dependent | 2023-07-16 03:30 | 2023-07-16 21:30 |  | 15 | 4 | 4 | 4 | 4 | 0 |  |  | 2023-07-16 03:30 | 2023-07-16 21:30 | Elec 1 | 23SD2
10770310 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4410 | ELEC | Phos Acid | 10770310 - 60W Elec OLL Prog GldWtrInst 44TK1001 | 10770310 | 0020 | Issue Permit - 10770310 - 60W Elec OLL Prog GldWtrInst 44TK1001 | 0 | Task Dependent | 2023-07-16 03:00 | 2023-07-16 03:30 |  | 7 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 03:00 | 2023-07-16 03:30 | Phos Permit Issuer | 23SD2
10770310 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4410 | ELEC | Phos Acid | 10770310 - 60W Elec OLL Prog GldWtrInst 44TK1001 | 10770310 | 0040 | Close Permit - 10770310 - 60W Elec OLL Prog GldWtrInst 44TK1001 | 0 | Task Dependent | 2023-07-16 21:30 | 2023-07-16 22:00 |  | 15 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 21:30 | 2023-07-16 22:00 | Phos Permit Issuer | 23SD2
10771514 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4420 | ELEC | Phos Acid | 10771514 - 60W Elec INT Prog DrvInst 44CB2001 | 10771514 | 0010 | Inspect/Test Belt Instrumentation. | 0 | Task Dependent | 2023-07-16 07:00 | 2023-07-16 09:00 |  | 19 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-16 07:00 | 2023-07-16 09:00 | Elec 3 | 23SD2
10771514 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4420 | ELEC | Phos Acid | 10771514 - 60W Elec INT Prog DrvInst 44CB2001 | 10771514 | 0020 | Issue Permit - 10771514 - 60W Elec INT Prog DrvInst 44CB2001 | 0 | Task Dependent | 2023-07-15 16:30 | 2023-07-15 17:00 |  | 9.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 16:30 | 2023-07-15 17:00 | Phos Permit Issuer | 23SD2
10771514 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4420 | ELEC | Phos Acid | 10771514 - 60W Elec INT Prog DrvInst 44CB2001 | 10771514 | 0030 | Close Permit - 10771514 - 60W Elec INT Prog DrvInst 44CB2001 | 0 | Task Dependent | 2023-07-16 09:00 | 2023-07-16 09:30 |  | 19 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 09:00 | 2023-07-16 09:30 | Phos Permit Issuer | 23SD2
10771534 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4420 | ELEC | Phos Acid | 10771534 - 60W Elec INT Srv DrvLCU 44PC2007 | 10771534 | 0010 | Issue Permit - 10771534 - 60W Elec INT Srv DrvLCU 44PC2007 | 0 | Task Dependent | 2023-07-15 | 2023-07-15 00:30 |  | 23 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 | 2023-07-15 00:30 | Phos Permit Issuer | 23SD2
10771534 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4420 | ELEC | Phos Acid | 10771534 - 60W Elec INT Srv DrvLCU 44PC2007 | 10771534 | 0020 | Inspect/Service Drive Components | 0 | Task Dependent | 2023-07-15 00:30 | 2023-07-15 01:30 |  | 28 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-15 00:30 | 2023-07-15 01:30 | Elec 2 | 23SD2
10771534 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4420 | ELEC | Phos Acid | 10771534 - 60W Elec INT Srv DrvLCU 44PC2007 | 10771534 | 0030 | Close Permit - 10771534 - 60W Elec INT Srv DrvLCU 44PC2007 | 0 | Task Dependent | 2023-07-15 01:30 | 2023-07-15 02:00 |  | 28 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 01:30 | 2023-07-15 02:00 | Phos Permit Issuer | 23SD2
10771713 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4475 | ELEC | Phos Acid | 10771713 - 60W Elec ISO Srv Press 44PT75001 | 10771713 | 0010 | Issue Permit - 10771713 - 60W Elec ISO Srv Press 44PT75001 | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 07:30 |  | 17 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 07:30 | Phos Permit Issuer | 23SD2
10771713 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4475 | ELEC | Phos Acid | 10771713 - 60W Elec ISO Srv Press 44PT75001 | 10771713 | 0020 | Inspect/Service Press Instrument | 0 | Task Dependent | 2023-07-15 07:30 | 2023-07-15 09:30 |  | 17 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-15 07:30 | 2023-07-15 09:30 | 45ft EWP, Elec 4 | 23SD2
10771713 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4475 | ELEC | Phos Acid | 10771713 - 60W Elec ISO Srv Press 44PT75001 | 10771713 | 0040 | Close Permit - 10771713 - 60W Elec ISO Srv Press 44PT75001 | 0 | Task Dependent | 2023-07-15 09:30 | 2023-07-15 10:00 |  | 17 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 09:30 | 2023-07-15 10:00 | Phos Permit Issuer | 23SD2
10772332 - 0040 | Not Started | GLSTest-01.BENE.MAINT.2411 | DAWSON2 | Beneficiation | 10772332 - MF-Make up water holed | 10772332 | 0040 | franna crew to transport pipe | 0 | Task Dependent | 2023-07-16 01:30 | 2023-07-16 02:30 |  | 11 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-16 01:30 | 2023-07-16 02:30 | Franna, Rigger, Crane Operator | 23SD2
10772332 - 0070 | Not Started | GLSTest-01.BENE.MAINT.2411 | DAWSON2 | Beneficiation | 10772332 - MF-Make up water holed | 10772332 | 0070 | Remove/Replace | 0 | Task Dependent | 2023-07-16 01:30 | 2023-07-16 07:30 |  | 11 | 4 | 4 | 16 | 16 | 0 |  |  | 2023-07-16 01:30 | 2023-07-16 07:30 | 45ft EWP, 55t Crane, Crane Operator, Rigger, Fitter | 23SD2
10772935 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.MISC | ELEC | Phos Acid | 10772935 - 2Y Elec Srv ISO Acid MCC | 10772935 | 0010 | Service MCCs | 0 | Task Dependent | 2023-07-15 11:30 | 2023-07-15 13:00 |  | 19.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-15 11:30 | 2023-07-15 13:00 | Elec 3 | 23SD2
10773340 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4438 | ELEC | Phos Acid | 10773340 - 60W Elec OLL Prog CVlv 44TK3807 | 10773340 | 0010 | Issue Permit - 10773340 - 60W Elec OLL Prog CVlv 44TK3807 | 0 | Task Dependent | 2023-07-16 19:00 | 2023-07-16 19:30 |  | 7 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 19:00 | 2023-07-16 19:30 | Phos Permit Issuer | 23SD2
10773340 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4438 | ELEC | Phos Acid | 10773340 - 60W Elec OLL Prog CVlv 44TK3807 | 10773340 | 0020 | Inspect/Service Control Valve | 0 | Task Dependent | 2023-07-16 19:30 | 2023-07-16 21:30 |  | 24 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-16 19:30 | 2023-07-16 21:30 | Elec 1 | 23SD2
10773340 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4438 | ELEC | Phos Acid | 10773340 - 60W Elec OLL Prog CVlv 44TK3807 | 10773340 | 0030 | Close Permit - 10773340 - 60W Elec OLL Prog CVlv 44TK3807 | 0 | Task Dependent | 2023-07-16 21:30 | 2023-07-16 22:00 |  | 24 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 21:30 | 2023-07-16 22:00 | Phos Permit Issuer | 23SD2
10773341 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4438 | ELEC | Phos Acid | 10773341 - 60W Elec OLL Prog CVlv 44TK3806 | 10773341 | 0010 | Issue Permit - 10773341 - 60W Elec OLL Prog CVlv 44TK3806 | 0 | Task Dependent | 2023-07-14 22:00 | 2023-07-14 22:30 |  | 22 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 22:00 | 2023-07-14 22:30 | Phos Permit Issuer | 23SD2
10773341 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4438 | ELEC | Phos Acid | 10773341 - 60W Elec OLL Prog CVlv 44TK3806 | 10773341 | 0020 | Inspect/Service Control Valve | 0 | Task Dependent | 2023-07-14 22:30 | 2023-07-15 02:30 |  | 22 | 4 | 4 | 4 | 4 | 0 |  |  | 2023-07-14 22:30 | 2023-07-15 02:30 | Elec 1 | 23SD2
10773341 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4438 | ELEC | Phos Acid | 10773341 - 60W Elec OLL Prog CVlv 44TK3806 | 10773341 | 0030 | EWP Inspect/Service Control Valve | 0 | Task Dependent | 2023-07-14 22:30 | 2023-07-15 00:30 |  | 24 | 2 | 2 | 0 | 0 | 0 |  |  | 2023-07-14 22:30 | 2023-07-15 00:30 | 45ft EWP | 23SD2
10773341 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4438 | ELEC | Phos Acid | 10773341 - 60W Elec OLL Prog CVlv 44TK3806 | 10773341 | 0040 | Close Permit - 10773341 - 60W Elec OLL Prog CVlv 44TK3806 | 0 | Task Dependent | 2023-07-15 02:30 | 2023-07-15 03:00 |  | 22 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 02:30 | 2023-07-15 03:00 | Phos Permit Issuer | 23SD2
10773343 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4438 | ELEC | Phos Acid | 10773343 - 60W Elec OLL Prog XVlv 44PF3808 | 10773343 | 0010 | Inspect/Service Control Valve | 0 | Task Dependent | 2023-07-14 22:30 | 2023-07-15 00:30 |  | 24 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-14 22:30 | 2023-07-15 00:30 | Elec 2 | 23SD2
10773487 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON2 | Phos Acid | 10773487 - 75W MFit INT Rplc DrvVTM 44XV2502 | 10773487 | 0010 | Issue Permit - 10773487 - 75W MFit INT Rplc DrvVTM 44XV2502 | 0 | Task Dependent | 2023-07-15 20:30 | 2023-07-15 21:00 |  | 17.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 20:30 | 2023-07-15 21:00 | Phos Permit Issuer | 23SD2
10773487 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON2 | Phos Acid | 10773487 - 75W MFit INT Rplc DrvVTM 44XV2502 | 10773487 | 0020 | Inspect/Service Rotork Actuator | 0 | Task Dependent | 2023-07-15 22:30 | 2023-07-16 02:00 |  | 22 | 3.5 | 3.5 | 3.5 | 3.5 | 0 |  |  | 2023-07-15 22:30 | 2023-07-16 02:00 | Elec | 23SD2
10773487 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON2 | Phos Acid | 10773487 - 75W MFit INT Rplc DrvVTM 44XV2502 | 10773487 | 0030 | Disconnect Actuator | 0 | Task Dependent | 2023-07-15 21:00 | 2023-07-15 21:30 |  | 22 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 21:00 | 2023-07-15 21:30 | Elec | 23SD2
10773487 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON2 | Phos Acid | 10773487 - 75W MFit INT Rplc DrvVTM 44XV2502 | 10773487 | 0040 | Remove Actuator | 0 | Task Dependent | 2023-07-15 21:30 | 2023-07-15 22:30 |  | 22 | 1 | 1 | 4 | 4 | 0 |  |  | 2023-07-15 21:30 | 2023-07-15 22:30 | Franna, Crane Operator, Rigger, 60ft EWP, Fitter | 23SD2
10773487 - 0090 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON2 | Phos Acid | 10773487 - 75W MFit INT Rplc DrvVTM 44XV2502 | 10773487 | 0090 | Replace Nut | 0 | Task Dependent | 2023-07-15 22:30 | 2023-07-15 23:30 |  | 24.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-15 22:30 | 2023-07-15 23:30 | 60ft EWP, Fitter | 23SD2
10773487 - 0130 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON2 | Phos Acid | 10773487 - 75W MFit INT Rplc DrvVTM 44XV2502 | 10773487 | 0130 | Install Actuator | 0 | Task Dependent | 2023-07-16 03:00 | 2023-07-16 04:00 |  | 22 | 1 | 1 | 4 | 4 | 0 |  |  | 2023-07-16 03:00 | 2023-07-16 04:00 | Franna, Crane Operator, Rigger, 60ft EWP, Fitter | 23SD2
10773487 - 0140 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON2 | Phos Acid | 10773487 - 75W MFit INT Rplc DrvVTM 44XV2502 | 10773487 | 0140 | Reconnect Actuator | 0 | Task Dependent | 2023-07-16 04:00 | 2023-07-16 04:30 |  | 31 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 04:00 | 2023-07-16 04:30 | Elec | 23SD2
10773487 - 0150 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON2 | Phos Acid | 10773487 - 75W MFit INT Rplc DrvVTM 44XV2502 | 10773487 | 0150 | Replace drive nut | 0 | Task Dependent | 2023-07-16 02:00 | 2023-07-16 03:00 |  | 22 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-16 02:00 | 2023-07-16 03:00 | Elec | 23SD2
10773487 - 0160 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON2 | Phos Acid | 10773487 - 75W MFit INT Rplc DrvVTM 44XV2502 | 10773487 | 0160 | Close Permit - 10773487 - 75W MFit INT Rplc DrvVTM 44XV2502 | 0 | Task Dependent | 2023-07-16 04:30 | 2023-07-16 05:00 |  | 31 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 04:30 | 2023-07-16 05:00 | Phos Permit Issuer | 23SD2
10773488 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4425 | ELEC | Phos Acid | 10773488 - 75W Elec INT Srv DrvLCU 44XV2503 | 10773488 | 0010 | Issue Permit - 10773488 - 75W Elec INT Srv DrvLCU 44XV2503 | 0 | Task Dependent | 2023-07-14 20:30 | 2023-07-14 21:00 |  | 26.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 20:30 | 2023-07-14 21:00 | Phos Permit Issuer | 23SD2
10773488 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4425 | ELEC | Phos Acid | 10773488 - 75W Elec INT Srv DrvLCU 44XV2503 | 10773488 | 0020 | Inspect/Service VTM LCU | 0 | Task Dependent | 2023-07-14 21:00 | 2023-07-14 22:00 |  | 26.5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-14 21:00 | 2023-07-14 22:00 | Elec 1 | 23SD2
10773488 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4425 | ELEC | Phos Acid | 10773488 - 75W Elec INT Srv DrvLCU 44XV2503 | 10773488 | 0030 | Close Permit - 10773488 - 75W Elec INT Srv DrvLCU 44XV2503 | 0 | Task Dependent | 2023-07-14 22:00 | 2023-07-14 22:30 |  | 26.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 22:00 | 2023-07-14 22:30 | Phos Permit Issuer | 23SD2
10773495 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4425 | ELEC | Phos Acid | 10773495 - 60W Elec ISO Srv Press 44PT25001 | 10773495 | 0010 | Issue Permit - 10773495 - 60W Elec ISO Srv Press 44PT25001 | 0 | Task Dependent | 2023-07-15 12:30 | 2023-07-15 13:00 |  | 7.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 12:30 | 2023-07-15 13:00 | Phos Permit Issuer | 23SD2
10773495 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4425 | ELEC | Phos Acid | 10773495 - 60W Elec ISO Srv Press 44PT25001 | 10773495 | 0020 | Inspect/Service Press Instrument | 0 | Task Dependent | 2023-07-15 13:00 | 2023-07-15 17:00 |  | 13 | 4 | 4 | 4 | 4 | 0 |  |  | 2023-07-15 13:00 | 2023-07-15 17:00 | Elec 3 | 23SD2
10773495 - 0025 | Not Started | GLSTest-01.PHOS.MAINT.4425 | ELEC | Phos Acid | 10773495 - 60W Elec ISO Srv Press 44PT25001 | 10773495 | 0025 | FI - Flange Management | 0 | Task Dependent | 2023-07-16 07:00 | 2023-07-16 09:00 |  | 13 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-16 07:00 | 2023-07-16 09:00 | Fitter | 23SD2
10773495 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4425 | ELEC | Phos Acid | 10773495 - 60W Elec ISO Srv Press 44PT25001 | 10773495 | 0030 | Close Permit - 10773495 - 60W Elec ISO Srv Press 44PT25001 | 0 | Task Dependent | 2023-07-16 09:00 | 2023-07-16 09:30 |  | 13 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 09:00 | 2023-07-16 09:30 | Phos Permit Issuer | 23SD2
10773548 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4480 | ELEC | Phos Acid | 10773548 - 720W Elec INT Rplc DrvCell 44CB8001 | 10773548 | 0010 | Issue Permit - 10773548 - 720W Elec INT Rplc DrvCell 44CB8001 | 0 | Task Dependent | 2023-07-16 07:00 | 2023-07-16 07:30 |  | 7 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 07:00 | 2023-07-16 07:30 | Phos Permit Issuer | 23SD2
10773548 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4480 | ELEC | Phos Acid | 10773548 - 720W Elec INT Rplc DrvCell 44CB8001 | 10773548 | 0020 | Inspect/Service Drive Components | 0 | Task Dependent | 2023-07-16 07:30 | 2023-07-16 11:30 |  | 7 | 4 | 4 | 4 | 4 | 0 |  |  | 2023-07-16 07:30 | 2023-07-16 11:30 | Elec 4 | 23SD2
10773548 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4480 | ELEC | Phos Acid | 10773548 - 720W Elec INT Rplc DrvCell 44CB8001 | 10773548 | 0030 | Close Permit - 10773548 - 720W Elec INT Rplc DrvCell 44CB8001 | 0 | Task Dependent | 2023-07-16 11:30 | 2023-07-16 12:00 |  | 7 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 11:30 | 2023-07-16 12:00 | Phos Permit Issuer | 23SD2
10774353 - 0010 | Not Started | GLSTest-01.PWR.MAINT.5422 | PWR | Power Station | 10774353 - Local HMI Screen Not Displaying | 10774353 | 0010 | Local HMI Screen Not Displaying | 0 | Task Dependent | 2023-07-15 22:30 | 2023-07-16 02:30 |  | 41 | 4 | 4 | 4 | 4 | 0 |  |  | 2023-07-15 22:30 | 2023-07-16 02:30 | Pwr Elec | 23SD2
10774593 - 0010 | Not Started | GLSTest-01.PWR.MAINT.5422 | PWR | Power Station | 10774593 - 30W Insp PwrSD Trbn Gnrtr 2 | 10774593 | 0010 | Issue Permit - 10774593 - 30W Insp PwrSD Trbn Gnrtr 2 | 0 | Task Dependent | 2023-07-15 02:00 | 2023-07-15 02:30 |  | 40 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 02:00 | 2023-07-15 02:30 | Pwr Ops | 23SD2
10774593 - 0020 | Not Started | GLSTest-01.PWR.MAINT.5422 | PWR | Power Station | 10774593 - 30W Insp PwrSD Trbn Gnrtr 2 | 10774593 | 0020 | 30W Mech Insp Turbine Generator | 0 | Task Dependent | 2023-07-15 02:30 | 2023-07-15 21:30 |  | 40 | 15 | 15 | 30 | 30 | 0 |  |  | 2023-07-15 02:30 | 2023-07-15 21:30 | Pwr Fitter | 23SD2
10774593 - 0030 | Not Started | GLSTest-01.PWR.MAINT.5422 | PWR | Power Station | 10774593 - 30W Insp PwrSD Trbn Gnrtr 2 | 10774593 | 0030 | 30W Elec Insp Turbine Generator | 0 | Task Dependent | 2023-07-15 02:30 | 2023-07-15 09:30 |  | 50 | 5 | 5 | 10 | 10 | 0 |  |  | 2023-07-15 02:30 | 2023-07-15 09:30 | Pwr Elec | 23SD2
10774593 - 0040 | Not Started | GLSTest-01.PWR.MAINT.5422 | PWR | Power Station | 10774593 - 30W Insp PwrSD Trbn Gnrtr 2 | 10774593 | 0040 | Close Permit - 10774593 - 30W Insp PwrSD Trbn Gnrtr 2 | 0 | Task Dependent | 2023-07-15 21:30 | 2023-07-15 22:00 |  | 40 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 21:30 | 2023-07-15 22:00 | Pwr Ops | 23SD2
10774594 - 0010 | Not Started | GLSTest-01.PWR.MAINT.5442 | PWR | Power Station | 10774594 - HVS - 60W Insp PwrSD Trbn Gnrtr 4 | 10774594 | 0010 | Issue Permit - 10774594 - HVS - 60W Insp PwrSD Trbn Gnrtr 4 | 0 | Task Dependent | 2023-07-13 02:00 | 2023-07-13 02:30 |  | 40 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 02:00 | 2023-07-13 02:30 | Pwr Ops | 23SD2
10774594 - 0020 | Not Started | GLSTest-01.PWR.MAINT.5442 | PWR | Power Station | 10774594 - HVS - 60W Insp PwrSD Trbn Gnrtr 4 | 10774594 | 0020 | HV Switching requirements | 0 | Task Dependent | 2023-07-13 02:30 | 2023-07-13 04:30 |  | 40 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-13 02:30 | 2023-07-13 04:30 | HV Elec | 23SD2
10774594 - 0030 | Not Started | GLSTest-01.PWR.MAINT.5442 | PWR | Power Station | 10774594 - HVS - 60W Insp PwrSD Trbn Gnrtr 4 | 10774594 | 0030 | 60W Mech Insp Turbine Generator | 0 | Task Dependent | 2023-07-13 04:30 | 2023-07-14 04:30 |  | 40 | 20 | 20 | 40 | 40 | 0 |  |  | 2023-07-13 04:30 | 2023-07-14 04:30 | 60ft EWP, Pwr Fitter | 23SD2
10774594 - 0040 | Not Started | GLSTest-01.PWR.MAINT.5442 | PWR | Power Station | 10774594 - HVS - 60W Insp PwrSD Trbn Gnrtr 4 | 10774594 | 0040 | 60W Elec Insp Turbine Generator | 0 | Task Dependent | 2023-07-13 04:30 | 2023-07-13 23:30 |  | 45 | 15 | 15 | 30 | 30 | 0 |  |  | 2023-07-13 04:30 | 2023-07-13 23:30 | Pwr Elec | 23SD2
10774594 - 0050 | Not Started | GLSTest-01.PWR.MAINT.5442 | PWR | Power Station | 10774594 - HVS - 60W Insp PwrSD Trbn Gnrtr 4 | 10774594 | 0050 | HV Switching requirements | 0 | Task Dependent | 2023-07-14 04:30 | 2023-07-14 08:30 |  | 40 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-14 04:30 | 2023-07-14 08:30 | HV Elec | 23SD2
10774594 - 0060 | Not Started | GLSTest-01.PWR.MAINT.5442 | PWR | Power Station | 10774594 - HVS - 60W Insp PwrSD Trbn Gnrtr 4 | 10774594 | 0060 | Close Permit - 10774594 - HVS - 60W Insp PwrSD Trbn Gnrtr 4 | 0 | Task Dependent | 2023-07-14 08:30 | 2023-07-14 09:00 |  | 40 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 08:30 | 2023-07-14 09:00 | Pwr Ops | 23SD2
10777727 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4623 | DAWSON3 | Granulation | 10777727 - 30W MFit Srv GranSD Pulv Lvl | 10777727 | 0010 | Inspect Pulverizers | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-14 00:30 |  | 34 | 20 | 20 | 40 | 40 | 0 |  |  | 2023-07-13 00:30 | 2023-07-14 00:30 | Fitter | 23SD2
10777727 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4623 | DAWSON3 | Granulation | 10777727 - 30W MFit Srv GranSD Pulv Lvl | 10777727 | 0020 | Issue Permit - 10777727 - 30W MFit Srv GranSD Pulv Lvl | 0 | Task Dependent | 2023-07-13 | 2023-07-13 00:30 |  | 34 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 | 2023-07-13 00:30 | Gran Permit Issuer | 23SD2
10777727 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4623 | DAWSON3 | Granulation | 10777727 - 30W MFit Srv GranSD Pulv Lvl | 10777727 | 0030 | Close Permit - 10777727 - 30W MFit Srv GranSD Pulv Lvl | 0 | Task Dependent | 2023-07-14 00:30 | 2023-07-14 01:00 |  | 34 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 00:30 | 2023-07-14 01:00 | Gran Permit Issuer | 23SD2
10779936 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10779936 - 15W MFit Inst/Rmv PhosSD Reactors Fans | 10779936 | 0005 | Issue Permit - 10779936 - 15W MFit Inst/Rmv PhosSD Reactors Fans | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 07:30 |  | 6.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 07:30 | Phos Permit Issuer | 23SD2
10779936 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10779936 - 15W MFit Inst/Rmv PhosSD Reactors Fans | 10779936 | 0010 | Install Fans on top of Reactors | 0 | Task Dependent | 2023-07-14 07:30 | 2023-07-14 10:30 |  | 6.5 | 3 | 3 | 12 | 12 | 0 |  |  | 2023-07-14 07:30 | 2023-07-14 10:30 | 55t Crane, Rigger, Crane Operator, Fitter | 23SD2
10779936 - 0050 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10779936 - 15W MFit Inst/Rmv PhosSD Reactors Fans | 10779936 | 0050 | Remove Fans from Reactors | 0 | Task Dependent | 2023-07-17 04:00 | 2023-07-17 09:00 |  | 15.5 | 3 | 3 | 12 | 12 | 0 |  |  | 2023-07-17 04:00 | 2023-07-17 09:00 | 55t Crane, Rigger, Crane Operator, Fitter | 23SD2
10779936 - 0090 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10779936 - 15W MFit Inst/Rmv PhosSD Reactors Fans | 10779936 | 0090 | Close Permit - 10779936 - 15W MFit Inst/Rmv PhosSD Reactors Fans | 0 | Task Dependent | 2023-07-17 09:00 | 2023-07-17 09:30 |  | 15.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-17 09:00 | 2023-07-17 09:30 | Phos Permit Issuer | 23SD2
10783315 - 0010 | Not Started | GLSTest-01.BENE.MAINT.2122 | BMW | Beneficiation | 10783315 - Replace corroded beams | 10783315 | 0010 | Issue Permit - 10783315 - Replace coroded beams | 0 | Task Dependent | 2023-07-15 04:30 | 2023-07-15 05:00 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 04:30 | 2023-07-15 05:00 | Bene Permit Issuer | 23SD2
10783315 - 0050 | Not Started | GLSTest-01.BENE.MAINT.2122 | BMW | Beneficiation | 10783315 - Replace corroded beams | 10783315 | 0050 | Repair as per assessment | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 23:30 |  | 0 | 14.5 | 14.5 | 29 | 29 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 23:30 | BMW | 23SD2
10783315 - 0080 | Not Started | GLSTest-01.BENE.MAINT.2122 | BMW | Beneficiation | 10783315 - Replace corroded beams | 10783315 | 0080 | Close Permit - 10783315 - Replace coroded beams | 0 | Task Dependent | 2023-07-15 23:30 | 2023-07-16 |  | 22 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 23:30 | 2023-07-16 | Bene Permit Issuer | 23SD2
10783688 - 0010 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON2 | Beneficiation | 10783688 - 30W MFit Insp BeneSD Ball Mill | 10783688 | 0010 | Issue Permit - 10783688 - 30W MFit Insp BeneSD Ball Mill | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 07:30 |  | 41 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 07:30 | Bene Permit Issuer | 23SD2
10783688 - 0020 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON2 | Beneficiation | 10783688 - 30W MFit Insp BeneSD Ball Mill | 10783688 | 0020 | 30W Mech Insp Ball Mill Shut | 0 | Task Dependent | 2023-07-14 07:30 | 2023-07-14 15:30 |  | 41 | 8 | 8 | 16 | 16 | 0 |  |  | 2023-07-14 07:30 | 2023-07-14 15:30 | Fitter | 23SD2
10783688 - 0030 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON2 | Beneficiation | 10783688 - 30W MFit Insp BeneSD Ball Mill | 10783688 | 0030 | Close Permit - 10783688 - 30W MFit Insp BeneSD Ball Mill | 0 | Task Dependent | 2023-07-14 15:30 | 2023-07-14 16:00 |  | 41 | 0.5 | 0.5 | 0 | 0 | 0 |  |  | 2023-07-14 15:30 | 2023-07-14 16:00 | Bene Permit Issuer | 23SD2
10784951 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4623 | DAWSON3 | Granulation | 10784951 - 30W MFit Insp GranSD Fines Cnv | 10784951 | 0010 | Issue Permit - 10784951 - 30W MFit Insp GranSD Fines Cnv | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 01:00 |  | 27.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 01:00 | Gran Permit Issuer | 23SD2
10784951 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4623 | DAWSON3 | Granulation | 10784951 - 30W MFit Insp GranSD Fines Cnv | 10784951 | 0020 | Inspect Conveyor V-Belts | 0 | Task Dependent | 2023-07-13 01:00 | 2023-07-13 05:00 |  | 27.5 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-13 01:00 | 2023-07-13 05:00 | Fitter | 23SD2
10784951 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4623 | DAWSON3 | Granulation | 10784951 - 30W MFit Insp GranSD Fines Cnv | 10784951 | 0030 | Close Permit - 10784951 - 30W MFit Insp GranSD Fines Cnv | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 07:30 |  | 27.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 07:30 | Gran Permit Issuer | 23SD2
10785074 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4440 | ELEC | Phos Acid | 10785074 - 60W Elec INT Rplc DrvCntrl 44FC4001 | 10785074 | 0010 | Issue Permit - 10785074 - 60W Elec INT Rplc DrvCntrl 44FC4001 | 0 | Task Dependent | 2023-07-15 03:00 | 2023-07-15 03:30 |  | 18 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 03:00 | 2023-07-15 03:30 | Phos Permit Issuer | 23SD2
10785074 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4440 | ELEC | Phos Acid | 10785074 - 60W Elec INT Rplc DrvCntrl 44FC4001 | 10785074 | 0020 | Inspect/service Variable Speed Drive | 0 | Task Dependent | 2023-07-15 03:30 | 2023-07-15 04:30 |  | 18 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-15 03:30 | 2023-07-15 04:30 | Elec 1 | 23SD2
10785074 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4440 | ELEC | Phos Acid | 10785074 - 60W Elec INT Rplc DrvCntrl 44FC4001 | 10785074 | 0030 | Close Permit - 10785074 - 60W Elec INT Rplc DrvCntrl 44FC4001 | 0 | Task Dependent | 2023-07-15 04:30 | 2023-07-15 05:00 |  | 18 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 04:30 | 2023-07-15 05:00 | Phos Permit Issuer | 23SD2
10785075 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4440 | ELEC | Phos Acid | 10785075 - 60W Elec INT Srv DrvLCU 44FC4001 | 10785075 | 0010 | Issue Permit - 10785075 - 60W Elec INT Srv DrvLCU 44FC4001 | 0 | Task Dependent | 2023-07-15 03:00 | 2023-07-15 03:30 |  | 17 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 03:00 | 2023-07-15 03:30 | Phos Permit Issuer | 23SD2
10785075 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4440 | ELEC | Phos Acid | 10785075 - 60W Elec INT Srv DrvLCU 44FC4001 | 10785075 | 0020 | Inspect/Service Drive Components | 0 | Task Dependent | 2023-07-15 03:30 | 2023-07-15 19:30 |  | 17 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-15 03:30 | 2023-07-15 19:30 | Elec 1 | 23SD2
10785075 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4440 | ELEC | Phos Acid | 10785075 - 60W Elec INT Srv DrvLCU 44FC4001 | 10785075 | 0030 | Close Permit - 10785075 - 60W Elec INT Srv DrvLCU 44FC4001 | 0 | Task Dependent | 2023-07-15 19:30 | 2023-07-15 20:00 |  | 17 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 19:30 | 2023-07-15 20:00 | Phos Permit Issuer | 23SD2
10785076 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4420 | ELEC | Phos Acid | 10785076 - 90W Elec INT Srv DrvCell 44CB2001 | 10785076 | 0010 | Issue Permit - 10785076 - 90W Elec INT Srv DrvCell 44CB2001 | 0 | Task Dependent | 2023-07-16 08:30 | 2023-07-16 09:00 |  | 8 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 08:30 | 2023-07-16 09:00 | Phos Permit Issuer | 23SD2
10785076 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4420 | ELEC | Phos Acid | 10785076 - 90W Elec INT Srv DrvCell 44CB2001 | 10785076 | 0020 | Inspect/Service Drive Components | 0 | Task Dependent | 2023-07-16 09:00 | 2023-07-16 10:30 |  | 19.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-16 09:00 | 2023-07-16 10:30 | Elec 3 | 23SD2
10785076 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4420 | ELEC | Phos Acid | 10785076 - 90W Elec INT Srv DrvCell 44CB2001 | 10785076 | 0030 | Close Permit - 10785076 - 90W Elec INT Srv DrvCell 44CB2001 | 0 | Task Dependent | 2023-07-16 10:30 | 2023-07-16 11:00 |  | 19.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 10:30 | 2023-07-16 11:00 | Phos Permit Issuer | 23SD2
10785429 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4420 | DAWSON2 | Phos Acid | 10785429 - FI-2008 discharge line wrapped | 10785429 | 0010 | FI-2008 discharge line wrapped | 0 | Task Dependent | 2023-07-15 03:00 | 2023-07-15 15:00 |  | 38 | 10 | 10 | 20 | 20 | 0 |  |  | 2023-07-15 03:00 | 2023-07-15 15:00 | 80ft EWP, Fitter | 23SD2
10785429 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4420 | DAWSON2 | Phos Acid | 10785429 - FI-2008 discharge line wrapped | 10785429 | 0030 | Franna Pick up and Carry | 0 | Task Dependent | 2023-07-15 03:00 | 2023-07-15 05:00 |  | 46 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-15 03:00 | 2023-07-15 05:00 | Franna, Rigger, Crane Operator | 23SD2
10786138 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4425 | ELEC | Phos Acid | 10786138 - 60W Elec INT Srv DrvLCU 44PC2505 | 10786138 | 0010 | Issue Permit - 10786138 - 60W Elec INT Srv DrvLCU 44PC2505 | 0 | Task Dependent | 2023-07-14 22:00 | 2023-07-14 22:30 |  | 24.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 22:00 | 2023-07-14 22:30 | Phos Permit Issuer | 23SD2
10786138 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4425 | ELEC | Phos Acid | 10786138 - 60W Elec INT Srv DrvLCU 44PC2505 | 10786138 | 0020 | Inspect/Service Drive Components | 0 | Task Dependent | 2023-07-14 22:30 | 2023-07-15 |  | 24.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-14 22:30 | 2023-07-15 | Elec 1 | 23SD2
10786138 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4425 | ELEC | Phos Acid | 10786138 - 60W Elec INT Srv DrvLCU 44PC2505 | 10786138 | 0030 | Close Permit - 10786138 - 60W Elec INT Srv DrvLCU 44PC2505 | 0 | Task Dependent | 2023-07-15 | 2023-07-15 00:30 |  | 24.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 | 2023-07-15 00:30 | Phos Permit Issuer | 23SD2
10786988 - 0005 | Not Started | GLSTest-01.GRAN.MAINT.4622 | KINGS | Granulation | 10786988 - 4M Cntr Align GranSD Granulator | 10786988 | 0005 | Issue Permit - 10786988 - 4M Cntr Align GranSD Granulator | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 07:30 |  | 40 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 07:30 | Gran Permit Issuer | 23SD2
10786988 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | KINGS | Granulation | 10786988 - 4M Cntr Align GranSD Granulator | 10786988 | 0010 | 4M Mech Align Granulator Alignment | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 17:00 |  | 40 | 10 | 10 | 20 | 20 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 17:00 | Contract Fitter | 23SD2
10786988 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | KINGS | Granulation | 10786988 - 4M Cntr Align GranSD Granulator | 10786988 | 0030 | Close Permit - 10786988 - 4M Cntr Align GranSD Granulator | 0 | Task Dependent | 2023-07-13 16:30 | 2023-07-13 17:00 |  | 40 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 16:30 | 2023-07-13 17:00 | Gran Permit Issuer | 23SD2
10786989 - 0005 | Not Started | GLSTest-01.GRAN.MAINT.4622 | KINGS | Granulation | 10786989 - 4M Cntr Align GranSD Dryer | 10786989 | 0005 | Issue Permit - 10786989 - 4M Cntr Align GranSD Dryer | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 07:30 |  | 20 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 07:30 | Gran Permit Issuer | 23SD2
10786989 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | KINGS | Granulation | 10786989 - 4M Cntr Align GranSD Dryer | 10786989 | 0010 | 4M Mech Insp Dryer Alignment | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 17:00 |  | 20 | 10 | 10 | 20 | 20 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 17:00 | Contract Fitter | 23SD2
10786989 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | KINGS | Granulation | 10786989 - 4M Cntr Align GranSD Dryer | 10786989 | 0030 | Close Permit - 10786989 - 4M Cntr Align GranSD Dryer | 0 | Task Dependent | 2023-07-14 16:30 | 2023-07-14 17:00 |  | 20 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 16:30 | 2023-07-14 17:00 | Gran Permit Issuer | 23SD2
10788536 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4629 | GRAN | Granulation | 10788536 - 15W Prod Srv GranSD NH3 Sys | 10788536 | 0010 | Issue Permit - 10788536 - 15W Prod Srv GranSD NH3 Sys | 0 | Task Dependent | 2023-07-13 10:30 | 2023-07-13 11:00 |  | 28.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 10:30 | 2023-07-13 11:00 | Gran Permit Issuer | 23SD2
10788536 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4629 | GRAN | Granulation | 10788536 - 15W Prod Srv GranSD NH3 Sys | 10788536 | 0020 | Test Fan Damper | 0 | Task Dependent | 2023-07-13 11:00 | 2023-07-13 14:00 |  | 28.5 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-13 11:00 | 2023-07-13 14:00 | Gran Ops | 23SD2
10788536 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4629 | GRAN | Granulation | 10788536 - 15W Prod Srv GranSD NH3 Sys | 10788536 | 0030 | Close Permit - 10788536 - 15W Prod Srv GranSD NH3 Sys | 0 | Task Dependent | 2023-07-13 14:00 | 2023-07-13 14:30 |  | 28.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 14:00 | 2023-07-13 14:30 | Gran Permit Issuer | 23SD2
10788578 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4480 | RUBBER | Phos Acid | 10788578 - 15W MFit Rplc PhosSD 44CB8001 | 10788578 | 0010 | Issue Permit - 10788578 - 15W MFit Rplc PhosSD 44CB8001 | 0 | Task Dependent | 2023-07-15 10:30 | 2023-07-15 11:00 |  | 36 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 10:30 | 2023-07-15 11:00 | Phos Permit Issuer | 23SD2
10788578 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4480 | RUBBER | Phos Acid | 10788578 - 15W MFit Rplc PhosSD 44CB8001 | 10788578 | 0020 | Inspect Conveyor | 0 | Task Dependent | 2023-07-16 01:00 | 2023-07-16 02:30 |  | 25 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-16 01:00 | 2023-07-16 02:30 | Rubber | 23SD2
10788578 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4480 | RUBBER | Phos Acid | 10788578 - 15W MFit Rplc PhosSD 44CB8001 | 10788578 | 0030 | Clean scraper bolts | 0 | Task Dependent | 2023-07-15 11:00 | 2023-07-15 12:00 |  | 36 | 1 | 1 | 3 | 3 | 0 |  |  | 2023-07-15 11:00 | 2023-07-15 12:00 | Waterblast Truck, Cleaning Ops | 23SD2
10788578 - 0050 | Not Started | GLSTest-01.PHOS.MAINT.4480 | RUBBER | Phos Acid | 10788578 - 15W MFit Rplc PhosSD 44CB8001 | 10788578 | 0050 | Replace Scraper | 0 | Task Dependent | 2023-07-16 02:30 | 2023-07-16 08:30 |  | 25 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-16 02:30 | 2023-07-16 08:30 | Rubber | 23SD2
10788578 - 0060 | Not Started | GLSTest-01.PHOS.MAINT.4480 | RUBBER | Phos Acid | 10788578 - 15W MFit Rplc PhosSD 44CB8001 | 10788578 | 0060 | Close Permit - 10788578 - 15W MFit Rplc PhosSD 44CB8001 | 0 | Task Dependent | 2023-07-16 08:30 | 2023-07-16 09:00 |  | 25 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 08:30 | 2023-07-16 09:00 | Phos Permit Issuer | 23SD2
10788587 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4420 | DAWSON3 | Phos Acid | 10788587 - 15W MFit Rplc PhosSD 41PC2009 | 10788587 | 0010 | Issue Permit - 10788587 - 15W MFit Rplc PhosSD 41PC2009 | 0 | Task Dependent | 2023-07-15 01:30 | 2023-07-15 02:00 |  | 38 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 01:30 | 2023-07-15 02:00 | Phos Permit Issuer | 23SD2
10788587 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4420 | DAWSON3 | Phos Acid | 10788587 - 15W MFit Rplc PhosSD 41PC2009 | 10788587 | 0020 | Remove Pump | 0 | Task Dependent | 2023-07-15 02:00 | 2023-07-15 04:00 |  | 38 | 2 | 2 | 8 | 8 | 0 |  |  | 2023-07-15 02:00 | 2023-07-15 04:00 | Crane Operator, Rigger, Franna, Fitter | 23SD2
10788587 - 0060 | Not Started | GLSTest-01.PHOS.MAINT.4420 | DAWSON3 | Phos Acid | 10788587 - 15W MFit Rplc PhosSD 41PC2009 | 10788587 | 0060 | Replace Pump | 0 | Task Dependent | 2023-07-15 04:00 | 2023-07-15 08:00 |  | 38 | 2 | 2 | 8 | 8 | 0 |  |  | 2023-07-15 04:00 | 2023-07-15 08:00 | Crane Operator, Rigger, Franna, Fitter | 23SD2
10788587 - 0100 | Not Started | GLSTest-01.PHOS.MAINT.4420 | DAWSON3 | Phos Acid | 10788587 - 15W MFit Rplc PhosSD 41PC2009 | 10788587 | 0100 | Close Permit - 10788587 - 15W MFit Rplc PhosSD 41PC2009 | 0 | Task Dependent | 2023-07-15 08:00 | 2023-07-15 08:30 |  | 38 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 08:00 | 2023-07-15 08:30 | Phos Permit Issuer | 23SD2
10788588 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4420 | RUBBER | Phos Acid | 10788588 - 15W MFit Insp PhosSD 41CB2001 | 10788588 | 0010 | Issue Permit - 10788588 - 15W MFit Insp PhosSD 41CB2001 | 0 | Task Dependent | 2023-07-14 23:00 | 2023-07-14 23:30 |  | 46.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 23:00 | 2023-07-14 23:30 | Phos Permit Issuer | 23SD2
10788588 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4420 | RUBBER | Phos Acid | 10788588 - 15W MFit Insp PhosSD 41CB2001 | 10788588 | 0020 | Inspect Conveyor | 0 | Task Dependent | 2023-07-14 23:30 | 2023-07-15 |  | 46.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 23:30 | 2023-07-15 | Rubber | 23SD2
10788593 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4480 | RUBBER | Phos Acid | 10788593 - 15W MFit Rplc ClcnConv PhosSD 44CB8003 | 10788593 | 0010 | Issue Permit - 10788593 - 15W MFit Rplc ClcnConv PhosSD 44CB8003 | 0 | Task Dependent | 2023-07-15 08:00 | 2023-07-15 08:30 |  | 11.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 08:00 | 2023-07-15 08:30 | Phos Permit Issuer | 23SD2
10788593 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4480 | RUBBER | Phos Acid | 10788593 - 15W MFit Rplc ClcnConv PhosSD 44CB8003 | 10788593 | 0020 | Inspect Conveyor | 0 | Task Dependent | 2023-07-16 07:00 | 2023-07-16 08:30 |  | 15 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-16 07:00 | 2023-07-16 08:30 | Rubber | 23SD2
10788593 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4480 | CLEAN 2 | Phos Acid | 10788593 - 15W MFit Rplc ClcnConv PhosSD 44CB8003 | 10788593 | 0030 | Clean scraper bolts | 0 | Task Dependent | 2023-07-15 08:30 | 2023-07-15 09:30 |  | 11.5 | 1 | 1 | 3 | 3 | 0 |  |  | 2023-07-15 08:30 | 2023-07-15 09:30 | Waterblast Truck, Cleaning Ops | 23SD2
10788593 - 0050 | Not Started | GLSTest-01.PHOS.MAINT.4480 | RUBBER | Phos Acid | 10788593 - 15W MFit Rplc ClcnConv PhosSD 44CB8003 | 10788593 | 0050 | Replace Scraper | 0 | Task Dependent | 2023-07-16 08:30 | 2023-07-16 12:30 |  | 15 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-16 08:30 | 2023-07-16 12:30 | Rubber | 23SD2
10788593 - 0060 | Not Started | GLSTest-01.PHOS.MAINT.4480 | RUBBER | Phos Acid | 10788593 - 15W MFit Rplc ClcnConv PhosSD 44CB8003 | 10788593 | 0060 | Close Permit - 10788593 - 15W MFit Rplc ClcnConv PhosSD 44CB8003 | 0 | Task Dependent | 2023-07-16 12:30 | 2023-07-16 13:00 |  | 31.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 12:30 | 2023-07-16 13:00 | Phos Permit Issuer | 23SD2
10788624 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4435 | ELEC | Phos Acid | 10788624 - 60W Elec INT Srv DrvLCU 44PC3501 | 10788624 | 0010 | Issue Permit - 10788624 - 60W Elec INT Srv DrvLCU 44PC3501 | 0 | Task Dependent | 2023-07-15 11:00 | 2023-07-15 11:30 |  | 15.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 11:00 | 2023-07-15 11:30 | Phos Permit Issuer | 23SD2
10788624 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4435 | ELEC | Phos Acid | 10788624 - 60W Elec INT Srv DrvLCU 44PC3501 | 10788624 | 0020 | Inspect/Service Drive Components | 0 | Task Dependent | 2023-07-15 11:30 | 2023-07-15 13:00 |  | 15.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-15 11:30 | 2023-07-15 13:00 | Projects Elec | 23SD2
10788624 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4435 | ELEC | Phos Acid | 10788624 - 60W Elec INT Srv DrvLCU 44PC3501 | 10788624 | 0030 | Close Permit - 10788624 - 60W Elec INT Srv DrvLCU 44PC3501 | 0 | Task Dependent | 2023-07-15 13:00 | 2023-07-15 13:30 |  | 15.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 13:00 | 2023-07-15 13:30 | Phos Permit Issuer | 23SD2
10788629 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4425 | PHOS | Phos Acid | 10788629 - 15W Prod Insp Pump Skid PhosSD HHR | 10788629 | 0010 | Inspect Pump | 0 | Task Dependent | 2023-07-15 | 2023-07-15 00:30 |  | 36 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 | 2023-07-15 00:30 | Phos Ops | 23SD2
10788629 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4425 | PHOS | Phos Acid | 10788629 - 15W Prod Insp Pump Skid PhosSD HHR | 10788629 | 0020 | Inspect Belt Drive | 0 | Task Dependent | 2023-07-15 00:30 | 2023-07-15 01:00 |  | 36 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 00:30 | 2023-07-15 01:00 | Phos Ops | 23SD2
10789290 - 0010 | Not Started | GLSTest-01.ACID.MAINT.4310 | DAWSON3 | Phos Acid | 10789290 - FI-Replace PSV 43PSV10009 | 10789290 | 0010 | FI-Replace PSV 43PSV10009 | 0 | Task Dependent | 2023-07-15 19:30 | 2023-07-15 23:30 |  | 19 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-15 19:30 | 2023-07-15 23:30 | Fitter | 23SD2
10789707 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON1 | Phos Acid | 10789707 - 15W MFit Rmv PhosSD Reactor Spargers | 10789707 | 0010 | Remove Reactor Spargers | 0 | Task Dependent | 2023-07-17 14:00 | 2023-07-17 20:00 |  | 16.5 | 4 | 4 | 16 | 16 | 0 |  |  | 2023-07-17 14:00 | 2023-07-17 20:00 | 55t Crane, Rigger, Crane Operator, Fitter | 23SD2
10789707 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON1 | Phos Acid | 10789707 - 15W MFit Rmv PhosSD Reactor Spargers | 10789707 | 0020 | Install Reactor Spargers | 0 | Task Dependent | 2023-07-16 19:30 | 2023-07-16 23:30 |  | 4 | 4 | 4 | 16 | 16 | 0 |  |  | 2023-07-16 19:30 | 2023-07-16 23:30 | 55t Crane, Rigger, Crane Operator, Fitter | 23SD2
10789760 - 0005 | Not Started | GLSTest-01.GRAN.MAINT.MISC | DAWSON1 | Granulation | 10789760 - 15W MFit Insp GranSD Dryside Hatches | 10789760 | 0005 | Issue Permit - 10789760 - 15W MFit Insp GranSD Dryside Hatches | 0 | Task Dependent | 2023-07-12 10:30 | 2023-07-12 11:00 |  | 11 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 10:30 | 2023-07-12 11:00 | Gran Permit Issuer | 23SD2
10789760 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.MISC | DAWSON1 | Granulation | 10789760 - 15W MFit Insp GranSD Dryside Hatches | 10789760 | 0010 | 15W Mech Insp Open Hatches before Clean | 0 | Task Dependent | 2023-07-12 11:00 | 2023-07-12 23:00 |  | 11 | 10 | 10 | 30 | 30 | 0 |  |  | 2023-07-12 11:00 | 2023-07-12 23:00 | Fitter | 23SD2
10789760 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.MISC | DAWSON1 | Granulation | 10789760 - 15W MFit Insp GranSD Dryside Hatches | 10789760 | 0020 | 15W Mech Insp Close Hatches after Clean | 0 | Task Dependent | 2023-07-13 13:00 | 2023-07-14 01:00 |  | 19 | 10 | 10 | 30 | 30 | 0 |  |  | 2023-07-13 13:00 | 2023-07-14 01:00 | Fitter | 23SD2
10789760 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.MISC | DAWSON1 | Granulation | 10789760 - 15W MFit Insp GranSD Dryside Hatches | 10789760 | 0030 | Close Permit - 10789760 - 15W MFit Insp GranSD Dryside Hatches | 0 | Task Dependent | 2023-07-14 01:00 | 2023-07-14 01:30 |  | 33.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 01:00 | 2023-07-14 01:30 | Gran Permit Issuer | 23SD2
10789761 - 0005 | Not Started | GLSTest-01.GRAN.MAINT.MISC | DAWSON1 | Granulation | 10789761 - 15W MFit Insp GranSD Wetside Hatches | 10789761 | 0005 | Issue Permit - 10789761 - 15W MFit Insp GranSD Wetside Hatches | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 01:00 |  | 19 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 01:00 | Gran Permit Issuer | 23SD2
10789761 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.MISC | DAWSON1 | Granulation | 10789761 - 15W MFit Insp GranSD Wetside Hatches | 10789761 | 0010 | 15W Mech Insp Open Hatches before Clean | 0 | Task Dependent | 2023-07-13 01:00 | 2023-07-13 13:00 |  | 19 | 10 | 10 | 30 | 30 | 0 |  |  | 2023-07-13 01:00 | 2023-07-13 13:00 | Fitter | 23SD2
10789761 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.MISC | DAWSON1 | Granulation | 10789761 - 15W MFit Insp GranSD Wetside Hatches | 10789761 | 0020 | 15W Mech Insp Close Hatches after Clean | 0 | Task Dependent | 2023-07-14 01:00 | 2023-07-14 13:00 |  | 19 | 10 | 10 | 30 | 30 | 0 |  |  | 2023-07-14 01:00 | 2023-07-14 13:00 | Fitter | 23SD2
10789761 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.MISC | DAWSON1 | Granulation | 10789761 - 15W MFit Insp GranSD Wetside Hatches | 10789761 | 0030 | Close Permit - 10789761 - 15W MFit Insp GranSD Wetside Hatches | 0 | Task Dependent | 2023-07-14 13:00 | 2023-07-14 13:30 |  | 19 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 13:00 | 2023-07-14 13:30 | Gran Permit Issuer | 23SD2
10789789 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4911 | ELEC | Granulation | 10789789 - 60W Elec Srv GranSD Weigh Strg Shd Cnv | 10789789 | 0010 | Service Weightometer | 0 | Task Dependent | 2023-07-13 13:30 | 2023-07-13 16:30 |  | 25.5 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-13 13:30 | 2023-07-13 16:30 | Elec 3 | 23SD2
10789802 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4911 | RUBBER | Granulation | 10789802 - 15W MFit Insp GranSD Fert Syst | 10789802 | 0010 | Issue Permit - 10789802 - 15W MFit Insp GranSD Fert Syst | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 07:30 |  | 43 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 07:30 | Gran Permit Issuer | 23SD2
10789802 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4911 | RUBBER | Granulation | 10789802 - 15W MFit Insp GranSD Fert Syst | 10789802 | 0020 | Inspect Conveyor | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 08:00 |  | 43 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 08:00 | Rubber | 23SD2
10789802 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4911 | RUBBER | Granulation | 10789802 - 15W MFit Insp GranSD Fert Syst | 10789802 | 0030 | Close Permit - 10789802 - 15W MFit Insp GranSD Fert Syst | 0 | Task Dependent | 2023-07-13 08:00 | 2023-07-13 08:30 |  | 48.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 08:00 | 2023-07-13 08:30 | Gran Permit Issuer | 23SD2
10789813 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON1 | Granulation | 10789813 - 15W MFit Srv GranSD Rtry Dryr | 10789813 | 0010 | Issue Permit - 10789813 - 15W MFit Srv GranSD Rtry Dryr | 0 | Task Dependent | 2023-07-14 00:30 | 2023-07-14 01:00 |  | 25.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 00:30 | 2023-07-14 01:00 | Gran Permit Issuer | 23SD2
10789813 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON1 | Granulation | 10789813 - 15W MFit Srv GranSD Rtry Dryr | 10789813 | 0020 | Inspect Rotary Drum | 0 | Task Dependent | 2023-07-14 01:00 | 2023-07-14 11:00 |  | 25.5 | 8 | 8 | 16 | 16 | 0 |  |  | 2023-07-14 01:00 | 2023-07-14 11:00 | Fitter | 23SD2
10789813 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON1 | Granulation | 10789813 - 15W MFit Srv GranSD Rtry Dryr | 10789813 | 0030 | Close Permit - 10789813 - 15W MFit Srv GranSD Rtry Dryr | 0 | Task Dependent | 2023-07-14 11:00 | 2023-07-14 11:30 |  | 25.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 11:00 | 2023-07-14 11:30 | Gran Permit Issuer | 23SD2
10789885 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON2 | Phos Acid | 10789885 - 15W MFit Rplc PhosSD Mixer 44TK2503 | 10789885 | 0010 | Issue Permit - 10789885 - 15W MFit Rplc PhosSD Mixer 44TK2503 | 0 | Task Dependent | 2023-07-16 19:00 | 2023-07-16 19:30 |  | 6.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 19:00 | 2023-07-16 19:30 | Phos Permit Issuer | 23SD2
10789885 - 0050 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON2 | Phos Acid | 10789885 - 15W MFit Rplc PhosSD Mixer 44TK2503 | 10789885 | 0050 | Replace mixer spray | 0 | Task Dependent | 2023-07-16 19:30 | 2023-07-16 22:30 |  | 6.5 | 3 | 3 | 12 | 12 | 0 |  |  | 2023-07-16 19:30 | 2023-07-16 22:30 | 55t Crane, Rigger, Crane Operator, Fitter | 23SD2
10789885 - 0060 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON2 | Phos Acid | 10789885 - 15W MFit Rplc PhosSD Mixer 44TK2503 | 10789885 | 0060 | Close Permit - 10789885 - 15W MFit Rplc PhosSD Mixer 44TK2503 | 0 | Task Dependent | 2023-07-16 22:30 | 2023-07-16 23:00 |  | 6.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 22:30 | 2023-07-16 23:00 | Phos Permit Issuer | 23SD2
10789886 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON2 | Phos Acid | 10789886 - 15W MFit Rplc PhosSD Mixer 44TK2504 | 10789886 | 0010 | Issue Permit - 10789886 - 15W MFit Rplc PhosSD Mixer 44TK2504 | 0 | Task Dependent | 2023-07-16 22:30 | 2023-07-16 23:00 |  | 6.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 22:30 | 2023-07-16 23:00 | Phos Permit Issuer | 23SD2
10789886 - 0050 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON2 | Phos Acid | 10789886 - 15W MFit Rplc PhosSD Mixer 44TK2504 | 10789886 | 0050 | Replace mixer spray | 0 | Task Dependent | 2023-07-16 22:30 | 2023-07-17 01:30 |  | 6.5 | 3 | 3 | 12 | 12 | 0 |  |  | 2023-07-16 22:30 | 2023-07-17 01:30 | 55t Crane, Rigger, Crane Operator, Fitter | 23SD2
10789886 - 0060 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON2 | Phos Acid | 10789886 - 15W MFit Rplc PhosSD Mixer 44TK2504 | 10789886 | 0060 | Close Permit - 10789886 - 15W MFit Rplc PhosSD Mixer 44TK2504 | 0 | Task Dependent | 2023-07-17 01:30 | 2023-07-17 02:00 |  | 6.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-17 01:30 | 2023-07-17 02:00 | Phos Permit Issuer | 23SD2
10789887 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON2 | Phos Acid | 10789887 - 15W MFit Rplc PhosSD Mixer 44TK2506 | 10789887 | 0010 | Issue Permit - 10789887 - 15W MFit Rplc PhosSD Mixer 44TK2506 | 0 | Task Dependent | 2023-07-17 01:30 | 2023-07-17 02:00 |  | 6.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-17 01:30 | 2023-07-17 02:00 | Phos Permit Issuer | 23SD2
10789887 - 0050 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON2 | Phos Acid | 10789887 - 15W MFit Rplc PhosSD Mixer 44TK2506 | 10789887 | 0050 | Replace mixer spray | 0 | Task Dependent | 2023-07-17 01:30 | 2023-07-17 04:30 |  | 6.5 | 3 | 3 | 12 | 12 | 0 |  |  | 2023-07-17 01:30 | 2023-07-17 04:30 | 55t Crane, Rigger, Crane Operator, Fitter | 23SD2
10789887 - 0060 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON2 | Phos Acid | 10789887 - 15W MFit Rplc PhosSD Mixer 44TK2506 | 10789887 | 0060 | Close Permit - 10789887 - 15W MFit Rplc PhosSD Mixer 44TK2506 | 0 | Task Dependent | 2023-07-17 04:30 | 2023-07-17 05:00 |  | 6.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-17 04:30 | 2023-07-17 05:00 | Phos Permit Issuer | 23SD2
10789926 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4480 | ELEC | Phos Acid | 10789926 - 60W Elec INT Srv DrvLCU 44AR8001 | 10789926 | 0010 | Issue Permit - 10789926 - 60W Elec INT Srv DrvLCU 44AR8001 | 0 | Task Dependent | 2023-07-16 07:00 | 2023-07-16 07:30 |  | 9.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 07:00 | 2023-07-16 07:30 | Phos Permit Issuer | 23SD2
10789926 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4480 | ELEC | Phos Acid | 10789926 - 60W Elec INT Srv DrvLCU 44AR8001 | 10789926 | 0020 | Inspect/Service Drive Components | 0 | Task Dependent | 2023-07-16 07:30 | 2023-07-16 09:00 |  | 9.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-16 07:30 | 2023-07-16 09:00 | Projects Elec | 23SD2
10789926 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4480 | ELEC | Phos Acid | 10789926 - 60W Elec INT Srv DrvLCU 44AR8001 | 10789926 | 0030 | Close Permit - 10789926 - 60W Elec INT Srv DrvLCU 44AR8001 | 0 | Task Dependent | 2023-07-16 09:00 | 2023-07-16 09:30 |  | 9.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 09:00 | 2023-07-16 09:30 | Phos Permit Issuer | 23SD2
10790964 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4623 | DAWSON2 | Granulation | 10790964 - 60W MFit Srv GranSD Elev Lvl Sdry Elev | 10790964 | 0010 | Issue Permit - 10790964 - 60W MFit Srv GranSD Elev Lvl Sdry Elev | 0 | Task Dependent | 2023-07-13 04:30 | 2023-07-13 05:00 |  | 21 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 04:30 | 2023-07-13 05:00 | Gran Permit Issuer | 23SD2
10790964 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4623 | DAWSON2 | Granulation | 10790964 - 60W MFit Srv GranSD Elev Lvl Sdry Elev | 10790964 | 0020 | Inspect Elevator | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 21:00 |  | 21 | 12 | 12 | 24 | 24 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 21:00 | Fitter | 23SD2
10790964 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4623 | DAWSON2 | Granulation | 10790964 - 60W MFit Srv GranSD Elev Lvl Sdry Elev | 10790964 | 0030 | Close Permit - 10790964 - 60W MFit Srv GranSD Elev Lvl Sdry Elev | 0 | Task Dependent | 2023-07-13 21:00 | 2023-07-13 21:30 |  | 21 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 21:00 | 2023-07-13 21:30 | Gran Permit Issuer | 23SD2
10790966 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | LUBE | Granulation | 10790966 - 30W FLAC Srv GranSD Grp2 RGV Exh Fan | 10790966 | 0010 | Issue Permit - 10790966 - 30W FLAC Srv GranSD Grp2 RGV Exh Fan | 0 | Task Dependent | 2023-07-13 19:30 | 2023-07-13 20:00 |  | 29 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 19:30 | 2023-07-13 20:00 | Gran Permit Issuer | 23SD2
10790966 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4628 | LUBE | Granulation | 10790966 - 30W FLAC Srv GranSD Grp2 RGV Exh Fan | 10790966 | 0020 | Lubricate Fan | 0 | Task Dependent | 2023-07-13 20:00 | 2023-07-14 01:00 |  | 44 | 5 | 5 | 10 | 10 | 0 |  |  | 2023-07-13 20:00 | 2023-07-14 01:00 | T/A, Lube | 23SD2
10790966 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4628 | LUBE | Granulation | 10790966 - 30W FLAC Srv GranSD Grp2 RGV Exh Fan | 10790966 | 0040 | Close Permit - 10790966 - 30W FLAC Srv GranSD Grp2 RGV Exh Fan | 0 | Task Dependent | 2023-07-14 01:00 | 2023-07-14 01:30 |  | 44 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 01:00 | 2023-07-14 01:30 | Gran Permit Issuer | 23SD2
10791742 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4480 | LUBE | Phos Acid | 10791742 - LU-Replace oil in gearbox | 10791742 | 0010 | Issue Permit - 10791742 - LU-Replace oil in gearbox | 0 | Task Dependent | 2023-07-16 03:00 | 2023-07-16 03:30 |  | 25 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 03:00 | 2023-07-16 03:30 | Phos Permit Issuer | 23SD2
10791742 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4480 | LUBE | Phos Acid | 10791742 - LU-Replace oil in gearbox | 10791742 | 0020 | LU-Replace oil in gearbox | 0 | Task Dependent | 2023-07-16 03:30 | 2023-07-16 08:30 |  | 27 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-16 03:30 | 2023-07-16 08:30 | Lube | 23SD2
10791742 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4480 | LUBE | Phos Acid | 10791742 - LU-Replace oil in gearbox | 10791742 | 0030 | Close Permit - 10791742 - LU-Replace oil in gearbox | 0 | Task Dependent | 2023-07-16 08:30 | 2023-07-16 09:00 |  | 27 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 08:30 | 2023-07-16 09:00 | Phos Permit Issuer | 23SD2
10791744 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4460 | DAWSON3 | Phos Acid | 10791744 - FI-40% acid manifold valves V6 , V7, V11 | 10791744 | 0010 | Issue Permit - 10791744 - FI-40% acid manifold valves V6 , V7, V11 | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 07:30 |  | 56 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 07:30 | Phos Permit Issuer | 23SD2
10791744 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4460 | DAWSON3 | Phos Acid | 10791744 - FI-40% acid manifold valves V6 , V7, V11 | 10791744 | 0020 | Replace 3 Knife Gate Valves | 0 | Task Dependent | 2023-07-14 07:30 | 2023-07-14 15:30 |  | 56 | 8 | 8 | 32 | 32 | 0 |  |  | 2023-07-14 07:30 | 2023-07-14 15:30 | Crawler Crane, Rigger, Crane Operator, Fitter | 23SD2
10791744 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4460 | DAWSON3 | Phos Acid | 10791744 - FI-40% acid manifold valves V6 , V7, V11 | 10791744 | 0030 | E&ITech to assist | 0 | Task Dependent | 2023-07-14 12:30 | 2023-07-14 15:30 |  | 61 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-14 12:30 | 2023-07-14 15:30 | Elec 1 | 23SD2
10791744 - 0070 | Not Started | GLSTest-01.PHOS.MAINT.4460 | DAWSON3 | Phos Acid | 10791744 - FI-40% acid manifold valves V6 , V7, V11 | 10791744 | 0070 | Close Permit - 10791744 - FI-40% acid manifold valves V6 , V7, V11 | 0 | Task Dependent | 2023-07-14 15:30 | 2023-07-14 16:00 |  | 56 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 15:30 | 2023-07-14 16:00 | Phos Permit Issuer | 23SD2
10792004 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4420 | RUBBER | Phos Acid | 10792004 - 15W SEng Insp PhosSD 44CB2001 | 10792004 | 0010 | Issue Permit - 10792004 - 15W SEng Insp PhosSD 44CB2001 | 0 | Task Dependent | 2023-07-14 23:30 | 2023-07-15 |  | 46.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 23:30 | 2023-07-15 | Phos Permit Issuer | 23SD2
10792004 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4420 | RUBBER | Phos Acid | 10792004 - 15W SEng Insp PhosSD 44CB2001 | 10792004 | 0020 | Inspect rubber liner and sock | 0 | Task Dependent | 2023-07-15 | 2023-07-15 01:00 |  | 46.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-15 | 2023-07-15 01:00 | Static Engineer, Rubber | 23SD2
10792004 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4420 | RUBBER | Phos Acid | 10792004 - 15W SEng Insp PhosSD 44CB2001 | 10792004 | 0040 | Close Permit - 10792004 - 15W SEng Insp PhosSD 44CB2001 | 0 | Task Dependent | 2023-07-15 01:00 | 2023-07-15 01:30 |  | 49.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 01:00 | 2023-07-15 01:30 | Phos Permit Issuer | 23SD2
10792480 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4440 | DAWSON1 | Phos Acid | 10792480 - FI-Replace impeller-side shaft bearing | 10792480 | 0010 | Issue Permit - 10792480 - FI-Replace impeller-side shaft bearing | 0 | Task Dependent | 2023-07-16 08:30 | 2023-07-16 09:00 |  | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 08:30 | 2023-07-16 09:00 | Phos Permit Issuer | 23SD2
10792480 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4440 | DAWSON1 | Phos Acid | 10792480 - FI-Replace impeller-side shaft bearing | 10792480 | 0020 | FI-Replace impeller-side shaft bearing | 0 | Task Dependent | 2023-07-16 09:00 | 2023-07-16 17:00 |  | 4 | 8 | 8 | 16 | 16 | 0 |  |  | 2023-07-16 09:00 | 2023-07-16 17:00 | Fitter | 23SD2
10792480 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4440 | DAWSON1 | Phos Acid | 10792480 - FI-Replace impeller-side shaft bearing | 10792480 | 0030 | Close Permit - 10792480 - FI-Replace impeller-side shaft bearing | 0 | Task Dependent | 2023-07-16 19:00 | 2023-07-16 19:30 |  | 7.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 19:00 | 2023-07-16 19:30 | Phos Permit Issuer | 23SD2
10792484 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4485 | LUBE | Phos Acid | 10792484 - LU-Change out oil in gearbox | 10792484 | 0010 | Issue Permit - 10792484 - LU-Change out oil in gearbox | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 07:30 |  | 57 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 07:30 | Phos Permit Issuer | 23SD2
10792484 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4485 | LUBE | Phos Acid | 10792484 - LU-Change out oil in gearbox | 10792484 | 0020 | LU-Change out oil in gearbox | 0 | Task Dependent | 2023-07-14 07:30 | 2023-07-14 14:30 |  | 57 | 7 | 7 | 7 | 7 | 0 |  |  | 2023-07-14 07:30 | 2023-07-14 14:30 | Lube | 23SD2
10792484 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4485 | LUBE | Phos Acid | 10792484 - LU-Change out oil in gearbox | 10792484 | 0030 | Franna Team Assist | 0 | Task Dependent | 2023-07-14 07:30 | 2023-07-14 10:30 |  | 61 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-14 07:30 | 2023-07-14 10:30 | Franna, Rigger, Crane Operator | 23SD2
10792484 - 0060 | Not Started | GLSTest-01.PHOS.MAINT.4485 | LUBE | Phos Acid | 10792484 - LU-Change out oil in gearbox | 10792484 | 0060 | visually inspect gears | 0 | Task Dependent | 2023-07-14 14:30 | 2023-07-14 16:00 |  | 57 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-14 14:30 | 2023-07-14 16:00 | Rotating Engineer | 23SD2
10792484 - 0070 | Not Started | GLSTest-01.PHOS.MAINT.4485 | LUBE | Phos Acid | 10792484 - LU-Change out oil in gearbox | 10792484 | 0070 | Close Permit - 10792484 - LU-Change out oil in gearbox | 0 | Task Dependent | 2023-07-14 16:00 | 2023-07-14 16:30 |  | 57 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 16:00 | 2023-07-14 16:30 | Phos Permit Issuer | 23SD2
10793019 - 0010 | Not Started | GLSTest-01.PWR.MAINT.5442 | PWR | Power Station | 10793019 - 4Y Elec Ovhl PwrSD Trbn 4 Fuel Gas FCV | 10793019 | 0010 | Turbine Fuel Gas FCV 4Y Elec Overhaul | 0 | Task Dependent | 2023-07-14 09:30 | 2023-07-14 21:30 |  | 40 | 10 | 10 | 10 | 10 | 0 |  |  | 2023-07-14 09:30 | 2023-07-14 21:30 | Pwr Elec | 23SD2
10793809 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4445 | DAWSON3 | Phos Acid | 10793809 - FI-Pump bypass line blocked | 10793809 | 0010 | Repair Pump bypass line | 0 | Task Dependent | 2023-07-16 11:00 | 2023-07-16 17:00 |  | 9 | 6 | 6 | 12 | 12 | 0 |  |  | 2023-07-16 11:00 | 2023-07-16 17:00 | 45ft EWP, Fitter | 23SD2
10794280 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4440 | DAWSON1 | Phos Acid | 10794280 - 30W MFit Insp PhosSD 44FC4002 | 10794280 | 0010 | Issue Permit - 10794280 - 30W MFit Insp PhosSD 44FC4002 | 0 | Task Dependent | 2023-07-16 09:00 | 2023-07-16 09:30 |  | 13 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 09:00 | 2023-07-16 09:30 | Phos Permit Issuer | 23SD2
10794280 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4440 | DAWSON1 | Phos Acid | 10794280 - 30W MFit Insp PhosSD 44FC4002 | 10794280 | 0020 | Torque bearing caps and hold down bolts | 0 | Task Dependent | 2023-07-16 09:30 | 2023-07-16 11:30 |  | 13 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-16 09:30 | 2023-07-16 11:30 | Fitter | 23SD2
10794280 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4440 | DAWSON1 | Phos Acid | 10794280 - 30W MFit Insp PhosSD 44FC4002 | 10794280 | 0030 | Close Permit - 10794280 - 30W MFit Insp PhosSD 44FC4002 | 0 | Task Dependent | 2023-07-16 11:30 | 2023-07-16 12:00 |  | 13 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 11:30 | 2023-07-16 12:00 | Phos Permit Issuer | 23SD2
10794333 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4480 | ELEC | Phos Acid | 10794333 - 15W Elec INT Prog DrvInst 44CB8003 | 10794333 | 0010 | Inspect/Test Belt Instrumentation. | 0 | Task Dependent | 2023-07-15 09:30 | 2023-07-15 11:36 |  | 16.9 | 2.1 | 2.1 | 2.1 | 2.1 | 0 |  |  | 2023-07-15 09:30 | 2023-07-15 11:36 | Elec 4 | 23SD2
10794333 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4480 | ELEC | Phos Acid | 10794333 - 15W Elec INT Prog DrvInst 44CB8003 | 10794333 | 0020 | Issue Permit - 10794333 - 15W Elec INT Prog DrvInst 44CB8003 | 0 | Task Dependent | 2023-07-15 09:00 | 2023-07-15 09:30 |  | 16.9 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 09:00 | 2023-07-15 09:30 | Phos Permit Issuer | 23SD2
10794333 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4480 | ELEC | Phos Acid | 10794333 - 15W Elec INT Prog DrvInst 44CB8003 | 10794333 | 0030 | Close Permit - 10794333 - 15W Elec INT Prog DrvInst 44CB8003 | 0 | Task Dependent | 2023-07-15 11:36 | 2023-07-15 12:06 |  | 16.9 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 11:36 | 2023-07-15 12:06 | Phos Permit Issuer | 23SD2
10795393 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4480 | ELEC | Phos Acid | 10795393 - 60W Elec INT Srv DrvMtr 44AR8001 | 10795393 | 0010 | Issue Permit - 10795393 - 60W Elec INT Srv DrvMtr 44AR8001 | 0 | Task Dependent | 2023-07-16 07:00 | 2023-07-16 07:30 |  | 9 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 07:00 | 2023-07-16 07:30 | Phos Permit Issuer | 23SD2
10795393 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4480 | ELEC | Phos Acid | 10795393 - 60W Elec INT Srv DrvMtr 44AR8001 | 10795393 | 0020 | Inspect/Service Drive Components | 0 | Task Dependent | 2023-07-16 07:30 | 2023-07-16 09:30 |  | 9 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-16 07:30 | 2023-07-16 09:30 | Projects Elec | 23SD2
10795393 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4480 | ELEC | Phos Acid | 10795393 - 60W Elec INT Srv DrvMtr 44AR8001 | 10795393 | 0030 | Close Permit - 10795393 - 60W Elec INT Srv DrvMtr 44AR8001 | 0 | Task Dependent | 2023-07-16 09:30 | 2023-07-16 10:00 |  | 9 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 09:30 | 2023-07-16 10:00 | Phos Permit Issuer | 23SD2
10796135 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4420 | RUBBER | Phos Acid | 10796135 - RW-Replace broken roller #13 | 10796135 | 0010 | Replace damaged roller #13 | 0 | Task Dependent | 2023-07-15 01:00 | 2023-07-15 04:00 |  | 46.5 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-15 01:00 | 2023-07-15 04:00 | Rubber | 23SD2
10796254 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10796254 - Replace electrical box door and hinges | 10796254 | 0010 | Replace electrical box door and hinges | 0 | Task Dependent | 2023-07-14 19:30 | 2023-07-16 01:30 |  | 13 | 16 | 16 | 32 | 32 | 0 |  |  | 2023-07-14 19:30 | 2023-07-16 01:30 | Elec 3 | 23SD2
10796451 - 0010 | Not Started | GLSTest-01.PWR.MAINT.5412 | PWR | Power Station | 10796451 - 18M MFit Rplc PwrSD GT 1 Air Filter | 10796451 | 0010 | PHMPS GT Air Filter 18M Mech Replace | 0 | Task Dependent | 2023-07-16 10:30 | 2023-07-16 12:30 |  | 40 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-16 10:30 | 2023-07-16 12:30 | 45ft EWP, Pwr Fitter | 23SD2
10796533 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4430 | ELEC | Phos Acid | 10796533 - 60W Elec INT Srv DrvLCU 44AR3001 | 10796533 | 0010 | Issue Permit - 10796533 - 60W Elec INT Srv DrvLCU 44AR3001 | 0 | Task Dependent | 2023-07-15 19:00 | 2023-07-15 19:30 |  | 17.1 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 19:00 | 2023-07-15 19:30 | Phos Permit Issuer | 23SD2
10796533 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4430 | ELEC | Phos Acid | 10796533 - 60W Elec INT Srv DrvLCU 44AR3001 | 10796533 | 0020 | Inspect/Service Drive Components | 0 | Task Dependent | 2023-07-15 19:30 | 2023-07-15 21:24 |  | 17.1 | 1.9 | 1.9 | 1.9 | 1.9 | 0 |  |  | 2023-07-15 19:30 | 2023-07-15 21:24 | Elec 2 | 23SD2
10796533 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4430 | ELEC | Phos Acid | 10796533 - 60W Elec INT Srv DrvLCU 44AR3001 | 10796533 | 0030 | Close Permit - 10796533 - 60W Elec INT Srv DrvLCU 44AR3001 | 0 | Task Dependent | 2023-07-15 21:24 | 2023-07-15 21:54 |  | 17.1 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 21:24 | 2023-07-15 21:54 | Phos Permit Issuer | 23SD2
10796623 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4625 | ENG | Granulation | 10796623 - 210W SEng Insp DvrtrGts GranSD 46HE2501 | 10796623 | 0010 | Issue Permit - 10796623 - 210W SEng Insp DvrtrGts GranSD 46HE2501 | 0 | Task Dependent | 2023-07-13 | 2023-07-13 00:30 |  | 53 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 | 2023-07-13 00:30 | Gran Permit Issuer | 23SD2
10796623 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4625 | ENG | Granulation | 10796623 - 210W SEng Insp DvrtrGts GranSD 46HE2501 | 10796623 | 0020 | Inspect diverter | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 01:30 |  | 53 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 01:30 | T/A, Static Engineer | 23SD2
10796623 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4625 | ENG | Granulation | 10796623 - 210W SEng Insp DvrtrGts GranSD 46HE2501 | 10796623 | 0040 | Close Permit - 10796623 - 210W SEng Insp DvrtrGts GranSD 46HE2501 | 0 | Task Dependent | 2023-07-13 01:30 | 2023-07-13 02:00 |  | 53 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 01:30 | 2023-07-13 02:00 | Gran Permit Issuer | 23SD2
10796624 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4625 | GRAN | Granulation | 10796624 - 15W Prod Insp GranSD HE2501 | 10796624 | 0010 | Test Fan Damper | 0 | Task Dependent | 2023-07-13 21:30 | 2023-07-13 22:30 |  | 36 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-13 21:30 | 2023-07-13 22:30 | Gran Ops | 23SD2
10796625 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4625 | GRAN | Granulation | 10796625 - 15W Prod Prog GranSD FC2501 | 10796625 | 0010 | Issue Permit - 10796625 - 15W Prod Prog GranSD FC2501 | 0 | Task Dependent | 2023-07-13 19:00 | 2023-07-13 19:30 |  | 33.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 19:00 | 2023-07-13 19:30 | Gran Permit Issuer | 23SD2
10796625 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4625 | GRAN | Granulation | 10796625 - 15W Prod Prog GranSD FC2501 | 10796625 | 0020 | Test Fan Damper | 0 | Task Dependent | 2023-07-13 19:30 | 2023-07-13 20:30 |  | 33.5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-13 19:30 | 2023-07-13 20:30 | Gran Ops | 23SD2
10796625 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4625 | GRAN | Granulation | 10796625 - 15W Prod Prog GranSD FC2501 | 10796625 | 0030 | Close Permit - 10796625 - 15W Prod Prog GranSD FC2501 | 0 | Task Dependent | 2023-07-13 20:30 | 2023-07-13 21:00 |  | 33.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 20:30 | 2023-07-13 21:00 | Gran Permit Issuer | 23SD2
10796629 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4625 | LUBE | Granulation | 10796629 - 30W FLAC Lube GranSD FC2501 | 10796629 | 0010 | Issue Permit - 10796629 - 30W FLAC Lube GranSD FC2501 | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 07:30 |  | 34 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 07:30 | Gran Permit Issuer | 23SD2
10796629 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4625 | LUBE | Granulation | 10796629 - 30W FLAC Lube GranSD FC2501 | 10796629 | 0020 | Grease Bearings | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 12:30 |  | 38.5 | 5 | 5 | 10 | 10 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 12:30 | T/A, Lube | 23SD2
10796629 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4625 | LUBE | Granulation | 10796629 - 30W FLAC Lube GranSD FC2501 | 10796629 | 0040 | Lubricate Fan | 0 | Task Dependent | 2023-07-13 12:30 | 2023-07-13 20:00 |  | 38.5 | 5.5 | 5.5 | 5.5 | 5.5 | 0 |  |  | 2023-07-13 12:30 | 2023-07-13 20:00 | Lube | 23SD2
10796629 - 0050 | Not Started | GLSTest-01.GRAN.MAINT.4625 | LUBE | Granulation | 10796629 - 30W FLAC Lube GranSD FC2501 | 10796629 | 0050 | Close Permit - 10796629 - 30W FLAC Lube GranSD FC2501 | 0 | Task Dependent | 2023-07-13 20:00 | 2023-07-13 20:30 |  | 38.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 20:00 | 2023-07-13 20:30 | Gran Permit Issuer | 23SD2
10796640 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4625 | ELEC | Granulation | 10796640 - 60W Elec INT Rplc DrvCntrl FC2501 | 10796640 | 0010 | Issue Permit - 10796640 - 60W Elec INT Rplc DrvCntrl FC2501 | 0 | Task Dependent | 2023-07-13 02:30 | 2023-07-13 03:00 |  | 20.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 02:30 | 2023-07-13 03:00 | Gran Permit Issuer | 23SD2
10796640 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4625 | ELEC | Granulation | 10796640 - 60W Elec INT Rplc DrvCntrl FC2501 | 10796640 | 0020 | Inspect/Service Variable Speed Drive | 0 | Task Dependent | 2023-07-13 03:00 | 2023-07-13 04:00 |  | 22.5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-13 03:00 | 2023-07-13 04:00 | Elec 2 | 23SD2
10796640 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4625 | ELEC | Granulation | 10796640 - 60W Elec INT Rplc DrvCntrl FC2501 | 10796640 | 0030 | Close Permit - 10796640 - 60W Elec INT Rplc DrvCntrl FC2501 | 0 | Task Dependent | 2023-07-13 04:00 | 2023-07-13 04:30 |  | 22.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 04:00 | 2023-07-13 04:30 | Gran Permit Issuer | 23SD2
10796642 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4625 | ELEC | Granulation | 10796642 - 60W Elec CAL Prog Temp FC2501 | 10796642 | 0010 | Issue Permit - 10796642 - 60W Elec CAL Prog Temp FC2501 | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 01:00 |  | 20 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 01:00 | Gran Permit Issuer | 23SD2
10796642 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4625 | ELEC | Granulation | 10796642 - 60W Elec CAL Prog Temp FC2501 | 10796642 | 0020 | Inspect/Service Temperature Instruments | 0 | Task Dependent | 2023-07-13 01:00 | 2023-07-13 04:30 |  | 20 | 3.5 | 3.5 | 3.5 | 3.5 | 0 |  |  | 2023-07-13 01:00 | 2023-07-13 04:30 | Elec 2 | 23SD2
10796642 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4625 | ELEC | Granulation | 10796642 - 60W Elec CAL Prog Temp FC2501 | 10796642 | 0030 | Close Permit - 10796642 - 60W Elec CAL Prog Temp FC2501 | 0 | Task Dependent | 2023-07-13 04:30 | 2023-07-13 05:00 |  | 20 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 04:30 | 2023-07-13 05:00 | Gran Permit Issuer | 23SD2
10796646 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4626 | GRAN | Granulation | 10796646 - 15W Prod Insp Screen GranSD PlshngCtng | 10796646 | 0010 | Issue Permit - 10796646 - 15W Prod Insp Screen GranSD PlshngCtng | 0 | Task Dependent | 2023-07-14 01:00 | 2023-07-14 01:30 |  | 29 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 01:00 | 2023-07-14 01:30 | Gran Permit Issuer | 23SD2
10796646 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4626 | GRAN | Granulation | 10796646 - 15W Prod Insp Screen GranSD PlshngCtng | 10796646 | 0020 | Inspect Screen | 0 | Task Dependent | 2023-07-14 01:30 | 2023-07-14 03:30 |  | 29 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-14 01:30 | 2023-07-14 03:30 | Gran Ops | 23SD2
10796646 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4626 | GRAN | Granulation | 10796646 - 15W Prod Insp Screen GranSD PlshngCtng | 10796646 | 0030 | Close Permit - 10796646 - 15W Prod Insp Screen GranSD PlshngCtng | 0 | Task Dependent | 2023-07-14 03:30 | 2023-07-14 04:00 |  | 29 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 03:30 | 2023-07-14 04:00 | Gran Permit Issuer | 23SD2
10796670 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4625 | DAWSON2 | Granulation | 10796670 - 30W MFit Insp GranSD CC2501 | 10796670 | 0010 | Issue Permit - 10796670 - 30W MFit Insp GranSD CC2501 | 0 | Task Dependent | 2023-07-13 | 2023-07-13 00:30 |  | 21 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 | 2023-07-13 00:30 | Gran Permit Issuer | 23SD2
10796670 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4625 | DAWSON2 | Granulation | 10796670 - 30W MFit Insp GranSD CC2501 | 10796670 | 0020 | Inspect Elevator | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 01:30 |  | 21 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 01:30 | Fitter | 23SD2
10796670 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4625 | DAWSON2 | Granulation | 10796670 - 30W MFit Insp GranSD CC2501 | 10796670 | 0030 | Close Permit - 10796670 - 30W MFit Insp GranSD CC2501 | 0 | Task Dependent | 2023-07-13 01:30 | 2023-07-13 02:00 |  | 21 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 01:30 | 2023-07-13 02:00 | Gran Permit Issuer | 23SD2
10796671 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4625 | ENG | Granulation | 10796671 - 210W REng Insp GndFlrFan GranSD ProdClng | 10796671 | 0010 | Issue Permit - 10796671 - 210W REng Insp GndFlrFan GranSD ProdClng | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 01:00 |  | 47 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 01:00 | Gran Permit Issuer | 23SD2
10796671 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4625 | ENG | Granulation | 10796671 - 210W REng Insp GndFlrFan GranSD ProdClng | 10796671 | 0020 | Inspect Fan | 0 | Task Dependent | 2023-07-13 01:30 | 2023-07-13 02:30 |  | 47 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-13 01:30 | 2023-07-13 02:30 | Rotating Engineer | 23SD2
10796671 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4625 | ENG | Granulation | 10796671 - 210W REng Insp GndFlrFan GranSD ProdClng | 10796671 | 0030 | Reinstate hatches | 0 | Task Dependent | 2023-07-14 14:30 | 2023-07-14 15:00 |  | 17 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-14 14:30 | 2023-07-14 15:00 | Fitter | 23SD2
10796671 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4625 | ENG | Granulation | 10796671 - 210W REng Insp GndFlrFan GranSD ProdClng | 10796671 | 0040 | Close Permit - 10796671 - 210W REng Insp GndFlrFan GranSD ProdClng | 0 | Task Dependent | 2023-07-14 15:00 | 2023-07-14 15:30 |  | 17 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 15:00 | 2023-07-14 15:30 | Gran Permit Issuer | 23SD2
10796672 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4623 | RUBBER | Granulation | 10796672 - 15W MFit Insp GranSD CB2401 | 10796672 | 0010 | Issue Permit - 10796672 - 15W MFit Insp GranSD CB2401 | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 08:00 |  | 43 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 08:00 | Gran Permit Issuer | 23SD2
10796672 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4623 | RUBBER | Granulation | 10796672 - 15W MFit Insp GranSD CB2401 | 10796672 | 0020 | Inspect Conveyor | 0 | Task Dependent | 2023-07-13 08:00 | 2023-07-13 09:30 |  | 43 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-13 08:00 | 2023-07-13 09:30 | Rubber | 23SD2
10796672 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4623 | RUBBER | Granulation | 10796672 - 15W MFit Insp GranSD CB2401 | 10796672 | 0030 | Close Permit - 10796672 - 15W MFit Insp GranSD CB2401 | 0 | Task Dependent | 2023-07-13 09:30 | 2023-07-13 10:00 |  | 47 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 09:30 | 2023-07-13 10:00 | Gran Permit Issuer | 23SD2
10796698 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10796698 - 60W Elec INT Prog DrvInst CB2401 | 10796698 | 0010 | Issue Permit - 10796698 - 60W Elec INT Prog DrvInst CB2401 | 0 | Task Dependent | 2023-07-13 20:00 | 2023-07-13 20:30 |  | 15 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 20:00 | 2023-07-13 20:30 | Gran Permit Issuer | 23SD2
10796698 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10796698 - 60W Elec INT Prog DrvInst CB2401 | 10796698 | 0020 | Inspect/Test Belt Instrumentation. | 0 | Task Dependent | 2023-07-13 20:30 | 2023-07-13 23:30 |  | 21 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-13 20:30 | 2023-07-13 23:30 | Elec 3 | 23SD2
10796698 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10796698 - 60W Elec INT Prog DrvInst CB2401 | 10796698 | 0030 | Close Permit - 10796698 - 60W Elec INT Prog DrvInst CB2401 | 0 | Task Dependent | 2023-07-13 23:30 | 2023-07-14 |  | 21 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 23:30 | 2023-07-14 | Gran Permit Issuer | 23SD2
10796709 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10796709 - 60W Elec INT Srv DrvMtr CB2401 | 10796709 | 0010 | Issue Permit - 10796709 - 60W Elec INT Srv DrvMtr CB2401 | 0 | Task Dependent | 2023-07-13 01:30 | 2023-07-13 02:00 |  | 19.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 01:30 | 2023-07-13 02:00 | Gran Permit Issuer | 23SD2
10796709 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10796709 - 60W Elec INT Srv DrvMtr CB2401 | 10796709 | 0020 | Inspect/Service Drive Components | 0 | Task Dependent | 2023-07-13 02:00 | 2023-07-13 05:00 |  | 21 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-13 02:00 | 2023-07-13 05:00 | Elec 3 | 23SD2
10796709 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10796709 - 60W Elec INT Srv DrvMtr CB2401 | 10796709 | 0030 | Close Permit - 10796709 - 60W Elec INT Srv DrvMtr CB2401 | 0 | Task Dependent | 2023-07-13 19:00 | 2023-07-13 19:30 |  | 21 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 19:00 | 2023-07-13 19:30 | Gran Permit Issuer | 23SD2
10796711 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4625 | DAWSON1 | Granulation | 10796711 - 30W MFit Insp ClrFn GranSD ProdClng | 10796711 | 0010 | Issue Permit - 10796711 - 30W MFit Insp ClrFn GranSD ProdClng | 0 | Task Dependent | 2023-07-14 01:30 | 2023-07-14 02:00 |  | 32 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 01:30 | 2023-07-14 02:00 | Gran Permit Issuer | 23SD2
10796711 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4625 | DAWSON1 | Granulation | 10796711 - 30W MFit Insp ClrFn GranSD ProdClng | 10796711 | 0020 | Adjust Fan | 0 | Task Dependent | 2023-07-14 02:00 | 2023-07-14 02:30 |  | 32 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 02:00 | 2023-07-14 02:30 | Fitter | 23SD2
10796711 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4625 | DAWSON1 | Granulation | 10796711 - 30W MFit Insp ClrFn GranSD ProdClng | 10796711 | 0030 | Close Permit - 10796711 - 30W MFit Insp ClrFn GranSD ProdClng | 0 | Task Dependent | 2023-07-14 02:30 | 2023-07-14 03:00 |  | 32 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 02:30 | 2023-07-14 03:00 | Gran Permit Issuer | 23SD2
10796716 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4623 | DAWSON3 | Granulation | 10796716 - 104W MFit Insp BckStp GranSD CB2601 | 10796716 | 0010 | Issue Permit - 10796716 - 104W MFit Insp BckStp GranSD CB2601 | 0 | Task Dependent | 2023-07-13 12:30 | 2023-07-13 13:00 |  | 27.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 12:30 | 2023-07-13 13:00 | Gran Permit Issuer | 23SD2
10796716 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4623 | DAWSON3 | Granulation | 10796716 - 104W MFit Insp BckStp GranSD CB2601 | 10796716 | 0020 | Remove guards | 0 | Task Dependent | 2023-07-13 13:00 | 2023-07-13 15:00 |  | 27.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-13 13:00 | 2023-07-13 15:00 | Fitter | 23SD2
10796716 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4623 | DAWSON3 | Granulation | 10796716 - 104W MFit Insp BckStp GranSD CB2601 | 10796716 | 0030 | Test backstop function | 0 | Task Dependent | 2023-07-13 15:00 | 2023-07-13 17:00 |  | 27.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-13 15:00 | 2023-07-13 17:00 | Fitter | 23SD2
10796716 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4623 | DAWSON3 | Granulation | 10796716 - 104W MFit Insp BckStp GranSD CB2601 | 10796716 | 0040 | Reinstall guards | 0 | Task Dependent | 2023-07-13 19:00 | 2023-07-13 21:00 |  | 27.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-13 19:00 | 2023-07-13 21:00 | Fitter | 23SD2
10796716 - 0050 | Not Started | GLSTest-01.GRAN.MAINT.4623 | DAWSON3 | Granulation | 10796716 - 104W MFit Insp BckStp GranSD CB2601 | 10796716 | 0050 | Close Permit - 10796716 - 104W MFit Insp BckStp GranSD CB2601 | 0 | Task Dependent | 2023-07-13 21:00 | 2023-07-13 21:30 |  | 27.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 21:00 | 2023-07-13 21:30 | Gran Permit Issuer | 23SD2
10797082 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4420 | DAWSON3 | Phos Acid | 10797082 - Floc water dilution valve u/s | 10797082 | 0005 | Issue Permit - 10797082 - Floc water dilution valve u/s | 0 | Task Dependent | 2023-07-15 19:00 | 2023-07-15 19:30 |  | 29.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 19:00 | 2023-07-15 19:30 | Phos Permit Issuer | 23SD2
10797082 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4420 | DAWSON3 | Phos Acid | 10797082 - Floc water dilution valve u/s | 10797082 | 0010 | Floc water dilution valve u/s | 0 | Task Dependent | 2023-07-15 19:30 | 2023-07-15 23:30 |  | 29.5 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-15 19:30 | 2023-07-15 23:30 | Fitter | 23SD2
10797082 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4420 | DAWSON3 | Phos Acid | 10797082 - Floc water dilution valve u/s | 10797082 | 0030 | Close Permit - 10797082 - Floc water dilution valve u/s | 0 | Task Dependent | 2023-07-15 23:30 | 2023-07-16 |  | 29.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 23:30 | 2023-07-16 | Phos Permit Issuer | 23SD2
10797806 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10797806 - 90W Elec INT Srv DrvCell 44AR1201 | 10797806 | 0010 | Issue Permit - 10797806 - 90W Elec INT Srv DrvCell 44AR1201 | 0 | Task Dependent | 2023-07-14 19:00 | 2023-07-14 19:30 |  | 26.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 19:00 | 2023-07-14 19:30 | Phos Permit Issuer | 23SD2
10797806 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10797806 - 90W Elec INT Srv DrvCell 44AR1201 | 10797806 | 0020 | Inspect/Service Drive Components | 0 | Task Dependent | 2023-07-14 19:30 | 2023-07-14 22:00 |  | 26.5 | 2.5 | 2.5 | 2.5 | 2.5 | 0 |  |  | 2023-07-14 19:30 | 2023-07-14 22:00 | Elec 2 | 23SD2
10797806 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10797806 - 90W Elec INT Srv DrvCell 44AR1201 | 10797806 | 0030 | Close Permit - 10797806 - 90W Elec INT Srv DrvCell 44AR1201 | 0 | Task Dependent | 2023-07-14 22:00 | 2023-07-14 22:30 |  | 26.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 22:00 | 2023-07-14 22:30 | Phos Permit Issuer | 23SD2
10797850 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4625 | ENG | Granulation | 10797850 - 60W REng Insp GranSD CC2501 | 10797850 | 0010 | Issue Permit - 10797850 - 60W REng Insp GranSD CC2501 | 0 | Task Dependent | 2023-07-13 09:00 | 2023-07-13 09:30 |  | 46 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 09:00 | 2023-07-13 09:30 | Gran Permit Issuer | 23SD2
10797850 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4625 | ENG | Granulation | 10797850 - 60W REng Insp GranSD CC2501 | 10797850 | 0020 | Inspect bucket elevator | 0 | Task Dependent | 2023-07-13 09:30 | 2023-07-13 10:30 |  | 46 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-13 09:30 | 2023-07-13 10:30 | Rotating Engineer | 23SD2
10797850 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4625 | ENG | Granulation | 10797850 - 60W REng Insp GranSD CC2501 | 10797850 | 0030 | Assist bucket elevator inspection | 0 | Task Dependent | 2023-07-13 09:30 | 2023-07-13 10:00 |  | 46.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 09:30 | 2023-07-13 10:00 | Fitter | 23SD2
10797850 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4625 | ENG | Granulation | 10797850 - 60W REng Insp GranSD CC2501 | 10797850 | 0040 | Close Permit - 10797850 - 60W REng Insp GranSD CC2501 | 0 | Task Dependent | 2023-07-13 10:30 | 2023-07-13 11:00 |  | 46 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 10:30 | 2023-07-13 11:00 | Gran Permit Issuer | 23SD2
10797853 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10797853 - 15W Elec OLL Stat Lnyd CB2601 | 10797853 | 0010 | Issue Permit - 10797853 - 15W Elec OLL Stat Lnyd CB2601 | 0 | Task Dependent | 2023-07-13 | 2023-07-13 00:30 |  | 22.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 | 2023-07-13 00:30 | Gran Permit Issuer | 23SD2
10797853 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10797853 - 15W Elec OLL Stat Lnyd CB2601 | 10797853 | 0020 | Inspect/Test Belt Instrumentation. | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 02:00 |  | 22.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 02:00 | Elec 3 | 23SD2
10797853 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10797853 - 15W Elec OLL Stat Lnyd CB2601 | 10797853 | 0030 | Close Permit - 10797853 - 15W Elec OLL Stat Lnyd CB2601 | 0 | Task Dependent | 2023-07-13 02:00 | 2023-07-13 02:30 |  | 22.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 02:00 | 2023-07-13 02:30 | Gran Permit Issuer | 23SD2
10797854 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10797854 - 15W Elec OLL Stat Lnyd FV2601 | 10797854 | 0010 | Issue Permit - 10797854 - 15W Elec OLL Stat Lnyd FV2601 | 0 | Task Dependent | 2023-07-13 | 2023-07-13 00:30 |  | 22.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 | 2023-07-13 00:30 | Gran Permit Issuer | 23SD2
10797854 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10797854 - 15W Elec OLL Stat Lnyd FV2601 | 10797854 | 0020 | Inspect/Test Belt Instrumentation. | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 02:00 |  | 22.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 02:00 | Elec 3 | 23SD2
10797854 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10797854 - 15W Elec OLL Stat Lnyd FV2601 | 10797854 | 0030 | Close Permit - 10797854 - 15W Elec OLL Stat Lnyd FV2601 | 0 | Task Dependent | 2023-07-13 02:00 | 2023-07-13 02:30 |  | 22.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 02:00 | 2023-07-13 02:30 | Gran Permit Issuer | 23SD2
10797855 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10797855 - 15W Elec OLL Stat Lnyd CB2401 | 10797855 | 0010 | Issue Permit - 10797855 - 15W Elec OLL Stat Lnyd CB2401 | 0 | Task Dependent | 2023-07-13 01:30 | 2023-07-13 02:00 |  | 21 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 01:30 | 2023-07-13 02:00 | Gran Permit Issuer | 23SD2
10797855 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10797855 - 15W Elec OLL Stat Lnyd CB2401 | 10797855 | 0020 | Inspect/Test Belt Instrumentation. | 0 | Task Dependent | 2023-07-13 02:00 | 2023-07-13 03:30 |  | 22.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-13 02:00 | 2023-07-13 03:30 | Elec 3 | 23SD2
10797855 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10797855 - 15W Elec OLL Stat Lnyd CB2401 | 10797855 | 0030 | Close Permit - 10797855 - 15W Elec OLL Stat Lnyd CB2401 | 0 | Task Dependent | 2023-07-13 03:30 | 2023-07-13 04:00 |  | 22.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 03:30 | 2023-07-13 04:00 | Gran Permit Issuer | 23SD2
10797856 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ENG | Granulation | 10797856 - 60W REng Insp GranSD CC2401 | 10797856 | 0010 | Issue Permit - 10797856 - 60W REng Insp GranSD CC2401 | 0 | Task Dependent | 2023-07-13 | 2023-07-13 00:30 |  | 53 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 | 2023-07-13 00:30 | Gran Permit Issuer | 23SD2
10797856 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ENG | Granulation | 10797856 - 60W REng Insp GranSD CC2401 | 10797856 | 0020 | Inspect bucket elevator | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 01:30 |  | 53 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 01:30 | Rotating Engineer | 23SD2
10797856 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ENG | Granulation | 10797856 - 60W REng Insp GranSD CC2401 | 10797856 | 0030 | Close Permit - 10797856 - 60W REng Insp GranSD CC2401 | 0 | Task Dependent | 2023-07-13 01:30 | 2023-07-13 02:00 |  | 53 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 01:30 | 2023-07-13 02:00 | Gran Permit Issuer | 23SD2
10797857 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10797857 - 15W Elec OLL Prog Wghr 46WIT26002 | 10797857 | 0010 | Issue Permit - 10797857 - 15W Elec OLL Prog Wghr 46WIT26002 | 0 | Task Dependent | 2023-07-13 04:30 | 2023-07-13 05:00 |  | 17 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 04:30 | 2023-07-13 05:00 | Gran Permit Issuer | 23SD2
10797857 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10797857 - 15W Elec OLL Prog Wghr 46WIT26002 | 10797857 | 0020 | Inspect/Service Belt Weigher | 0 | Task Dependent | 2023-07-13 19:00 | 2023-07-13 21:30 |  | 21.5 | 2.5 | 2.5 | 2.5 | 2.5 | 0 |  |  | 2023-07-13 19:00 | 2023-07-13 21:30 | Elec 3 | 23SD2
10797857 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10797857 - 15W Elec OLL Prog Wghr 46WIT26002 | 10797857 | 0030 | Close Permit - 10797857 - 15W Elec OLL Prog Wghr 46WIT26002 | 0 | Task Dependent | 2023-07-13 21:30 | 2023-07-13 22:00 |  | 21.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 21:30 | 2023-07-13 22:00 | Gran Permit Issuer | 23SD2
10797858 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10797858 - 15W Elec INT Prog Wghr 46WIT26002 | 10797858 | 0010 | Issue Permit - 10797858 - 15W Elec INT Prog Wghr 46WIT26002 | 0 | Task Dependent | 2023-07-13 19:30 | 2023-07-13 20:00 |  | 18 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 19:30 | 2023-07-13 20:00 | Gran Permit Issuer | 23SD2
10797858 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10797858 - 15W Elec INT Prog Wghr 46WIT26002 | 10797858 | 0020 | Inspect/Service Belt Weigher | 0 | Task Dependent | 2023-07-13 20:00 | 2023-07-13 20:30 |  | 23.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 20:00 | 2023-07-13 20:30 | Elec 3 | 23SD2
10797858 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10797858 - 15W Elec INT Prog Wghr 46WIT26002 | 10797858 | 0030 | Close Permit - 10797858 - 15W Elec INT Prog Wghr 46WIT26002 | 0 | Task Dependent | 2023-07-13 20:30 | 2023-07-13 21:00 |  | 23.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 20:30 | 2023-07-13 21:00 | Gran Permit Issuer | 23SD2
10797859 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10797859 - 15W Elec OLL Rplc Wghr 46WIT24001 | 10797859 | 0010 | Issue Permit - 10797859 - 15W Elec OLL Rplc Wghr 46WIT24001 | 0 | Task Dependent | 2023-07-13 03:00 | 2023-07-13 03:30 |  | 18.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 03:00 | 2023-07-13 03:30 | Gran Permit Issuer | 23SD2
10797859 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10797859 - 15W Elec OLL Rplc Wghr 46WIT24001 | 10797859 | 0020 | Inspect/Service Belt Weigher | 0 | Task Dependent | 2023-07-13 03:30 | 2023-07-13 20:00 |  | 21.5 | 2.5 | 2.5 | 2.5 | 2.5 | 0 |  |  | 2023-07-13 03:30 | 2023-07-13 20:00 | Elec 3 | 23SD2
10797859 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10797859 - 15W Elec OLL Rplc Wghr 46WIT24001 | 10797859 | 0030 | Close Permit - 10797859 - 15W Elec OLL Rplc Wghr 46WIT24001 | 0 | Task Dependent | 2023-07-13 20:00 | 2023-07-13 20:30 |  | 21.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 20:00 | 2023-07-13 20:30 | Gran Permit Issuer | 23SD2
10797870 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4621 | ENG | Granulation | 10797870 - 60W MFit Insp PN TkAgtr GranSD Rctn | 10797870 | 0010 | Issue Permit - 10797870 - 60W MFit Insp PN TkAgtr GranSD Rctn | 0 | Task Dependent | 2023-07-14 12:00 | 2023-07-14 12:30 |  | 17 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 12:00 | 2023-07-14 12:30 | Gran Permit Issuer | 23SD2
10797870 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4621 | ENG | Granulation | 10797870 - 60W MFit Insp PN TkAgtr GranSD Rctn | 10797870 | 0020 | Inspect Agitator (CSE) | 0 | Task Dependent | 2023-07-14 12:30 | 2023-07-14 14:00 |  | 17 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-14 12:30 | 2023-07-14 14:00 | Static Engineer | 23SD2
10797870 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4621 | ENG | Granulation | 10797870 - 60W MFit Insp PN TkAgtr GranSD Rctn | 10797870 | 0030 | Inspect Agitator (CSE) | 0 | Task Dependent | 2023-07-14 12:30 | 2023-07-14 15:00 |  | 17 | 2.5 | 2.5 | 5 | 5 | 0 |  |  | 2023-07-14 12:30 | 2023-07-14 15:00 | Fitter | 23SD2
10797870 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4621 | ENG | Granulation | 10797870 - 60W MFit Insp PN TkAgtr GranSD Rctn | 10797870 | 0040 | Close Permit - 10797870 - 60W MFit Insp PN TkAgtr GranSD Rctn | 0 | Task Dependent | 2023-07-14 15:00 | 2023-07-14 15:30 |  | 17 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 15:00 | 2023-07-14 15:30 | Gran Permit Issuer | 23SD2
10797880 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4621 | ELEC | Granulation | 10797880 - 120W Elec SIS Prog DPLvl 46LIT21003 | 10797880 | 0010 | Issue Permit - 10797880 - 120W Elec SIS Prog DPLvl 46LIT21003 | 0 | Task Dependent | 2023-07-14 10:00 | 2023-07-14 10:30 |  | 14.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 10:00 | 2023-07-14 10:30 | Gran Permit Issuer | 23SD2
10797880 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4621 | ELEC | Granulation | 10797880 - 120W Elec SIS Prog DPLvl 46LIT21003 | 10797880 | 0020 | Inspect/Service DP Level | 0 | Task Dependent | 2023-07-14 10:30 | 2023-07-14 11:30 |  | 27.5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-14 10:30 | 2023-07-14 11:30 | Elec 3 | 23SD2
10797880 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4621 | ELEC | Granulation | 10797880 - 120W Elec SIS Prog DPLvl 46LIT21003 | 10797880 | 0030 | Close Permit - 10797880 - 120W Elec SIS Prog DPLvl 46LIT21003 | 0 | Task Dependent | 2023-07-14 11:30 | 2023-07-14 12:00 |  | 27.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 11:30 | 2023-07-14 12:00 | Gran Permit Issuer | 23SD2
10797882 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4621 | ELEC | Granulation | 10797882 - 120W Elec OLL Prog XVlv PC2101 | 10797882 | 0010 | Issue Permit - 10797882 - 120W Elec OLL Prog XVlv PC2101 | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 07:30 |  | 21.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 07:30 | Gran Permit Issuer | 23SD2
10797882 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4621 | ELEC | Granulation | 10797882 - 120W Elec OLL Prog XVlv PC2101 | 10797882 | 0020 | Inspect/Service On/Off Valve | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 10:30 |  | 21.5 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 10:30 | Elec 1 | 23SD2
10797882 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4621 | ELEC | Granulation | 10797882 - 120W Elec OLL Prog XVlv PC2101 | 10797882 | 0030 | Close Permit - 10797882 - 120W Elec OLL Prog XVlv PC2101 | 0 | Task Dependent | 2023-07-13 10:30 | 2023-07-13 11:00 |  | 21.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 10:30 | 2023-07-13 11:00 | Gran Permit Issuer | 23SD2
10797885 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4621 | ELEC | Granulation | 10797885 - 60W Elec IOD Prog RadDT 46DIT21002 | 10797885 | 0010 | Issue Permit - 10797885 - 60W Elec IOD Prog RadDT 46DIT21002 | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 07:30 |  | 23 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 07:30 | Gran Permit Issuer | 23SD2
10797885 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4621 | ELEC | Granulation | 10797885 - 60W Elec IOD Prog RadDT 46DIT21002 | 10797885 | 0020 | Inspect/Service Density tx | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 09:00 |  | 23 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 09:00 | Elec 1 | 23SD2
10797885 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4621 | ELEC | Granulation | 10797885 - 60W Elec IOD Prog RadDT 46DIT21002 | 10797885 | 0030 | Close Permit - 10797885 - 60W Elec IOD Prog RadDT 46DIT21002 | 0 | Task Dependent | 2023-07-13 09:00 | 2023-07-13 09:30 |  | 23 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 09:00 | 2023-07-13 09:30 | Gran Permit Issuer | 23SD2
10797889 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4621 | ELEC | Granulation | 10797889 - 90W Elec INT Srv DrvCell PC2101 | 10797889 | 0010 | Issue Permit - 10797889 - 90W Elec INT Srv DrvCell PC2101 | 0 | Task Dependent | 2023-07-13 08:30 | 2023-07-13 09:00 |  | 21.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 08:30 | 2023-07-13 09:00 | Gran Permit Issuer | 23SD2
10797889 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4621 | ELEC | Granulation | 10797889 - 90W Elec INT Srv DrvCell PC2101 | 10797889 | 0020 | Inspect/Service Drive Components | 0 | Task Dependent | 2023-07-13 09:00 | 2023-07-13 10:30 |  | 23 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-13 09:00 | 2023-07-13 10:30 | Elec 1 | 23SD2
10797889 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4621 | ELEC | Granulation | 10797889 - 90W Elec INT Srv DrvCell PC2101 | 10797889 | 0030 | Close Permit - 10797889 - 90W Elec INT Srv DrvCell PC2101 | 0 | Task Dependent | 2023-07-13 10:30 | 2023-07-13 11:00 |  | 23 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 10:30 | 2023-07-13 11:00 | Gran Permit Issuer | 23SD2
10797891 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4621 | ELEC | Granulation | 10797891 - 60W Elec IOD Prog RadDT 46DIT21001 | 10797891 | 0010 | Issue Permit - 10797891 - 60W Elec IOD Prog RadDT 46DIT21001 | 0 | Task Dependent | 2023-07-13 10:00 | 2023-07-13 10:30 |  | 20 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 10:00 | 2023-07-13 10:30 | Gran Permit Issuer | 23SD2
10797891 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4621 | ELEC | Granulation | 10797891 - 60W Elec IOD Prog RadDT 46DIT21001 | 10797891 | 0020 | Inspect/Service Density tx | 0 | Task Dependent | 2023-07-13 10:30 | 2023-07-13 12:00 |  | 23 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-13 10:30 | 2023-07-13 12:00 | Elec 1 | 23SD2
10797891 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4621 | ELEC | Granulation | 10797891 - 60W Elec IOD Prog RadDT 46DIT21001 | 10797891 | 0030 | Close Permit - 10797891 - 60W Elec IOD Prog RadDT 46DIT21001 | 0 | Task Dependent | 2023-07-13 12:00 | 2023-07-13 12:30 |  | 23 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 12:00 | 2023-07-13 12:30 | Gran Permit Issuer | 23SD2
10797897 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | GRAN | Granulation | 10797897 - 15W Prod Mont GranSD Grnltn | 10797897 | 0010 | Issue Permit - 10797897 - 15W Prod Mont GranSD Grnltn | 0 | Task Dependent | 2023-07-13 04:30 | 2023-07-13 05:00 |  | 28.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 04:30 | 2023-07-13 05:00 | Gran Permit Issuer | 23SD2
10797897 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | GRAN | Granulation | 10797897 - 15W Prod Mont GranSD Grnltn | 10797897 | 0020 | Test Fan Damper | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 08:00 |  | 28.5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 08:00 | Gran Ops | 23SD2
10797897 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | GRAN | Granulation | 10797897 - 15W Prod Mont GranSD Grnltn | 10797897 | 0030 | Close Permit - 10797897 - 15W Prod Mont GranSD Grnltn | 0 | Task Dependent | 2023-07-13 08:00 | 2023-07-13 08:30 |  | 28.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 08:00 | 2023-07-13 08:30 | Gran Permit Issuer | 23SD2
10797914 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | LUBE | Granulation | 10797914 - 90W FLAC Lube Fld Cplg GranSD MX2201 | 10797914 | 0010 | Issue Permit - 10797914 - 90W FLAC Lube Fld Cplg GranSD MX2201 | 0 | Task Dependent | 2023-07-14 14:00 | 2023-07-14 14:30 |  | 10 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 14:00 | 2023-07-14 14:30 | Gran Permit Issuer | 23SD2
10797914 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | LUBE | Granulation | 10797914 - 90W FLAC Lube Fld Cplg GranSD MX2201 | 10797914 | 0020 | Sample Oil | 0 | Task Dependent | 2023-07-14 14:30 | 2023-07-14 22:30 |  | 42 | 6 | 6 | 6 | 6 | 0 |  |  | 2023-07-14 14:30 | 2023-07-14 22:30 | Lube | 23SD2
10797914 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | LUBE | Granulation | 10797914 - 90W FLAC Lube Fld Cplg GranSD MX2201 | 10797914 | 0030 | Replace Oil | 0 | Task Dependent | 2023-07-14 22:30 | 2023-07-15 04:30 |  | 42 | 6 | 6 | 6 | 6 | 0 |  |  | 2023-07-14 22:30 | 2023-07-15 04:30 | Lube | 23SD2
10797914 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4622 | LUBE | Granulation | 10797914 - 90W FLAC Lube Fld Cplg GranSD MX2201 | 10797914 | 0040 | Close Permit - 10797914 - 90W FLAC Lube Fld Cplg GranSD MX2201 | 0 | Task Dependent | 2023-07-15 04:30 | 2023-07-15 05:00 |  | 42 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 04:30 | 2023-07-15 05:00 | Gran Permit Issuer | 23SD2
10797917 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ENG | Granulation | 10797917 - 210W SEng Test GranSD 46FH2301 | 10797917 | 0010 | Issue Permit - 10797917 - 210W SEng Test GranSD 46FH2301 | 0 | Task Dependent | 2023-07-13 | 2023-07-13 00:30 |  | 44 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 | 2023-07-13 00:30 | Gran Permit Issuer | 23SD2
10797917 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ENG | Granulation | 10797917 - 210W SEng Test GranSD 46FH2301 | 10797917 | 0030 | Perform NDT | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 12:30 |  | 44 | 10 | 10 | 20 | 20 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 12:30 | T/A, Static Engineer | 23SD2
10797917 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ENG | Granulation | 10797917 - 210W SEng Test GranSD 46FH2301 | 10797917 | 0040 | Close Permit - 10797917 - 210W SEng Test GranSD 46FH2301 | 0 | Task Dependent | 2023-07-13 12:30 | 2023-07-13 13:00 |  | 44 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 12:30 | 2023-07-13 13:00 | Gran Permit Issuer | 23SD2
10797919 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10797919 - 30W MFit Rplc Rtry GranSD MX2201 | 10797919 | 0010 | Issue Permit - 10797919 - 30W MFit Rplc Rtry GranSD MX2201 | 0 | Task Dependent | 2023-07-13 11:30 | 2023-07-13 12:00 |  | 9 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 11:30 | 2023-07-13 12:00 | Gran Permit Issuer | 23SD2
10797919 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10797919 - 30W MFit Rplc Rtry GranSD MX2201 | 10797919 | 0030 | Service Rotary Drum | 0 | Task Dependent | 2023-07-13 15:00 | 2023-07-14 03:00 |  | 22.5 | 10 | 10 | 30 | 30 | 0 |  |  | 2023-07-13 15:00 | 2023-07-14 03:00 | T/A, Fitter | 23SD2
10797919 - 0050 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10797919 - 30W MFit Rplc Rtry GranSD MX2201 | 10797919 | 0050 | Replace Liners (CSE) | 0 | Task Dependent | 2023-07-13 15:00 | 2023-07-14 03:00 |  | 11 | 10 | 10 | 50 | 50 | 0 |  |  | 2023-07-13 15:00 | 2023-07-14 03:00 | T/A, Fitter | 23SD2
10797919 - 0100 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10797919 - 30W MFit Rplc Rtry GranSD MX2201 | 10797919 | 0100 | Remove Sacrificial Liner | 0 | Task Dependent | 2023-07-13 12:00 | 2023-07-13 13:00 |  | 9 | 1 | 1 | 3 | 3 | 0 |  |  | 2023-07-13 12:00 | 2023-07-13 13:00 | T/A, Rigger | 23SD2
10797919 - 0110 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10797919 - 30W MFit Rplc Rtry GranSD MX2201 | 10797919 | 0110 | Roll trolley out and lower chute to grade | 0 | Task Dependent | 2023-07-13 16:00 | 2023-07-13 20:00 |  | 9 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-13 16:00 | 2023-07-13 20:00 | Rigger | 23SD2
10797919 - 0130 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10797919 - 30W MFit Rplc Rtry GranSD MX2201 | 10797919 | 0130 | Open western access door | 0 | Task Dependent | 2023-07-14 | 2023-07-14 01:00 |  | 9 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-14 | 2023-07-14 01:00 | Fitter | 23SD2
10797919 - 0170 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10797919 - 30W MFit Rplc Rtry GranSD MX2201 | 10797919 | 0170 | Roll Trolley and Chute into Position | 0 | Task Dependent | 2023-07-14 09:30 | 2023-07-14 11:30 |  | 19 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-14 09:30 | 2023-07-14 11:30 | Rigger | 23SD2
10797919 - 0180 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10797919 - 30W MFit Rplc Rtry GranSD MX2201 | 10797919 | 0180 | Secure Cradle Trolley into Position | 0 | Task Dependent | 2023-07-14 11:30 | 2023-07-14 12:30 |  | 19 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-14 11:30 | 2023-07-14 12:30 | Rigger | 23SD2
10797919 - 0190 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10797919 - 30W MFit Rplc Rtry GranSD MX2201 | 10797919 | 0190 | Wrap Plastic Bags Around Come alongs | 0 | Task Dependent | 2023-07-14 16:30 | 2023-07-14 19:30 |  | 18 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-14 16:30 | 2023-07-14 19:30 | Rigger | 23SD2
10797919 - 0200 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10797919 - 30W MFit Rplc Rtry GranSD MX2201 | 10797919 | 0200 | Re-instate Sacrificial Liner | 0 | Task Dependent | 2023-07-14 19:30 | 2023-07-14 20:30 |  | 18 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-14 19:30 | 2023-07-14 20:30 | Rigger | 23SD2
10797919 - 0220 | Not Started | GLSTest-01.GRAN.MAINT.4622 | CLEAN 2 | Granulation | 10797919 - 30W MFit Rplc Rtry GranSD MX2201 | 10797919 | 0220 | Clean Bolts and rail to Access Sock | 0 | Task Dependent | 2023-07-12 11:00 | 2023-07-12 14:00 |  | 49.5 | 3 | 3 | 9 | 9 | 0 |  |  | 2023-07-12 11:00 | 2023-07-12 14:00 | Waterblast Truck, Cleaning Ops | 23SD2
10797919 - 0240 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10797919 - 30W MFit Rplc Rtry GranSD MX2201 | 10797919 | 0240 | Replace Granulator Sock | 0 | Task Dependent | 2023-07-14 03:00 | 2023-07-14 09:30 |  | 18 | 4.5 | 4.5 | 18 | 18 | 0 |  |  | 2023-07-14 03:00 | 2023-07-14 09:30 | Rigger, Fitter | 23SD2
10797919 - 0250 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10797919 - 30W MFit Rplc Rtry GranSD MX2201 | 10797919 | 0250 | Assist Sock Replacement | 0 | Task Dependent | 2023-07-14 03:00 | 2023-07-14 05:00 |  | 21.5 | 2 | 2 | 6 | 6 | 0 |  |  | 2023-07-14 03:00 | 2023-07-14 05:00 | Crane Operator, Franna, Rigger | 23SD2
10797919 - 0280 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10797919 - 30W MFit Rplc Rtry GranSD MX2201 | 10797919 | 0280 | Close Permit - 10797919 - 30W MFit Rplc Rtry GranSD MX2201 | 0 | Task Dependent | 2023-07-15 07:30 | 2023-07-15 08:00 |  | 9 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 07:30 | 2023-07-15 08:00 | Gran Permit Issuer | 23SD2
10797930 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | LUBE | Granulation | 10797930 - 15W FLAC Lube Dryr GranSD Grnltn | 10797930 | 0010 | Issue Permit - 10797930 - 15W FLAC Lube Dryr GranSD Grnltn | 0 | Task Dependent | 2023-07-13 | 2023-07-13 00:30 |  | 49 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 | 2023-07-13 00:30 | Gran Permit Issuer | 23SD2
10797930 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | LUBE | Granulation | 10797930 - 15W FLAC Lube Dryr GranSD Grnltn | 10797930 | 0020 | Lubricate Couplings | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 07:30 |  | 49 | 5 | 5 | 5 | 5 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 07:30 | Lube | 23SD2
10797930 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | LUBE | Granulation | 10797930 - 15W FLAC Lube Dryr GranSD Grnltn | 10797930 | 0030 | Close Permit - 10797930 - 15W FLAC Lube Dryr GranSD Grnltn | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 08:00 |  | 49 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 08:00 | Gran Permit Issuer | 23SD2
10797931 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | LUBE | Granulation | 10797931 - 15W FLAC Lube Grnl Lvl GranSD Grnltn | 10797931 | 0010 | Issue Permit - 10797931 - 15W FLAC Lube Grnl Lvl GranSD Grnltn | 0 | Task Dependent | 2023-07-14 00:30 | 2023-07-14 01:00 |  | 29.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 00:30 | 2023-07-14 01:00 | Gran Permit Issuer | 23SD2
10797931 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | LUBE | Granulation | 10797931 - 15W FLAC Lube Grnl Lvl GranSD Grnltn | 10797931 | 0020 | Lubricate Coupling | 0 | Task Dependent | 2023-07-14 01:00 | 2023-07-14 05:00 |  | 50 | 4 | 4 | 4 | 4 | 0 |  |  | 2023-07-14 01:00 | 2023-07-14 05:00 | Lube | 23SD2
10797931 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | LUBE | Granulation | 10797931 - 15W FLAC Lube Grnl Lvl GranSD Grnltn | 10797931 | 0030 | Close Permit - 10797931 - 15W FLAC Lube Grnl Lvl GranSD Grnltn | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 07:30 |  | 50 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 07:30 | Gran Permit Issuer | 23SD2
10797952 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10797952 - 60W Elec ISO Prog OPSO DryrBrnr | 10797952 | 0010 | Issue Permit - 10797952 - 60W Elec ISO Prog OPSO DryrBrnr | 0 | Task Dependent | 2023-07-13 | 2023-07-13 00:30 |  | 19.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 | 2023-07-13 00:30 | Gran Permit Issuer | 23SD2
10797952 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10797952 - 60W Elec ISO Prog OPSO DryrBrnr | 10797952 | 0020 | Inspect/service OPSO | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 05:00 |  | 19.5 | 4.5 | 4.5 | 4.5 | 4.5 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 05:00 | Elec 1 | 23SD2
10797952 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10797952 - 60W Elec ISO Prog OPSO DryrBrnr | 10797952 | 0030 | Close Permit - 10797952 - 60W Elec ISO Prog OPSO DryrBrnr | 0 | Task Dependent | 2023-07-13 19:00 | 2023-07-13 19:30 |  | 19.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 19:00 | 2023-07-13 19:30 | Gran Permit Issuer | 23SD2
10797953 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10797953 - 60W Elec OLL Prog CVlv 46PV23001 | 10797953 | 0010 | Issue Permit - 10797953 - 60W Elec OLL Prog CVlv 46PV23001 | 0 | Task Dependent | 2023-07-13 20:30 | 2023-07-13 21:00 |  | 15 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 20:30 | 2023-07-13 21:00 | Gran Permit Issuer | 23SD2
10797953 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10797953 - 60W Elec OLL Prog CVlv 46PV23001 | 10797953 | 0020 | Inspect/Service Control Valve | 0 | Task Dependent | 2023-07-13 21:00 | 2023-07-13 23:30 |  | 21.5 | 2.5 | 2.5 | 2.5 | 2.5 | 0 |  |  | 2023-07-13 21:00 | 2023-07-13 23:30 | Elec 1 | 23SD2
10797953 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10797953 - 60W Elec OLL Prog CVlv 46PV23001 | 10797953 | 0030 | Close Permit - 10797953 - 60W Elec OLL Prog CVlv 46PV23001 | 0 | Task Dependent | 2023-07-13 23:30 | 2023-07-14 |  | 21.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 23:30 | 2023-07-14 | Gran Permit Issuer | 23SD2
10797954 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10797954 - 90W Elec INT Srv DrvCell MX2201 | 10797954 | 0010 | Issue Permit - 10797954 - 90W Elec INT Srv DrvCell MX2201 | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 07:30 |  | 22.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 07:30 | Gran Permit Issuer | 23SD2
10797954 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10797954 - 90W Elec INT Srv DrvCell MX2201 | 10797954 | 0020 | Inspect/Service Drive Components | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 13:30 |  | 22.5 | 6 | 6 | 6 | 6 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 13:30 | Elec 3 | 23SD2
10797954 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10797954 - 90W Elec INT Srv DrvCell MX2201 | 10797954 | 0030 | Close Permit - 10797954 - 90W Elec INT Srv DrvCell MX2201 | 0 | Task Dependent | 2023-07-13 13:30 | 2023-07-13 14:00 |  | 22.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 13:30 | 2023-07-13 14:00 | Gran Permit Issuer | 23SD2
10797955 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10797955 - 90W Elec INT Srv DrvCell FH2301 | 10797955 | 0010 | Issue Permit - 10797955 - 90W Elec INT Srv DrvCell FH2301 | 0 | Task Dependent | 2023-07-13 | 2023-07-13 00:30 |  | 21 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 | 2023-07-13 00:30 | Gran Permit Issuer | 23SD2
10797955 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10797955 - 90W Elec INT Srv DrvCell FH2301 | 10797955 | 0020 | Inspect/Service Drive Components | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 03:30 |  | 21 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 03:30 | Elec 1 | 23SD2
10797955 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10797955 - 90W Elec INT Srv DrvCell FH2301 | 10797955 | 0030 | Close Permit - 10797955 - 90W Elec INT Srv DrvCell FH2301 | 0 | Task Dependent | 2023-07-13 03:30 | 2023-07-13 04:00 |  | 21 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 03:30 | 2023-07-13 04:00 | Gran Permit Issuer | 23SD2
10797956 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10797956 - 60W Elec INT Prog DrvInst CB2301 | 10797956 | 0010 | Issue Permit - 10797956 - 60W Elec INT Prog DrvInst CB2301 | 0 | Task Dependent | 2023-07-13 13:00 | 2023-07-13 13:30 |  | 20.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 13:00 | 2023-07-13 13:30 | Gran Permit Issuer | 23SD2
10797956 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10797956 - 60W Elec INT Prog DrvInst CB2301 | 10797956 | 0020 | Inspect/Test Belt Instrumentation. | 0 | Task Dependent | 2023-07-13 13:30 | 2023-07-13 15:30 |  | 26.5 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-13 13:30 | 2023-07-13 15:30 | Elec 1 | 23SD2
10797956 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10797956 - 60W Elec INT Prog DrvInst CB2301 | 10797956 | 0030 | Close Permit - 10797956 - 60W Elec INT Prog DrvInst CB2301 | 0 | Task Dependent | 2023-07-13 15:30 | 2023-07-13 16:00 |  | 26.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 15:30 | 2023-07-13 16:00 | Gran Permit Issuer | 23SD2
10797957 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10797957 - 30W Elec INT Srv DrvMtr FH2301 | 10797957 | 0010 | Inspect/Service Drive Components | 0 | Task Dependent | 2023-07-13 03:30 | 2023-07-13 05:00 |  | 22.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-13 03:30 | 2023-07-13 05:00 | Elec 1 | 23SD2
10797967 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10797967 - 60W Elec OLL Stat Lnyd CB2301 | 10797967 | 0010 | Issue Permit - 10797967 - 60W Elec OLL Stat Lnyd CB2301 | 0 | Task Dependent | 2023-07-13 14:00 | 2023-07-13 14:30 |  | 19.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 14:00 | 2023-07-13 14:30 | Gran Permit Issuer | 23SD2
10797967 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10797967 - 60W Elec OLL Stat Lnyd CB2301 | 10797967 | 0020 | Inspect/Test Belt Instrumentation. | 0 | Task Dependent | 2023-07-13 14:30 | 2023-07-13 16:30 |  | 26.5 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-13 14:30 | 2023-07-13 16:30 | Elec 1 | 23SD2
10797967 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10797967 - 60W Elec OLL Stat Lnyd CB2301 | 10797967 | 0030 | Close Permit - 10797967 - 60W Elec OLL Stat Lnyd CB2301 | 0 | Task Dependent | 2023-07-13 16:30 | 2023-07-13 17:00 |  | 26.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 16:30 | 2023-07-13 17:00 | Gran Permit Issuer | 23SD2
10797974 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10797974 - 15W Elec SIS Srv GasDet 46AT23002 | 10797974 | 0010 | Issue Permit - 10797974 - 15W Elec SIS Srv GasDet 46AT23002 | 0 | Task Dependent | 2023-07-13 20:30 | 2023-07-13 21:00 |  | 16.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 20:30 | 2023-07-13 21:00 | Gran Permit Issuer | 23SD2
10797974 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10797974 - 15W Elec SIS Srv GasDet 46AT23002 | 10797974 | 0020 | Inspect/Service Gas Detector | 0 | Task Dependent | 2023-07-13 21:00 | 2023-07-13 22:00 |  | 23 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-13 21:00 | 2023-07-13 22:00 | Elec 1 | 23SD2
10797974 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10797974 - 15W Elec SIS Srv GasDet 46AT23002 | 10797974 | 0030 | Close Permit - 10797974 - 15W Elec SIS Srv GasDet 46AT23002 | 0 | Task Dependent | 2023-07-13 22:00 | 2023-07-13 22:30 |  | 23 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 22:00 | 2023-07-13 22:30 | Gran Permit Issuer | 23SD2
10797978 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | BMW | Granulation | 10797978 - 60W MFab Insp GranSD FH2301 | 10797978 | 0010 | Reweld knockers | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 03:30 |  | 49 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 03:30 | BMW | 23SD2
10797978 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | BMW | Granulation | 10797978 - 60W MFab Insp GranSD FH2301 | 10797978 | 0020 | Inspect chairplate keepers | 0 | Task Dependent | 2023-07-13 03:30 | 2023-07-13 07:30 |  | 49 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-13 03:30 | 2023-07-13 07:30 | BMW | 23SD2
10798045 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4624 | GRAN | Granulation | 10798045 - 15W Prod Insp Screen GranSD PrdctScrnng | 10798045 | 0010 | Issue Permit - 10798045 - 15W Prod Insp Screen GranSD PrdctScrnng | 0 | Task Dependent | 2023-07-13 22:30 | 2023-07-13 23:00 |  | 28.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 22:30 | 2023-07-13 23:00 | Gran Permit Issuer | 23SD2
10798045 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4624 | GRAN | Granulation | 10798045 - 15W Prod Insp Screen GranSD PrdctScrnng | 10798045 | 0020 | Inspect Screens | 0 | Task Dependent | 2023-07-13 23:00 | 2023-07-14 08:00 |  | 28.5 | 7 | 7 | 7 | 7 | 0 |  |  | 2023-07-13 23:00 | 2023-07-14 08:00 | Gran Ops | 23SD2
10798045 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4624 | GRAN | Granulation | 10798045 - 15W Prod Insp Screen GranSD PrdctScrnng | 10798045 | 0030 | Close Permit - 10798045 - 15W Prod Insp Screen GranSD PrdctScrnng | 0 | Task Dependent | 2023-07-14 08:00 | 2023-07-14 08:30 |  | 28.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 08:00 | 2023-07-14 08:30 | Gran Permit Issuer | 23SD2
10798059 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4624 | RUBBER | Granulation | 10798059 - 15W MFit Insp GranSD FV2401 | 10798059 | 0010 | Issue Permit - 10798059 - 15W MFit Insp GranSD FV2401 | 0 | Task Dependent | 2023-07-13 16:00 | 2023-07-13 16:30 |  | 34 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 16:00 | 2023-07-13 16:30 | Gran Permit Issuer | 23SD2
10798059 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4624 | RUBBER | Granulation | 10798059 - 15W MFit Insp GranSD FV2401 | 10798059 | 0020 | Inspect Conveyor | 0 | Task Dependent | 2023-07-13 16:30 | 2023-07-13 20:00 |  | 34 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-13 16:30 | 2023-07-13 20:00 | Rubber | 23SD2
10798059 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4624 | RUBBER | Granulation | 10798059 - 15W MFit Insp GranSD FV2401 | 10798059 | 0030 | Close Permit - 10798059 - 15W MFit Insp GranSD FV2401 | 0 | Task Dependent | 2023-07-13 20:00 | 2023-07-13 20:30 |  | 41 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 20:00 | 2023-07-13 20:30 | Gran Permit Issuer | 23SD2
10798065 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4624 | DAWSON1 | Granulation | 10798065 - 120W MFit Rplc Screen GranSD SV2502 | 10798065 | 0010 | Issue Permit - 10798065 - 120W MFit Rplc Screen GranSD SV2502 | 0 | Task Dependent | 2023-07-13 | 2023-07-13 00:30 |  | 12 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 | 2023-07-13 00:30 | Gran Permit Issuer | 23SD2
10798065 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4624 | DAWSON1 | Granulation | 10798065 - 120W MFit Rplc Screen GranSD SV2502 | 10798065 | 0020 | Erect Scaffold | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 04:30 |  | 12 | 4 | 4 | 12 | 12 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 04:30 | Scaffolder | 23SD2
10798065 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4624 | DAWSON1 | Granulation | 10798065 - 120W MFit Rplc Screen GranSD SV2502 | 10798065 | 0030 | Inspect Screen | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 12:30 |  | 11 | 5 | 5 | 10 | 10 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 12:30 | Fitter | 23SD2
10798065 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4624 | DAWSON1 | Granulation | 10798065 - 120W MFit Rplc Screen GranSD SV2502 | 10798065 | 0040 | Replace Screen Components | 0 | Task Dependent | 2023-07-13 12:30 | 2023-07-14 12:30 |  | 11 | 20 | 20 | 40 | 40 | 0 |  |  | 2023-07-13 12:30 | 2023-07-14 12:30 | Fitter | 23SD2
10798065 - 0050 | Not Started | GLSTest-01.GRAN.MAINT.4624 | DAWSON1 | Granulation | 10798065 - 120W MFit Rplc Screen GranSD SV2502 | 10798065 | 0050 | Assist Screen Replace | 0 | Task Dependent | 2023-07-13 12:30 | 2023-07-13 20:30 |  | 34 | 6 | 6 | 18 | 18 | 0 |  |  | 2023-07-13 12:30 | 2023-07-13 20:30 | Scaffolder | 23SD2
10798065 - 0060 | Not Started | GLSTest-01.GRAN.MAINT.4624 | DAWSON1 | Granulation | 10798065 - 120W MFit Rplc Screen GranSD SV2502 | 10798065 | 0060 | Dismantle Scaffold Access | 0 | Task Dependent | 2023-07-14 12:30 | 2023-07-14 16:30 |  | 20 | 4 | 4 | 12 | 12 | 0 |  |  | 2023-07-14 12:30 | 2023-07-14 16:30 | Scaffolder | 23SD2
10798065 - 0070 | Not Started | GLSTest-01.GRAN.MAINT.4624 | DAWSON1 | Granulation | 10798065 - 120W MFit Rplc Screen GranSD SV2502 | 10798065 | 0070 | Close Permit - 10798065 - 120W MFit Rplc Screen GranSD SV2502 | 0 | Task Dependent | 2023-07-14 16:30 | 2023-07-14 17:00 |  | 20 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 16:30 | 2023-07-14 17:00 | Gran Permit Issuer | 23SD2
10798068 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4624 | DAWSON1 | Granulation | 10798068 - 30W MFit Insp Screen GranSD SV2402 | 10798068 | 0010 | Issue Permit - 10798068 - 30W MFit Insp Screen GranSD SV2402 | 0 | Task Dependent | 2023-07-13 | 2023-07-13 00:30 |  | 11 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 | 2023-07-13 00:30 | Gran Permit Issuer | 23SD2
10798068 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4624 | DAWSON1 | Granulation | 10798068 - 30W MFit Insp Screen GranSD SV2402 | 10798068 | 0020 | Inspect Screen | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 07:30 |  | 11 | 5 | 5 | 10 | 10 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 07:30 | Fitter | 23SD2
10798068 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4624 | DAWSON1 | Granulation | 10798068 - 30W MFit Insp Screen GranSD SV2402 | 10798068 | 0030 | Close Permit - 10798068 - 30W MFit Insp Screen GranSD SV2402 | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 08:00 |  | 49 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 08:00 | Gran Permit Issuer | 23SD2
10798070 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4624 | DAWSON1 | Granulation | 10798070 - 30W MFit Insp Screen GranSD SV2503 | 10798070 | 0010 | Issue Permit - 10798070 - 30W MFit Insp Screen GranSD SV2503 | 0 | Task Dependent | 2023-07-13 | 2023-07-13 00:30 |  | 25.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 | 2023-07-13 00:30 | Gran Permit Issuer | 23SD2
10798070 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4624 | DAWSON1 | Granulation | 10798070 - 30W MFit Insp Screen GranSD SV2503 | 10798070 | 0020 | Inspect Screen | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 05:00 |  | 25.5 | 4.5 | 4.5 | 9 | 9 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 05:00 | Fitter | 23SD2
10798070 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4624 | DAWSON1 | Granulation | 10798070 - 30W MFit Insp Screen GranSD SV2503 | 10798070 | 0030 | Close Permit - 10798070 - 30W MFit Insp Screen GranSD SV2503 | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 07:30 |  | 25.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 07:30 | Gran Permit Issuer | 23SD2
10798083 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4624 | ELEC | Granulation | 10798083 - 60W Elec INT Prog DrvInst CC2402 | 10798083 | 0010 | Issue Permit - 10798083 - 60W Elec INT Prog DrvInst CC2402 | 0 | Task Dependent | 2023-07-13 | 2023-07-13 00:30 |  | 23 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 | 2023-07-13 00:30 | Gran Permit Issuer | 23SD2
10798083 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4624 | ELEC | Granulation | 10798083 - 60W Elec INT Prog DrvInst CC2402 | 10798083 | 0020 | Inspect/Service Drive Instrumentation | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 01:30 |  | 23 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 01:30 | Elec 2 | 23SD2
10798083 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4624 | ELEC | Granulation | 10798083 - 60W Elec INT Prog DrvInst CC2402 | 10798083 | 0030 | Close Permit - 10798083 - 60W Elec INT Prog DrvInst CC2402 | 0 | Task Dependent | 2023-07-13 01:30 | 2023-07-13 02:00 |  | 23 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 01:30 | 2023-07-13 02:00 | Gran Permit Issuer | 23SD2
10798103 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4624 | ENG | Granulation | 10798103 - 60W REng Insp GranSD CC2402 | 10798103 | 0010 | Issue Permit - 10798103 - 60W REng Insp GranSD CC2402 | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 07:30 |  | 46 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 07:30 | Gran Permit Issuer | 23SD2
10798103 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4624 | ENG | Granulation | 10798103 - 60W REng Insp GranSD CC2402 | 10798103 | 0020 | Inspect bucket elevator | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 08:30 |  | 46 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 08:30 | Rotating Engineer | 23SD2
10798103 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4624 | ENG | Granulation | 10798103 - 60W REng Insp GranSD CC2402 | 10798103 | 0030 | Assist bucket elevator inspection | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 08:00 |  | 46.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 08:00 | Fitter | 23SD2
10798103 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4624 | ENG | Granulation | 10798103 - 60W REng Insp GranSD CC2402 | 10798103 | 0040 | Close Permit - 10798103 - 60W REng Insp GranSD CC2402 | 0 | Task Dependent | 2023-07-13 08:30 | 2023-07-13 09:00 |  | 46 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 08:30 | 2023-07-13 09:00 | Gran Permit Issuer | 23SD2
10798123 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | GRAN | Granulation | 10798123 - 30W Prod Mont PROC GranSD Scrbbng | 10798123 | 0010 | Stroke valve to verify function | 0 | Task Dependent | 2023-07-13 19:00 | 2023-07-13 20:00 |  | 28.5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-13 19:00 | 2023-07-13 20:00 | Gran Ops | 23SD2
10798124 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | GRAN | Granulation | 10798124 - 15W Prod Prog Fan GranSD Scrbbng | 10798124 | 0010 | Issue Permit - 10798124 - 15W Prod Prog Fan GranSD Scrbbng | 0 | Task Dependent | 2023-07-13 08:30 | 2023-07-13 09:00 |  | 28.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 08:30 | 2023-07-13 09:00 | Gran Permit Issuer | 23SD2
10798124 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4628 | GRAN | Granulation | 10798124 - 15W Prod Prog Fan GranSD Scrbbng | 10798124 | 0020 | Test Fan Damper | 0 | Task Dependent | 2023-07-13 09:00 | 2023-07-13 10:00 |  | 28.5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-13 09:00 | 2023-07-13 10:00 | Gran Ops | 23SD2
10798124 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4628 | GRAN | Granulation | 10798124 - 15W Prod Prog Fan GranSD Scrbbng | 10798124 | 0030 | Close Permit - 10798124 - 15W Prod Prog Fan GranSD Scrbbng | 0 | Task Dependent | 2023-07-13 10:00 | 2023-07-13 10:30 |  | 28.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 10:00 | 2023-07-13 10:30 | Gran Permit Issuer | 23SD2
10798142 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | DAWSON1 | Granulation | 10798142 - 60W MFit Insp GranSD 46AR2802 | 10798142 | 0010 | Issue Permit - 10798142 - 60W MFit Insp GranSD 46AR2802 | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 01:00 |  | 45 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 01:00 | Gran Permit Issuer | 23SD2
10798142 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4628 | DAWSON1 | Granulation | 10798142 - 60W MFit Insp GranSD 46AR2802 | 10798142 | 0020 | Vac Out Tank | 0 | Task Dependent | 2023-07-13 23:00 | 2023-07-14 01:00 |  | 27.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-13 23:00 | 2023-07-14 01:00 | Vac Truck, Cleaning Ops | 23SD2
10798142 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4628 | DAWSON1 | Granulation | 10798142 - 60W MFit Insp GranSD 46AR2802 | 10798142 | 0040 | Inspect Agitator | 0 | Task Dependent | 2023-07-14 01:00 | 2023-07-14 01:30 |  | 27.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 01:00 | 2023-07-14 01:30 | Rotating Engineer | 23SD2
10798142 - 0050 | Not Started | GLSTest-01.GRAN.MAINT.4628 | DAWSON1 | Granulation | 10798142 - 60W MFit Insp GranSD 46AR2802 | 10798142 | 0050 | Unbox | 0 | Task Dependent | 2023-07-13 01:00 | 2023-07-13 01:30 |  | 45 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-13 01:00 | 2023-07-13 01:30 | Fitter | 23SD2
10798142 - 0060 | Not Started | GLSTest-01.GRAN.MAINT.4628 | DAWSON1 | Granulation | 10798142 - 60W MFit Insp GranSD 46AR2802 | 10798142 | 0060 | Inspect running agitator | 0 | Task Dependent | 2023-07-14 01:30 | 2023-07-14 02:00 |  | 27.5 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-14 01:30 | 2023-07-14 02:00 | Fitter, Rotating Engineer | 23SD2
10798142 - 0080 | Not Started | GLSTest-01.GRAN.MAINT.4628 | DAWSON1 | Granulation | 10798142 - 60W MFit Insp GranSD 46AR2802 | 10798142 | 0080 | Close Permit - 10798142 - 60W MFit Insp GranSD 46AR2802 | 0 | Task Dependent | 2023-07-14 02:30 | 2023-07-14 03:00 |  | 27.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 02:30 | 2023-07-14 03:00 | Gran Permit Issuer | 23SD2
10798153 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798153 - 120W Elec OLL Prog CVlv 46FV28002 | 10798153 | 0010 | Issue Permit - 10798153 - 120W Elec OLL Prog CVlv 46FV28002 | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 07:30 |  | 22 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 07:30 | Gran Permit Issuer | 23SD2
10798153 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798153 - 120W Elec OLL Prog CVlv 46FV28002 | 10798153 | 0020 | Inspect/Service Control Valve | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 10:00 |  | 22 | 2.5 | 2.5 | 2.5 | 2.5 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 10:00 | Projects Elec | 23SD2
10798153 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798153 - 120W Elec OLL Prog CVlv 46FV28002 | 10798153 | 0030 | Close Permit - 10798153 - 120W Elec OLL Prog CVlv 46FV28002 | 0 | Task Dependent | 2023-07-13 10:00 | 2023-07-13 10:30 |  | 22 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 10:00 | 2023-07-13 10:30 | Gran Permit Issuer | 23SD2
10798157 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798157 - 120W Elec OLL Prog CVlv 46FV28005 | 10798157 | 0010 | Issue Permit - 10798157 - 120W Elec OLL Prog CVlv 46FV28005 | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 07:30 |  | 22 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 07:30 | Gran Permit Issuer | 23SD2
10798157 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798157 - 120W Elec OLL Prog CVlv 46FV28005 | 10798157 | 0020 | Inspect/Service Control Valve | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 10:00 |  | 22 | 2.5 | 2.5 | 2.5 | 2.5 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 10:00 | Projects Elec | 23SD2
10798157 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798157 - 120W Elec OLL Prog CVlv 46FV28005 | 10798157 | 0030 | Close Permit - 10798157 - 120W Elec OLL Prog CVlv 46FV28005 | 0 | Task Dependent | 2023-07-13 10:00 | 2023-07-13 10:30 |  | 22 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 10:00 | 2023-07-13 10:30 | Gran Permit Issuer | 23SD2
10798158 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798158 - 60W Elec OLL Prog CVlv 46FV28001 | 10798158 | 0010 | Issue Permit - 10798158 - 60W Elec OLL Prog CVlv 46FV28001 | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 07:30 |  | 22 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 07:30 | Gran Permit Issuer | 23SD2
10798158 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798158 - 60W Elec OLL Prog CVlv 46FV28001 | 10798158 | 0020 | Inspect/Service Control Valve | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 10:00 |  | 22 | 2.5 | 2.5 | 2.5 | 2.5 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 10:00 | Projects Elec | 23SD2
10798158 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798158 - 60W Elec OLL Prog CVlv 46FV28001 | 10798158 | 0030 | Close Permit - 10798158 - 60W Elec OLL Prog CVlv 46FV28001 | 0 | Task Dependent | 2023-07-13 10:00 | 2023-07-13 10:30 |  | 22 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 10:00 | 2023-07-13 10:30 | Gran Permit Issuer | 23SD2
10798159 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798159 - 120W Elec OLL Prog XVlv 46XV28028 | 10798159 | 0010 | Issue Permit - 10798159 - 120W Elec OLL Prog XVlv 46XV28028 | 0 | Task Dependent | 2023-07-13 14:00 | 2023-07-13 14:30 |  | 16 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 14:00 | 2023-07-13 14:30 | Gran Permit Issuer | 23SD2
10798159 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798159 - 120W Elec OLL Prog XVlv 46XV28028 | 10798159 | 0020 | Inspect/Service On/Off Valve | 0 | Task Dependent | 2023-07-13 14:30 | 2023-07-13 16:00 |  | 23 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-13 14:30 | 2023-07-13 16:00 | Elec 2 | 23SD2
10798159 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798159 - 120W Elec OLL Prog XVlv 46XV28028 | 10798159 | 0030 | Close Permit - 10798159 - 120W Elec OLL Prog XVlv 46XV28028 | 0 | Task Dependent | 2023-07-13 16:00 | 2023-07-13 16:30 |  | 23 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 16:00 | 2023-07-13 16:30 | Gran Permit Issuer | 23SD2
10798160 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798160 - 60W Elec OLL Prog CVlv 46HV28006 | 10798160 | 0010 | Issue Permit - 10798160 - 60W Elec OLL Prog CVlv 46HV28006 | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 07:30 |  | 22 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 07:30 | Gran Permit Issuer | 23SD2
10798160 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798160 - 60W Elec OLL Prog CVlv 46HV28006 | 10798160 | 0020 | Inspect/Service Control Valve | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 10:00 |  | 22 | 2.5 | 2.5 | 2.5 | 2.5 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 10:00 | Elec 2 | 23SD2
10798160 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798160 - 60W Elec OLL Prog CVlv 46HV28006 | 10798160 | 0030 | Close Permit - 10798160 - 60W Elec OLL Prog CVlv 46HV28006 | 0 | Task Dependent | 2023-07-13 10:00 | 2023-07-13 10:30 |  | 22 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 10:00 | 2023-07-13 10:30 | Gran Permit Issuer | 23SD2
10798164 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798164 - 120W Elec INT Rplc DrvCell AR2802 | 10798164 | 0010 | Issue Permit - 10798164 - 120W Elec INT Rplc DrvCell AR2802 | 0 | Task Dependent | 2023-07-13 01:00 | 2023-07-13 01:30 |  | 21.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 01:00 | 2023-07-13 01:30 | Gran Permit Issuer | 23SD2
10798164 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798164 - 120W Elec INT Rplc DrvCell AR2802 | 10798164 | 0020 | Inspect/Service Drive Components | 0 | Task Dependent | 2023-07-13 01:30 | 2023-07-13 03:00 |  | 22 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-13 01:30 | 2023-07-13 03:00 | Elec 2 | 23SD2
10798164 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798164 - 120W Elec INT Rplc DrvCell AR2802 | 10798164 | 0030 | Close Permit - 10798164 - 120W Elec INT Rplc DrvCell AR2802 | 0 | Task Dependent | 2023-07-13 03:00 | 2023-07-13 03:30 |  | 22 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 03:00 | 2023-07-13 03:30 | Gran Permit Issuer | 23SD2
10798166 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798166 - 90W Elec INT Srv DrvCell PC2802 | 10798166 | 0010 | Issue Permit - 10798166 - 90W Elec INT Srv DrvCell PC2802 | 0 | Task Dependent | 2023-07-13 10:00 | 2023-07-13 10:30 |  | 20 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 10:00 | 2023-07-13 10:30 | Gran Permit Issuer | 23SD2
10798166 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798166 - 90W Elec INT Srv DrvCell PC2802 | 10798166 | 0020 | Inspect/Service Drive Components | 0 | Task Dependent | 2023-07-13 10:30 | 2023-07-13 12:00 |  | 23 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-13 10:30 | 2023-07-13 12:00 | Elec 1 | 23SD2
10798166 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798166 - 90W Elec INT Srv DrvCell PC2802 | 10798166 | 0030 | Close Permit - 10798166 - 90W Elec INT Srv DrvCell PC2802 | 0 | Task Dependent | 2023-07-13 12:00 | 2023-07-13 12:30 |  | 23 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 12:00 | 2023-07-13 12:30 | Gran Permit Issuer | 23SD2
10798174 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798174 - 60W Elec CAL Prog Temp FC2801 | 10798174 | 0010 | Issue Permit - 10798174 - 60W Elec CAL Prog Temp FC2801 | 0 | Task Dependent | 2023-07-13 14:00 | 2023-07-13 14:30 |  | 15.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 14:00 | 2023-07-13 14:30 | Gran Permit Issuer | 23SD2
10798174 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798174 - 60W Elec CAL Prog Temp FC2801 | 10798174 | 0020 | Inspect/Service Temperature Instruments | 0 | Task Dependent | 2023-07-13 14:30 | 2023-07-13 16:30 |  | 22.5 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-13 14:30 | 2023-07-13 16:30 | Elec 2 | 23SD2
10798174 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798174 - 60W Elec CAL Prog Temp FC2801 | 10798174 | 0030 | Close Permit - 10798174 - 60W Elec CAL Prog Temp FC2801 | 0 | Task Dependent | 2023-07-13 16:30 | 2023-07-13 17:00 |  | 22.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 16:30 | 2023-07-13 17:00 | Gran Permit Issuer | 23SD2
10798178 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798178 - 60W Elec CAL Prog Temp FC2802 | 10798178 | 0010 | Issue Permit - 10798178 - 60W Elec CAL Prog Temp FC2802 | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 07:30 |  | 6 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 07:30 | Gran Permit Issuer | 23SD2
10798178 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798178 - 60W Elec CAL Prog Temp FC2802 | 10798178 | 0020 | Inspect/Service Temperature Instruments | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 10:30 |  | 6 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 10:30 | Elec 2 | 23SD2
10798178 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798178 - 60W Elec CAL Prog Temp FC2802 | 10798178 | 0030 | Close Permit - 10798178 - 60W Elec CAL Prog Temp FC2802 | 0 | Task Dependent | 2023-07-13 10:30 | 2023-07-13 11:00 |  | 6 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 10:30 | 2023-07-13 11:00 | Gran Permit Issuer | 23SD2
10798210 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798210 - 60W Elec IOD Prog VegaDT 46DT28033 | 10798210 | 0010 | Issue Permit - 10798210 - 60W Elec IOD Prog VegaDT 46DT28033 | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 07:30 |  | 23 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 07:30 | Gran Permit Issuer | 23SD2
10798210 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798210 - 60W Elec IOD Prog VegaDT 46DT28033 | 10798210 | 0020 | Inspect/Service Density tx | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 09:00 |  | 23 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 09:00 | Projects Elec | 23SD2
10798210 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798210 - 60W Elec IOD Prog VegaDT 46DT28033 | 10798210 | 0030 | Close Permit - 10798210 - 60W Elec IOD Prog VegaDT 46DT28033 | 0 | Task Dependent | 2023-07-13 09:00 | 2023-07-13 09:30 |  | 23 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 09:00 | 2023-07-13 09:30 | Gran Permit Issuer | 23SD2
10798213 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798213 - 60W Elec IOD Prog VegaDT 46DIT28001 | 10798213 | 0010 | Issue Permit - 10798213 - 60W Elec IOD Prog VegaDT 46DIT28001 | 0 | Task Dependent | 2023-07-13 11:30 | 2023-07-13 12:00 |  | 18.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 11:30 | 2023-07-13 12:00 | Gran Permit Issuer | 23SD2
10798213 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798213 - 60W Elec IOD Prog VegaDT 46DIT28001 | 10798213 | 0020 | Inspect/Service Density tx | 0 | Task Dependent | 2023-07-13 12:00 | 2023-07-13 13:30 |  | 23 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-13 12:00 | 2023-07-13 13:30 | Elec 1 | 23SD2
10798213 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10798213 - 60W Elec IOD Prog VegaDT 46DIT28001 | 10798213 | 0030 | Close Permit - 10798213 - 60W Elec IOD Prog VegaDT 46DIT28001 | 0 | Task Dependent | 2023-07-13 13:30 | 2023-07-13 14:00 |  | 23 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 13:30 | 2023-07-13 14:00 | Gran Permit Issuer | 23SD2
10798222 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | DAWSON3 | Granulation | 10798222 - 52W MFit Rplc SprysFlngs GranSD 46SU2701 | 10798222 | 0010 | Issue Permit - 10798222 - 52W MFit Rplc SprysFlngs GranSD 46SU2701 | 0 | Task Dependent | 2023-07-13 22:00 | 2023-07-13 22:30 |  | 15 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 22:00 | 2023-07-13 22:30 | Gran Permit Issuer | 23SD2
10798222 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4628 | DAWSON3 | Granulation | 10798222 - 52W MFit Rplc SprysFlngs GranSD 46SU2701 | 10798222 | 0020 | Remove sprays bars | 0 | Task Dependent | 2023-07-13 22:30 | 2023-07-14 01:30 |  | 15 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-13 22:30 | 2023-07-14 01:30 | Fitter | 23SD2
10798222 - 0050 | Not Started | GLSTest-01.GRAN.MAINT.4628 | DAWSON3 | Granulation | 10798222 - 52W MFit Rplc SprysFlngs GranSD 46SU2701 | 10798222 | 0050 | Inspect spray bar welds | 0 | Task Dependent | 2023-07-14 01:30 | 2023-07-14 03:30 |  | 15 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-14 01:30 | 2023-07-14 03:30 | Static Engineer | 23SD2
10798222 - 0060 | Not Started | GLSTest-01.GRAN.MAINT.4628 | DAWSON3 | Granulation | 10798222 - 52W MFit Rplc SprysFlngs GranSD 46SU2701 | 10798222 | 0060 | CSE - Inspect strips | 0 | Task Dependent | 2023-07-15 | 2023-07-15 02:00 |  | 8 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-15 | 2023-07-15 02:00 | T/A, Static Engineer | 23SD2
10798222 - 0080 | Not Started | GLSTest-01.GRAN.MAINT.4628 | DAWSON3 | Granulation | 10798222 - 52W MFit Rplc SprysFlngs GranSD 46SU2701 | 10798222 | 0080 | Reinstate sprays bars | 0 | Task Dependent | 2023-07-14 03:30 | 2023-07-14 08:30 |  | 15 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-14 03:30 | 2023-07-14 08:30 | Fitter | 23SD2
10798222 - 0100 | Not Started | GLSTest-01.GRAN.MAINT.4628 | DAWSON3 | Granulation | 10798222 - 52W MFit Rplc SprysFlngs GranSD 46SU2701 | 10798222 | 0100 | Close Permit - 10798222 - 52W MFit Rplc SprysFlngs GranSD 46SU2701 | 0 | Task Dependent | 2023-07-15 02:00 | 2023-07-15 02:30 |  | 8 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 02:00 | 2023-07-15 02:30 | Gran Permit Issuer | 23SD2
10798223 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | DAWSON1 | Granulation | 10798223 - 52W MFit Rplc Sprays GranSD 46SU2801 | 10798223 | 0010 | Issue Permit - 10798223 - 52W MFit Rplc Sprays GranSD 46SU2801 | 0 | Task Dependent | 2023-07-14 12:30 | 2023-07-14 13:00 |  | 11 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 12:30 | 2023-07-14 13:00 | Gran Permit Issuer | 23SD2
10798223 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4628 | DAWSON1 | Granulation | 10798223 - 52W MFit Rplc Sprays GranSD 46SU2801 | 10798223 | 0020 | Remove sprays | 0 | Task Dependent | 2023-07-14 13:00 | 2023-07-14 16:00 |  | 11 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-14 13:00 | 2023-07-14 16:00 | Fitter | 23SD2
10798223 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4628 | DAWSON1 | Granulation | 10798223 - 52W MFit Rplc Sprays GranSD 46SU2801 | 10798223 | 0030 | Close Permit - 10798223 - 52W MFit Rplc Sprays GranSD 46SU2801 | 0 | Task Dependent | 2023-07-14 23:00 | 2023-07-14 23:30 |  | 11 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 23:00 | 2023-07-14 23:30 | Gran Permit Issuer | 23SD2
10798233 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4629 | GRAN | Granulation | 10798233 - 15W Prod Mont Fan GranSD NH3Systm | 10798233 | 0010 | Issue Permit - 10798233 - 15W Prod Mont Fan GranSD NH3Systm | 0 | Task Dependent | 2023-07-13 14:30 | 2023-07-13 15:00 |  | 28.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 14:30 | 2023-07-13 15:00 | Gran Permit Issuer | 23SD2
10798233 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4629 | GRAN | Granulation | 10798233 - 15W Prod Mont Fan GranSD NH3Systm | 10798233 | 0020 | Test Fan Damper | 0 | Task Dependent | 2023-07-13 15:00 | 2023-07-13 16:00 |  | 28.5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-13 15:00 | 2023-07-13 16:00 | Gran Ops | 23SD2
10798233 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4629 | GRAN | Granulation | 10798233 - 15W Prod Mont Fan GranSD NH3Systm | 10798233 | 0030 | Close Permit - 10798233 - 15W Prod Mont Fan GranSD NH3Systm | 0 | Task Dependent | 2023-07-13 16:00 | 2023-07-13 16:30 |  | 28.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 16:00 | 2023-07-13 16:30 | Gran Permit Issuer | 23SD2
10798240 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4629 | LUBE | Granulation | 10798240 - 30W FLAC Lube GranSD FC2901 | 10798240 | 0010 | Issue Permit - 10798240 - 30W FLAC Lube GranSD FC2901 | 0 | Task Dependent | 2023-07-14 04:30 | 2023-07-14 05:00 |  | 24.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 04:30 | 2023-07-14 05:00 | Gran Permit Issuer | 23SD2
10798240 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4629 | LUBE | Granulation | 10798240 - 30W FLAC Lube GranSD FC2901 | 10798240 | 0020 | Lubricate Fan | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 07:30 |  | 48.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 07:30 | Lube | 23SD2
10798240 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4629 | LUBE | Granulation | 10798240 - 30W FLAC Lube GranSD FC2901 | 10798240 | 0030 | Close Permit - 10798240 - 30W FLAC Lube GranSD FC2901 | 0 | Task Dependent | 2023-07-14 07:30 | 2023-07-14 08:00 |  | 48.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 07:30 | 2023-07-14 08:00 | Gran Permit Issuer | 23SD2
10798241 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4629 | ELEC | Granulation | 10798241 - 30W Elec ISO Stat GdWvRdr 46LIT29003 | 10798241 | 0010 | Issue Permit - 10798241 - 30W Elec ISO Stat GdWvRdr 46LIT29003 | 0 | Task Dependent | 2023-07-13 12:30 | 2023-07-13 13:00 |  | 18 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 12:30 | 2023-07-13 13:00 | Gran Permit Issuer | 23SD2
10798241 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4629 | ELEC | Granulation | 10798241 - 30W Elec ISO Stat GdWvRdr 46LIT29003 | 10798241 | 0020 | Perform function test of SIF #232 | 0 | Task Dependent | 2023-07-13 13:00 | 2023-07-13 15:00 |  | 23.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-13 13:00 | 2023-07-13 15:00 | Process Control Tech, Elec 4 | 23SD2
10798241 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4629 | ELEC | Granulation | 10798241 - 30W Elec ISO Stat GdWvRdr 46LIT29003 | 10798241 | 0040 | Close Permit - 10798241 - 30W Elec ISO Stat GdWvRdr 46LIT29003 | 0 | Task Dependent | 2023-07-13 15:00 | 2023-07-13 15:30 |  | 23.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 15:00 | 2023-07-13 15:30 | Gran Permit Issuer | 23SD2
10798248 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4629 | ELEC | Granulation | 10798248 - 30W Elec ISO Srv SIF#232 46LV29002 | 10798248 | 0010 | Issue Permit - 10798248 - 30W Elec ISO Srv SIF#232 46LV29002 | 0 | Task Dependent | 2023-07-13 02:30 | 2023-07-13 03:00 |  | 46 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 02:30 | 2023-07-13 03:00 | Gran Permit Issuer | 23SD2
10798248 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4629 | ELEC | Granulation | 10798248 - 30W Elec ISO Srv SIF#232 46LV29002 | 10798248 | 0020 | Perform function test of SIF #232 | 0 | Task Dependent | 2023-07-13 03:00 | 2023-07-13 05:00 |  | 46 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-13 03:00 | 2023-07-13 05:00 | Process Control Tech, Projects Elec | 23SD2
10798248 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4629 | ELEC | Granulation | 10798248 - 30W Elec ISO Srv SIF#232 46LV29002 | 10798248 | 0040 | Close Permit - 10798248 - 30W Elec ISO Srv SIF#232 46LV29002 | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 07:30 |  | 46 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 07:30 | Gran Permit Issuer | 23SD2
10798249 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4629 | ELEC | Granulation | 10798249 - 120W Elec CAL Prog Temp 46TIT29007 | 10798249 | 0010 | Issue Permit - 10798249 - 120W Elec CAL Prog Temp 46TIT29007 | 0 | Task Dependent | 2023-07-13 14:30 | 2023-07-13 15:00 |  | 16 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 14:30 | 2023-07-13 15:00 | Gran Permit Issuer | 23SD2
10798249 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4629 | ELEC | Granulation | 10798249 - 120W Elec CAL Prog Temp 46TIT29007 | 10798249 | 0020 | Inspect/Service Temperature Instruments | 0 | Task Dependent | 2023-07-13 15:00 | 2023-07-13 17:00 |  | 23.5 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-13 15:00 | 2023-07-13 17:00 | Elec 4 | 23SD2
10798249 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4629 | ELEC | Granulation | 10798249 - 120W Elec CAL Prog Temp 46TIT29007 | 10798249 | 0030 | Close Permit - 10798249 - 120W Elec CAL Prog Temp 46TIT29007 | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 07:30 |  | 23.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 07:30 | Gran Permit Issuer | 23SD2
10798252 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4629 | ELEC | Granulation | 10798252 - 120W Elec ISO Prog GWave 46LIT29004 | 10798252 | 0010 | Issue Permit - 10798252 - 120W Elec ISO Prog GWave 46LIT29004 | 0 | Task Dependent | 2023-07-14 13:00 | 2023-07-14 13:30 |  | 8.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 13:00 | 2023-07-14 13:30 | Gran Permit Issuer | 23SD2
10798252 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4629 | ELEC | Granulation | 10798252 - 120W Elec ISO Prog GWave 46LIT29004 | 10798252 | 0020 | Inspect/Service Level tx | 0 | Task Dependent | 2023-07-14 13:30 | 2023-07-14 14:30 |  | 24.5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-14 13:30 | 2023-07-14 14:30 | Elec 4 | 23SD2
10798252 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4629 | ELEC | Granulation | 10798252 - 120W Elec ISO Prog GWave 46LIT29004 | 10798252 | 0030 | Close Permit - 10798252 - 120W Elec ISO Prog GWave 46LIT29004 | 0 | Task Dependent | 2023-07-14 14:30 | 2023-07-14 15:00 |  | 24.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 14:30 | 2023-07-14 15:00 | Gran Permit Issuer | 23SD2
10798253 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4629 | ELEC | Granulation | 10798253 - 60W Elec SIS Prog Press 46PIT29004 | 10798253 | 0010 | Issue Permit - 10798253 - 60W Elec SIS Prog Press 46PIT29004 | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 07:30 |  | 22.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 07:30 | Gran Permit Issuer | 23SD2
10798253 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4629 | ELEC | Granulation | 10798253 - 60W Elec SIS Prog Press 46PIT29004 | 10798253 | 0020 | Inspect/Service Press Instrument | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 10:30 |  | 22.5 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 10:30 | Elec 4 | 23SD2
10798253 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4629 | ELEC | Granulation | 10798253 - 60W Elec SIS Prog Press 46PIT29004 | 10798253 | 0030 | Close Permit - 10798253 - 60W Elec SIS Prog Press 46PIT29004 | 0 | Task Dependent | 2023-07-13 10:30 | 2023-07-13 11:00 |  | 22.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 10:30 | 2023-07-13 11:00 | Gran Permit Issuer | 23SD2
10798259 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4629 | ELEC | Granulation | 10798259 - 60W Elec OLL Prog CVlv 46FV29002 | 10798259 | 0010 | Issue Permit - 10798259 - 60W Elec OLL Prog CVlv 46FV29002 | 0 | Task Dependent | 2023-07-13 10:00 | 2023-07-13 10:30 |  | 20 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 10:00 | 2023-07-13 10:30 | Gran Permit Issuer | 23SD2
10798259 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4629 | ELEC | Granulation | 10798259 - 60W Elec OLL Prog CVlv 46FV29002 | 10798259 | 0020 | Inspect/Service Control Valve | 0 | Task Dependent | 2023-07-13 10:30 | 2023-07-13 13:00 |  | 23 | 2.5 | 2.5 | 2.5 | 2.5 | 0 |  |  | 2023-07-13 10:30 | 2023-07-13 13:00 | Elec 4 | 23SD2
10798259 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4629 | ELEC | Granulation | 10798259 - 60W Elec OLL Prog CVlv 46FV29002 | 10798259 | 0030 | Close Permit - 10798259 - 60W Elec OLL Prog CVlv 46FV29002 | 0 | Task Dependent | 2023-07-13 13:00 | 2023-07-13 13:30 |  | 23 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 13:00 | 2023-07-13 13:30 | Gran Permit Issuer | 23SD2
10798313 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | LUBE | Granulation | 10798313 - 15W FLAC Anls Oil Smpl GranSD GRAN | 10798313 | 0010 | Issue Permit - 10798313 - 15W FLAC Anls Oil Smpl GranSD GRAN | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 07:30 |  | 7 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 07:30 | Gran Permit Issuer | 23SD2
10798313 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | LUBE | Granulation | 10798313 - 15W FLAC Anls Oil Smpl GranSD GRAN | 10798313 | 0020 | Sample Oil | 0 | Task Dependent | 2023-07-15 07:30 | 2023-07-15 09:30 |  | 52 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-15 07:30 | 2023-07-15 09:30 | Lube | 23SD2
10798313 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | LUBE | Granulation | 10798313 - 15W FLAC Anls Oil Smpl GranSD GRAN | 10798313 | 0030 | Close Permit - 10798313 - 15W FLAC Anls Oil Smpl GranSD GRAN | 0 | Task Dependent | 2023-07-15 09:30 | 2023-07-15 10:00 |  | 52 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 09:30 | 2023-07-15 10:00 | Gran Permit Issuer | 23SD2
10798331 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.MISC | RUBBER | Granulation | 10798331 - 15W MFit Insp GranSD GRAN | 10798331 | 0010 | Issue Permit - 10798331 - 15W MFit Insp GranSD GRAN | 0 | Task Dependent | 2023-07-13 19:30 | 2023-07-13 20:00 |  | 34 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 19:30 | 2023-07-13 20:00 | Gran Permit Issuer | 23SD2
10798331 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.MISC | RUBBER | Granulation | 10798331 - 15W MFit Insp GranSD GRAN | 10798331 | 0020 | Inspect Conveyor | 0 | Task Dependent | 2023-07-13 20:00 | 2023-07-14 00:30 |  | 34 | 4.5 | 4.5 | 4.5 | 4.5 | 0 |  |  | 2023-07-13 20:00 | 2023-07-14 00:30 | Rubber | 23SD2
10798331 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.MISC | RUBBER | Granulation | 10798331 - 15W MFit Insp GranSD GRAN | 10798331 | 0030 | Close Permit - 10798331 - 15W MFit Insp GranSD GRAN | 0 | Task Dependent | 2023-07-14 00:30 | 2023-07-14 01:00 |  | 34 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 00:30 | 2023-07-14 01:00 | Gran Permit Issuer | 23SD2
10798378 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10798378 - 30W Elec Rplc Brnr Mjr GranSD Grnltn | 10798378 | 0010 | Prepare Confined space entry permit | 0 | Task Dependent | 2023-07-12 22:00 | 2023-07-13 |  | 20 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-12 22:00 | 2023-07-13 | Gran Permit Issuer | 23SD2
10798378 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10798378 - 30W Elec Rplc Brnr Mjr GranSD Grnltn | 10798378 | 0020 | Open Burner for confined space entry | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 01:30 |  | 20 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 01:30 | Fitter | 23SD2
10798378 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10798378 - 30W Elec Rplc Brnr Mjr GranSD Grnltn | 10798378 | 0030 | Perform Internal Inspection/Clean | 0 | Task Dependent | 2023-07-13 19:00 | 2023-07-13 21:00 |  | 20 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-13 19:00 | 2023-07-13 21:00 | Elec 1 | 23SD2
10798685 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10798685 - Replace Leaking Regulator | 10798685 | 0010 | Replace Leaking Regulator | 0 | Task Dependent | 2023-07-15 23:30 | 2023-07-16 01:30 |  | 17 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-15 23:30 | 2023-07-16 01:30 | Elec 1 | 23SD2
10799062 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10799062 - CMR-0009248 Install test switch | 10799062 | 0010 | Issue Permit - 10799062 - CMR-0009248 Install test switch | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 07:30 |  | 25 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 07:30 | Phos Permit Issuer | 23SD2
10799062 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10799062 - CMR-0009248 Install test switch | 10799062 | 0020 | CMR-0009248 Install test switch | 0 | Task Dependent | 2023-07-14 07:30 | 2023-07-14 13:30 |  | 25 | 6 | 6 | 6 | 6 | 0 |  |  | 2023-07-14 07:30 | 2023-07-14 13:30 | Elec 1 | 23SD2
10799062 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10799062 - CMR-0009248 Install test switch | 10799062 | 0030 | Close Permit - 10799062 - CMR-0009248 Install test switch | 0 | Task Dependent | 2023-07-14 13:30 | 2023-07-14 14:00 |  | 25 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 13:30 | 2023-07-14 14:00 | Phos Permit Issuer | 23SD2
10799063 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4420 | ELEC | Phos Acid | 10799063 - CMR-0009249 Install test switch | 10799063 | 0010 | Issue Permit - 10799063 - CMR-0009249 Install test switch | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 07:30 |  | 15 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 07:30 | Phos Permit Issuer | 23SD2
10799063 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4420 | ELEC | Phos Acid | 10799063 - CMR-0009249 Install test switch | 10799063 | 0020 | CMR-0009249 Install test switch | 0 | Task Dependent | 2023-07-15 07:30 | 2023-07-15 13:30 |  | 15 | 6 | 6 | 6 | 6 | 0 |  |  | 2023-07-15 07:30 | 2023-07-15 13:30 | Elec 3 | 23SD2
10799063 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4420 | ELEC | Phos Acid | 10799063 - CMR-0009249 Install test switch | 10799063 | 0030 | Close Permit - 10799063 - CMR-0009249 Install test switch | 0 | Task Dependent | 2023-07-15 13:30 | 2023-07-15 14:00 |  | 15 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 13:30 | 2023-07-15 14:00 | Phos Permit Issuer | 23SD2
10799528 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4440 | DAWSON1 | Phos Acid | 10799528 - 15W MFit Repr PhosSD 44CO4001 | 10799528 | 0010 | Issue Permit - 10799528 - 15W MFit Repr PhosSD 44CO4001 | 0 | Task Dependent | 2023-07-15 12:00 | 2023-07-15 12:30 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 12:00 | 2023-07-15 12:30 | Phos Permit Issuer | 23SD2
10799528 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4440 | DAWSON1 | Phos Acid | 10799528 - 15W MFit Repr PhosSD 44CO4001 | 10799528 | 0020 | Remove Sprays | 0 | Task Dependent | 2023-07-15 12:30 | 2023-07-15 16:30 |  | 0 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-15 12:30 | 2023-07-15 16:30 | Fitter | 23SD2
10799528 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4440 | DAWSON1 | Phos Acid | 10799528 - 15W MFit Repr PhosSD 44CO4001 | 10799528 | 0030 | Reinstate Sprays | 0 | Task Dependent | 2023-07-16 09:00 | 2023-07-16 13:00 |  | 11.5 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-16 09:00 | 2023-07-16 13:00 | Fitter | 23SD2
10799528 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4440 | DAWSON1 | Phos Acid | 10799528 - 15W MFit Repr PhosSD 44CO4001 | 10799528 | 0040 | Close Permit - 10799528 - 15W MFit Repr PhosSD 44CO4001 | 0 | Task Dependent | 2023-07-16 13:00 | 2023-07-16 13:30 |  | 11.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 13:00 | 2023-07-16 13:30 | Phos Permit Issuer | 23SD2
10799584 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4425 | ELEC | Phos Acid | 10799584 - 60W Elec INT Srv DrvLCU 44AR2503 | 10799584 | 0010 | Issue Permit - 10799584 - 60W Elec INT Srv DrvLCU 44AR2503 | 0 | Task Dependent | 2023-07-15 13:00 | 2023-07-15 13:30 |  | 9 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 13:00 | 2023-07-15 13:30 | Phos Permit Issuer | 23SD2
10799584 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4425 | ELEC | Phos Acid | 10799584 - 60W Elec INT Srv DrvLCU 44AR2503 | 10799584 | 0020 | Inspect/Service Drive Components | 0 | Task Dependent | 2023-07-15 13:30 | 2023-07-16 07:30 |  | 15 | 4 | 4 | 4 | 4 | 0 |  |  | 2023-07-15 13:30 | 2023-07-16 07:30 | Elec 3 | 23SD2
10799584 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4425 | ELEC | Phos Acid | 10799584 - 60W Elec INT Srv DrvLCU 44AR2503 | 10799584 | 0030 | Close Permit - 10799584 - 60W Elec INT Srv DrvLCU 44AR2503 | 0 | Task Dependent | 2023-07-16 07:30 | 2023-07-16 08:00 |  | 15 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 07:30 | 2023-07-16 08:00 | Phos Permit Issuer | 23SD2
10799622 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4625 | ENG | Granulation | 10799622 - 16W REng Insp Grnd Flr GranSD ProdClng | 10799622 | 0010 | Issue Permit - 10799622 - 16W REng Insp Grnd Flr GranSD ProdClng | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 01:00 |  | 48 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 01:00 | Gran Permit Issuer | 23SD2
10799622 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4625 | ENG | Granulation | 10799622 - 16W REng Insp Grnd Flr GranSD ProdClng | 10799622 | 0020 | Inspect Fan | 0 | Task Dependent | 2023-07-13 01:00 | 2023-07-13 02:00 |  | 48 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-13 01:00 | 2023-07-13 02:00 | Maintenance Engineer | 23SD2
10799622 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4625 | ENG | Granulation | 10799622 - 16W REng Insp Grnd Flr GranSD ProdClng | 10799622 | 0030 | Close Permit - 10799622 - 16W REng Insp Grnd Flr GranSD ProdClng | 0 | Task Dependent | 2023-07-13 02:00 | 2023-07-13 02:30 |  | 48 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 02:00 | 2023-07-13 02:30 | Gran Permit Issuer | 23SD2
10799624 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4621 | ENG | Granulation | 10799624 - 45W SEng Stat GranSD 46TK2101 | 10799624 | 0010 | Issue Permit - 10799624 - 45W SEng Stat GranSD 46TK2101 | 0 | Task Dependent | 2023-07-14 12:00 | 2023-07-14 12:30 |  | 9.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 12:00 | 2023-07-14 12:30 | Gran Permit Issuer | 23SD2
10799624 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4621 | ENG | Granulation | 10799624 - 45W SEng Stat GranSD 46TK2101 | 10799624 | 0020 | Inspect Tank Internal (CSE) | 0 | Task Dependent | 2023-07-14 12:30 | 2023-07-14 14:30 |  | 9.5 | 2 | 2 | 6 | 6 | 0 |  |  | 2023-07-14 12:30 | 2023-07-14 14:30 | T/A, Fitter, Static Engineer | 23SD2
10799624 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4621 | ENG | Granulation | 10799624 - 45W SEng Stat GranSD 46TK2101 | 10799624 | 0040 | Perform NDT (CSE) | 0 | Task Dependent | 2023-07-14 12:30 | 2023-07-15 00:30 |  | 9.5 | 10 | 10 | 40 | 40 | 0 |  |  | 2023-07-14 12:30 | 2023-07-15 00:30 | Fitter, T/A, Fitter, Static Engineer | 23SD2
10799624 - 0080 | Not Started | GLSTest-01.GRAN.MAINT.4621 | ENG | Granulation | 10799624 - 45W SEng Stat GranSD 46TK2101 | 10799624 | 0080 | Close Permit - 10799624 - 45W SEng Stat GranSD 46TK2101 | 0 | Task Dependent | 2023-07-15 00:30 | 2023-07-15 01:00 |  | 9.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 00:30 | 2023-07-15 01:00 | Gran Permit Issuer | 23SD2
10799629 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10799629 - 60W Elec OLL Prog XVlv 46MX2201WP | 10799629 | 0010 | Issue Permit - 10799629 - 60W Elec OLL Prog XVlv 46MX2201WP | 0 | Task Dependent | 2023-07-14 08:30 | 2023-07-14 09:00 |  | 15.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 08:30 | 2023-07-14 09:00 | Gran Permit Issuer | 23SD2
10799629 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10799629 - 60W Elec OLL Prog XVlv 46MX2201WP | 10799629 | 0020 | Inspect/Service On/Off Valve | 0 | Task Dependent | 2023-07-14 09:00 | 2023-07-14 10:30 |  | 27 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-14 09:00 | 2023-07-14 10:30 | Elec 3 | 23SD2
10799629 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10799629 - 60W Elec OLL Prog XVlv 46MX2201WP | 10799629 | 0030 | Close Permit - 10799629 - 60W Elec OLL Prog XVlv 46MX2201WP | 0 | Task Dependent | 2023-07-14 10:30 | 2023-07-14 11:00 |  | 27 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 10:30 | 2023-07-14 11:00 | Gran Permit Issuer | 23SD2
10799635 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ENG | Granulation | 10799635 - 16W REng Insp Grnd Flr GranSD Scrbbng | 10799635 | 0010 | Issue Permit - 10799635 - 16W REng Insp Grnd Flr GranSD Scrbbng | 0 | Task Dependent | 2023-07-13 | 2023-07-13 00:30 |  | 55.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 | 2023-07-13 00:30 | Gran Permit Issuer | 23SD2
10799635 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ENG | Granulation | 10799635 - 16W REng Insp Grnd Flr GranSD Scrbbng | 10799635 | 0020 | Inspect Fan | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 02:00 |  | 55.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 02:00 | Maintenance Engineer | 23SD2
10799635 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ENG | Granulation | 10799635 - 16W REng Insp Grnd Flr GranSD Scrbbng | 10799635 | 0030 | Close Permit - 10799635 - 16W REng Insp Grnd Flr GranSD Scrbbng | 0 | Task Dependent | 2023-07-13 02:00 | 2023-07-13 02:30 |  | 55.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 02:00 | 2023-07-13 02:30 | Gran Permit Issuer | 23SD2
10800466 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4480 | RUBBER | Phos Acid | 10800466 - RW shuttle A rollers. | 10800466 | 0010 | Issue Permit - 10800466 - RW shuttle A rollers. | 0 | Task Dependent | 2023-07-15 10:30 | 2023-07-15 11:00 |  | 10 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 10:30 | 2023-07-15 11:00 | Phos Permit Issuer | 23SD2
10800466 - 0015 | Not Started | GLSTest-01.PHOS.MAINT.4480 | RUBBER | Phos Acid | 10800466 - RW shuttle A rollers. | 10800466 | 0015 | Cleanaway to clean under pan | 0 | Task Dependent | 2023-07-15 11:00 | 2023-07-15 23:00 |  | 10 | 10 | 10 | 30 | 30 | 0 |  |  | 2023-07-15 11:00 | 2023-07-15 23:00 | Waterblast Truck, Cleaning Ops | 23SD2
10800466 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4480 | RUBBER | Phos Acid | 10800466 - RW shuttle A rollers. | 10800466 | 0020 | RW - Replace return rollers that are bro | 0 | Task Dependent | 2023-07-16 01:00 | 2023-07-16 04:00 |  | 27.5 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-16 01:00 | 2023-07-16 04:00 | Rubber | 23SD2
10800466 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4480 | RUBBER | Phos Acid | 10800466 - RW shuttle A rollers. | 10800466 | 0030 | Close Permit - 10800466 - RW shuttle A rollers. | 0 | Task Dependent | 2023-07-16 04:00 | 2023-07-16 04:30 |  | 27.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 04:00 | 2023-07-16 04:30 | Phos Permit Issuer | 23SD2
10800473 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4420 | RUBBER | Phos Acid | 10800473 - RW Reactor feed impact rollers. | 10800473 | 0010 | Issue Permit - 10800473 - RW Reactor feed impact rollers. | 0 | Task Dependent | 2023-07-14 20:00 | 2023-07-14 20:30 |  | 45 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 20:00 | 2023-07-14 20:30 | Phos Permit Issuer | 23SD2
10800473 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4420 | RUBBER | Phos Acid | 10800473 - RW Reactor feed impact rollers. | 10800473 | 0020 | OP's to clean around tail end of conveyor | 0 | Task Dependent | 2023-07-14 20:30 | 2023-07-14 23:30 |  | 45 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-14 20:30 | 2023-07-14 23:30 | Phos Ops | 23SD2
10800473 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4420 | RUBBER | Phos Acid | 10800473 - RW Reactor feed impact rollers. | 10800473 | 0040 | RW Replace Reactor feed impact rollers. | 0 | Task Dependent | 2023-07-16 01:30 | 2023-07-16 09:30 |  | 23 | 6 | 6 | 12 | 12 | 0 |  |  | 2023-07-16 01:30 | 2023-07-16 09:30 | Rubber | 23SD2
10800473 - 0050 | Not Started | GLSTest-01.PHOS.MAINT.4420 | RUBBER | Phos Acid | 10800473 - RW Reactor feed impact rollers. | 10800473 | 0050 | Close Permit - 10800473 - RW Reactor feed impact rollers. | 0 | Task Dependent | 2023-07-16 09:30 | 2023-07-16 10:00 |  | 23 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 09:30 | 2023-07-16 10:00 | Phos Permit Issuer | 23SD2
10800865 - 0010 | Not Started | GLSTest-01.BENE.MAINT.2111 | ELEC | Beneficiation | 10800865 - EL change precision rollers jaw feed con | 10800865 | 0010 | Change precision rollers jaw feed | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 17:00 |  | 20 | 10 | 10 | 20 | 20 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 17:00 | Elec 2 | 23SD2
10800865 - 0040 | Not Started | GLSTest-01.BENE.MAINT.2111 | ELEC | Beneficiation | 10800865 - EL change precision rollers jaw feed con | 10800865 | 0040 | Franna Team Assist | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 11:00 |  | 26 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 11:00 | Rigger, Crane Operator, Franna | 23SD2
10801301 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4621 | ELEC | Granulation | 10801301 - 60W Elec OLL Prog XVlv PC2102 | 10801301 | 0010 | Issue Permit - 10801301 - 60W Elec OLL Prog XVlv PC2102 | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 07:30 |  | 23 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 07:30 | Gran Permit Issuer | 23SD2
10801301 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4621 | ELEC | Granulation | 10801301 - 60W Elec OLL Prog XVlv PC2102 | 10801301 | 0020 | Inspect/Service On/Off Valve | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 09:00 |  | 23 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 09:00 | Elec 2 | 23SD2
10801301 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4621 | ELEC | Granulation | 10801301 - 60W Elec OLL Prog XVlv PC2102 | 10801301 | 0030 | Close Permit - 10801301 - 60W Elec OLL Prog XVlv PC2102 | 0 | Task Dependent | 2023-07-13 09:00 | 2023-07-13 09:30 |  | 23 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 09:00 | 2023-07-13 09:30 | Gran Permit Issuer | 23SD2
10802381 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10802381 - 15W Elec OLL Stat Lnyd 44CB1101 | 10802381 | 0010 | Issue Permit - 10802381 - 15W Elec OLL Stat Lnyd 44CB1101 | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 07:30 |  | 26 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 07:30 | Phos Permit Issuer | 23SD2
10802381 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10802381 - 15W Elec OLL Stat Lnyd 44CB1101 | 10802381 | 0020 | Inspect/Test Belt Instrumentation. | 0 | Task Dependent | 2023-07-14 07:30 | 2023-07-14 12:30 |  | 26 | 5 | 5 | 5 | 5 | 0 |  |  | 2023-07-14 07:30 | 2023-07-14 12:30 | Elec 1 | 23SD2
10802381 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10802381 - 15W Elec OLL Stat Lnyd 44CB1101 | 10802381 | 0030 | Close Permit - 10802381 - 15W Elec OLL Stat Lnyd 44CB1101 | 0 | Task Dependent | 2023-07-14 12:30 | 2023-07-14 13:00 |  | 26 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 12:30 | 2023-07-14 13:00 | Phos Permit Issuer | 23SD2
10802408 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4626 | GRAN | Granulation | 10802408 - 15W Prod Insp GranSD PlshngCtng | 10802408 | 0010 | Inspect | 0 | Task Dependent | 2023-07-14 04:30 | 2023-07-14 07:30 |  | 29 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-14 04:30 | 2023-07-14 07:30 | Gran Ops | 23SD2
10802421 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | LUBE | Granulation | 10802421 - 15W FLAC OLL Insp Dryr 46FH2301LUB1 | 10802421 | 0010 | Issue Permit - 10802421 - 15W FLAC OLL Insp Dryr 46FH2301LUB1 | 0 | Task Dependent | 2023-07-15 09:00 | 2023-07-15 09:30 |  | 6.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 09:00 | 2023-07-15 09:30 | Gran Permit Issuer | 23SD2
10802421 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | LUBE | Granulation | 10802421 - 15W FLAC OLL Insp Dryr 46FH2301LUB1 | 10802421 | 0020 | Test spray pattern | 0 | Task Dependent | 2023-07-15 09:30 | 2023-07-15 10:00 |  | 53.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 09:30 | 2023-07-15 10:00 | Lube | 23SD2
10802421 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | LUBE | Granulation | 10802421 - 15W FLAC OLL Insp Dryr 46FH2301LUB1 | 10802421 | 0030 | Close Permit - 10802421 - 15W FLAC OLL Insp Dryr 46FH2301LUB1 | 0 | Task Dependent | 2023-07-15 10:00 | 2023-07-15 10:30 |  | 53.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 10:00 | 2023-07-15 10:30 | Gran Permit Issuer | 23SD2
10802422 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | LUBE | Granulation | 10802422 - 15W FLAC OLL Insp Grnl 46MX2201LUB1 | 10802422 | 0010 | Issue Permit - 10802422 - 15W FLAC OLL Insp Grnl 46MX2201LUB1 | 0 | Task Dependent | 2023-07-15 04:00 | 2023-07-15 04:30 |  | 9.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 04:00 | 2023-07-15 04:30 | Gran Permit Issuer | 23SD2
10802422 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | LUBE | Granulation | 10802422 - 15W FLAC OLL Insp Grnl 46MX2201LUB1 | 10802422 | 0020 | Test spray pattern | 0 | Task Dependent | 2023-07-15 04:30 | 2023-07-15 05:00 |  | 53.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 04:30 | 2023-07-15 05:00 | Lube | 23SD2
10802422 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | LUBE | Granulation | 10802422 - 15W FLAC OLL Insp Grnl 46MX2201LUB1 | 10802422 | 0030 | Close Permit - 10802422 - 15W FLAC OLL Insp Grnl 46MX2201LUB1 | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 07:30 |  | 53.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 07:30 | Gran Permit Issuer | 23SD2
10802427 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4624 | GRAN | Granulation | 10802427 - 15W Prod Insp GranSD PrdctScrnng | 10802427 | 0010 | Inspect Screens | 0 | Task Dependent | 2023-07-13 23:30 | 2023-07-14 00:30 |  | 29 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-13 23:30 | 2023-07-14 00:30 | Gran Ops | 23SD2
10802432 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4629 | GRAN | Granulation | 10802432 - 30W Prod Mont PROC GranSD NH3Systm | 10802432 | 0010 | Stroke valve to verify function | 0 | Task Dependent | 2023-07-13 21:00 | 2023-07-13 22:00 |  | 28.5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-13 21:00 | 2023-07-13 22:00 | Gran Ops | 23SD2
10802436 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4611 | ELEC | Granulation | 10802436 - 30W Elec SIS Srv UPS GRAN | 10802436 | 0010 | Inspect/Service UPS | 0 | Task Dependent | 2023-07-13 12:00 | 2023-07-13 14:30 |  | 26 | 2.5 | 2.5 | 5 | 5 | 0 |  |  | 2023-07-13 12:00 | 2023-07-13 14:30 | Contract Elec, Elec 1 | 23SD2
10802859 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4624 | DAWSON1 | Granulation | 10802859 - FI-Product screen #3 hole in panel | 10802859 | 0010 | Issue Permit - 10802859 - FI-Product screen #3 hole in panel | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 08:00 |  | 25.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 08:00 | Gran Permit Issuer | 23SD2
10802859 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4624 | DAWSON1 | Granulation | 10802859 - FI-Product screen #3 hole in panel | 10802859 | 0020 | Replace screen panel | 0 | Task Dependent | 2023-07-13 08:00 | 2023-07-13 12:00 |  | 25.5 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-13 08:00 | 2023-07-13 12:00 | Fitter | 23SD2
10802859 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4624 | DAWSON1 | Granulation | 10802859 - FI-Product screen #3 hole in panel | 10802859 | 0030 | Close Permit - 10802859 - FI-Product screen #3 hole in panel | 0 | Task Dependent | 2023-07-13 12:00 | 2023-07-13 12:30 |  | 25.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 12:00 | 2023-07-13 12:30 | Gran Permit Issuer | 23SD2
10802913 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10802913 - Scope to replace solenoid panel. | 10802913 | 0010 | Issue Permit - 10802913 - Scope to replace solenoid panel. | 0 | Task Dependent | 2023-07-14 16:30 | 2023-07-14 17:00 |  | 14 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 16:30 | 2023-07-14 17:00 | Phos Permit Issuer | 23SD2
10802913 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10802913 - Scope to replace solenoid panel. | 10802913 | 0020 | replace solenoid panel. | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 13:00 |  | 14 | 6 | 6 | 6 | 6 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 13:00 | Elec 2 | 23SD2
10802913 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10802913 - Scope to replace solenoid panel. | 10802913 | 0040 | Close Permit - 10802913 - Scope to replace solenoid panel. | 0 | Task Dependent | 2023-07-15 13:00 | 2023-07-15 13:30 |  | 14 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 13:00 | 2023-07-15 13:30 | Phos Permit Issuer | 23SD2
10803403 - 0010 | Not Started | GLSTest-01.BENE.MAINT.2132 | LUBE | Beneficiation | 10803403 - 30W FLAC Lube Trunnion BeneSD Grndg | 10803403 | 0010 | Issue Permit - 10803403 - 30W FLAC Lube Trunnion BeneSD Grndg | 0 | Task Dependent | 2023-07-15 04:30 | 2023-07-15 05:00 |  | 15 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 04:30 | 2023-07-15 05:00 | Bene Permit Issuer | 23SD2
10803403 - 0020 | Not Started | GLSTest-01.BENE.MAINT.2132 | LUBE | Beneficiation | 10803403 - 30W FLAC Lube Trunnion BeneSD Grndg | 10803403 | 0020 | Collect Sample | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 07:30 |  | 34.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 07:30 | Lube | 23SD2
10803403 - 0030 | Not Started | GLSTest-01.BENE.MAINT.2132 | LUBE | Beneficiation | 10803403 - 30W FLAC Lube Trunnion BeneSD Grndg | 10803403 | 0030 | Erect Scaffold Access | 0 | Task Dependent | 2023-07-15 07:30 | 2023-07-15 11:30 |  | 34.5 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-15 07:30 | 2023-07-15 11:30 | Scaffolder | 23SD2
10803403 - 0040 | Not Started | GLSTest-01.BENE.MAINT.2132 | LUBE | Beneficiation | 10803403 - 30W FLAC Lube Trunnion BeneSD Grndg | 10803403 | 0040 | Clean Grease | 0 | Task Dependent | 2023-07-15 11:30 | 2023-07-15 21:30 |  | 34.5 | 8 | 8 | 16 | 16 | 0 |  |  | 2023-07-15 11:30 | 2023-07-15 21:30 | T/A, Lube | 23SD2
10803403 - 0060 | Not Started | GLSTest-01.BENE.MAINT.2132 | LUBE | Beneficiation | 10803403 - 30W FLAC Lube Trunnion BeneSD Grndg | 10803403 | 0060 | Dismantle Scaffold Access | 0 | Task Dependent | 2023-07-15 21:30 | 2023-07-15 23:30 |  | 27.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-15 21:30 | 2023-07-15 23:30 | Scaffolder | 23SD2
10803403 - 0080 | Not Started | GLSTest-01.BENE.MAINT.2132 | LUBE | Beneficiation | 10803403 - 30W FLAC Lube Trunnion BeneSD Grndg | 10803403 | 0080 | Franna Lift Drums | 0 | Task Dependent | 2023-07-15 11:30 | 2023-07-15 13:30 |  | 40.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-15 11:30 | 2023-07-15 13:30 | Crane Operator, Rigger, Franna | 23SD2
10803403 - 0100 | Not Started | GLSTest-01.BENE.MAINT.2132 | LUBE | Beneficiation | 10803403 - 30W FLAC Lube Trunnion BeneSD Grndg | 10803403 | 0100 | Close Permit - 10803403 - 30W FLAC Lube Trunnion BeneSD Grndg | 0 | Task Dependent | 2023-07-15 23:30 | 2023-07-16 |  | 27.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 23:30 | 2023-07-16 | Bene Permit Issuer | 23SD2
10804308 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4440 | DAWSON1 | Phos Acid | 10804308 - 30W MFit Rplc PhosSD 44FC4001 | 10804308 | 0010 | Issue Permit - 10804308 - 30W MFit Rplc PhosSD 44FC4001 | 0 | Task Dependent | 2023-07-16 04:00 | 2023-07-16 04:30 |  | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 04:00 | 2023-07-16 04:30 | Phos Permit Issuer | 23SD2
10804308 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4440 | DAWSON1 | Phos Acid | 10804308 - 30W MFit Rplc PhosSD 44FC4001 | 10804308 | 0020 | Adjust Fan | 0 | Task Dependent | 2023-07-16 04:30 | 2023-07-16 05:00 |  | 4 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-16 04:30 | 2023-07-16 05:00 | Fitter | 23SD2
10804308 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4440 | DAWSON1 | Phos Acid | 10804308 - 30W MFit Rplc PhosSD 44FC4001 | 10804308 | 0030 | Inspect Belt Drive | 0 | Task Dependent | 2023-07-16 07:00 | 2023-07-16 08:00 |  | 4 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-16 07:00 | 2023-07-16 08:00 | Fitter | 23SD2
10804308 - 0050 | Not Started | GLSTest-01.PHOS.MAINT.4440 | DAWSON1 | Phos Acid | 10804308 - 30W MFit Rplc PhosSD 44FC4001 | 10804308 | 0050 | Close Permit - 10804308 - 30W MFit Rplc PhosSD 44FC4001 | 0 | Task Dependent | 2023-07-16 08:00 | 2023-07-16 08:30 |  | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 08:00 | 2023-07-16 08:30 | Phos Permit Issuer | 23SD2
10804479 - 0010 | Not Started | GLSTest-01.BENE.MAINT.2142 | BMW | Beneficiation | 10804479 - 60W MFit Rplc BeneSD 21TR4201 | 10804479 | 0010 | Issue Permit - 10804479 - 60W MFit Rplc BeneSD 21TR4201 | 0 | Task Dependent | 2023-07-15 19:00 | 2023-07-15 19:30 |  | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 19:00 | 2023-07-15 19:30 | Bene Permit Issuer | 23SD2
10804479 - 0030 | Not Started | GLSTest-01.BENE.MAINT.2142 | BMW | Beneficiation | 10804479 - 60W MFit Rplc BeneSD 21TR4201 | 10804479 | 0030 | Inspect Thickener | 0 | Task Dependent | 2023-07-16 00:30 | 2023-07-16 08:30 |  | 1 | 6 | 6 | 6 | 6 | 0 |  |  | 2023-07-16 00:30 | 2023-07-16 08:30 | Rotating Engineer | 23SD2
10804479 - 0040 | Not Started | GLSTest-01.BENE.MAINT.2142 | BMW | Beneficiation | 10804479 - 60W MFit Rplc BeneSD 21TR4201 | 10804479 | 0040 | Lift scaff into thickener | 0 | Task Dependent | 2023-07-15 19:30 | 2023-07-15 20:30 |  | 1 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-15 19:30 | 2023-07-15 20:30 | Rigger, Crane Operator, 55t Crane | 23SD2
10804479 - 0070 | Not Started | GLSTest-01.BENE.MAINT.2142 | BMW | Beneficiation | 10804479 - 60W MFit Rplc BeneSD 21TR4201 | 10804479 | 0070 | Erect Scaffold Access-Thickener | 0 | Task Dependent | 2023-07-15 20:30 | 2023-07-16 00:30 |  | 1 | 4 | 4 | 12 | 12 | 0 |  |  | 2023-07-15 20:30 | 2023-07-16 00:30 | Scaffolder | 23SD2
10804479 - 0150 | Not Started | GLSTest-01.BENE.MAINT.2142 | BMW | Beneficiation | 10804479 - 60W MFit Rplc BeneSD 21TR4201 | 10804479 | 0150 | Inspect and change Rake Blades | 0 | Task Dependent | 2023-07-16 00:30 | 2023-07-16 10:30 |  | 1 | 8 | 8 | 24 | 24 | 0 |  |  | 2023-07-16 00:30 | 2023-07-16 10:30 | BMW | 23SD2
10804479 - 0160 | Not Started | GLSTest-01.BENE.MAINT.2142 | BMW | Beneficiation | 10804479 - 60W MFit Rplc BeneSD 21TR4201 | 10804479 | 0160 | Dismantle Scaffold Access | 0 | Task Dependent | 2023-07-16 10:30 | 2023-07-16 14:30 |  | 1 | 4 | 4 | 12 | 12 | 0 |  |  | 2023-07-16 10:30 | 2023-07-16 14:30 | Scaffolder | 23SD2
10804479 - 0170 | Not Started | GLSTest-01.BENE.MAINT.2142 | BMW | Beneficiation | 10804479 - 60W MFit Rplc BeneSD 21TR4201 | 10804479 | 0170 | Lift out scaffold | 0 | Task Dependent | 2023-07-16 14:30 | 2023-07-16 15:30 |  | 1 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-16 14:30 | 2023-07-16 15:30 | Rigger, Crane Operator, 55t Crane | 23SD2
10804479 - 0230 | Not Started | GLSTest-01.BENE.MAINT.2142 | BMW | Beneficiation | 10804479 - 60W MFit Rplc BeneSD 21TR4201 | 10804479 | 0230 | Close Permit - 10804479 - 60W MFit Rplc BeneSD 21TR4201 | 0 | Task Dependent | 2023-07-16 15:30 | 2023-07-16 16:00 |  | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 15:30 | 2023-07-16 16:00 | Bene Permit Issuer | 23SD2
10804579 - 0010 | Not Started | GLSTest-01.BENE.MAINT.2430 | ELEC | Beneficiation | 10804579 - 30W Elec SIS Srv UPS BENE | 10804579 | 0010 | Contractor - Inspect/Service UPS | 0 | Task Dependent | 2023-07-14 22:30 | 2023-07-15 01:00 |  | 23.5 | 2.5 | 2.5 | 2.5 | 2.5 | 0 |  |  | 2023-07-14 22:30 | 2023-07-15 01:00 | Contract Elec | 23SD2
10804579 - 0020 | Not Started | GLSTest-01.BENE.MAINT.2430 | ELEC | Beneficiation | 10804579 - 30W Elec SIS Srv UPS BENE | 10804579 | 0020 | Assist - Inspect/Service UPS | 0 | Task Dependent | 2023-07-14 22:30 | 2023-07-15 00:30 |  | 24 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-14 22:30 | 2023-07-15 00:30 | Elec 2 | 23SD2
10805261 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4420 | DAWSON2 | Phos Acid | 10805261 - Rocky 1&2 Vac box seal water poor flow | 10805261 | 0010 | Issue Permit - 10805261 - Rocky 1&2 Vac box seal water poor flow | 0 | Task Dependent | 2023-07-16 08:00 | 2023-07-16 08:30 |  | 12 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 08:00 | 2023-07-16 08:30 | Phos Permit Issuer | 23SD2
10805261 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4420 | DAWSON2 | Phos Acid | 10805261 - Rocky 1&2 Vac box seal water poor flow | 10805261 | 0020 | Install tap in point to header | 0 | Task Dependent | 2023-07-16 08:30 | 2023-07-16 12:30 |  | 12 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-16 08:30 | 2023-07-16 12:30 | T/A, BMW | 23SD2
10805261 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4420 | DAWSON2 | Phos Acid | 10805261 - Rocky 1&2 Vac box seal water poor flow | 10805261 | 0040 | Remove old pipework | 0 | Task Dependent | 2023-07-16 08:30 | 2023-07-16 11:30 |  | 12 | 3 | 3 | 9 | 9 | 0 |  |  | 2023-07-16 08:30 | 2023-07-16 11:30 | 19ft Elec Scissor Lift, Fitter | 23SD2
10805261 - 0050 | Not Started | GLSTest-01.PHOS.MAINT.4420 | DAWSON2 | Phos Acid | 10805261 - Rocky 1&2 Vac box seal water poor flow | 10805261 | 0050 | Install new pipework | 0 | Task Dependent | 2023-07-16 11:30 | 2023-07-16 20:30 |  | 12 | 7 | 7 | 21 | 21 | 0 |  |  | 2023-07-16 11:30 | 2023-07-16 20:30 | 19ft Elec Scissor Lift, Fitter | 23SD2
10805261 - 0060 | Not Started | GLSTest-01.PHOS.MAINT.4420 | DAWSON2 | Phos Acid | 10805261 - Rocky 1&2 Vac box seal water poor flow | 10805261 | 0060 | Close Permit - 10805261 - Rocky 1&2 Vac box seal water poor flow | 0 | Task Dependent | 2023-07-16 20:30 | 2023-07-16 21:00 |  | 12 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 20:30 | 2023-07-16 21:00 | Phos Permit Issuer | 23SD2
10806534 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4911 | ELEC | Granulation | 10806534 - 3M Elec Insp ISO Product Tripper Cnv | 10806534 | 0010 | 3M Elec Insp Product Tripper CV Isol | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 07:42 |  | 28.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 07:42 | Projects Elec | 23SD2
10806644 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4440 | ENG | Phos Acid | 10806644 - 15W REng Insp PhosSD 44FC4002 | 10806644 | 0010 | Inspect Fan | 0 | Task Dependent | 2023-07-16 04:30 | 2023-07-16 05:00 |  | 17.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 04:30 | 2023-07-16 05:00 | Rotating Engineer | 23SD2
10806645 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4440 | ENG | Phos Acid | 10806645 - 15W REng Insp PhosSD 44FC4001 | 10806645 | 0010 | Inspect Fan | 0 | Task Dependent | 2023-07-15 03:30 | 2023-07-15 04:00 |  | 38.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 03:30 | 2023-07-15 04:00 | Maintenance Engineer | 23SD2
10806701 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4480 | ELEC | Phos Acid | 10806701 - 30W Elec INT Srv DrvLCU 44CB8003 | 10806701 | 0010 | Issue Permit - 10806701 - 30W Elec INT Srv DrvLCU 44CB8003 | 0 | Task Dependent | 2023-07-15 09:00 | 2023-07-15 09:30 |  | 17.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 09:00 | 2023-07-15 09:30 | Phos Permit Issuer | 23SD2
10806701 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4480 | ELEC | Phos Acid | 10806701 - 30W Elec INT Srv DrvLCU 44CB8003 | 10806701 | 0020 | Inspect/Service Drive Components | 0 | Task Dependent | 2023-07-15 09:30 | 2023-07-15 11:00 |  | 17.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-15 09:30 | 2023-07-15 11:00 | Elec 4 | 23SD2
10806701 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4480 | ELEC | Phos Acid | 10806701 - 30W Elec INT Srv DrvLCU 44CB8003 | 10806701 | 0030 | Close Permit - 10806701 - 30W Elec INT Srv DrvLCU 44CB8003 | 0 | Task Dependent | 2023-07-15 11:00 | 2023-07-15 11:30 |  | 17.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 11:00 | 2023-07-15 11:30 | Phos Permit Issuer | 23SD2
10806706 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10806706 - 60W Elec INT Srv DrvLCU 44AR1201 | 10806706 | 0010 | Issue Permit - 10806706 - 60W Elec INT Srv DrvLCU 44AR1201 | 0 | Task Dependent | 2023-07-14 19:00 | 2023-07-14 19:30 |  | 26.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 19:00 | 2023-07-14 19:30 | Phos Permit Issuer | 23SD2
10806706 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10806706 - 60W Elec INT Srv DrvLCU 44AR1201 | 10806706 | 0020 | Inspect/Service Drive Components | 0 | Task Dependent | 2023-07-14 19:30 | 2023-07-14 22:00 |  | 26.5 | 2.5 | 2.5 | 2.5 | 2.5 | 0 |  |  | 2023-07-14 19:30 | 2023-07-14 22:00 | Elec 2 | 23SD2
10806706 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10806706 - 60W Elec INT Srv DrvLCU 44AR1201 | 10806706 | 0030 | Close Permit - 10806706 - 60W Elec INT Srv DrvLCU 44AR1201 | 0 | Task Dependent | 2023-07-14 22:00 | 2023-07-14 22:30 |  | 26.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 22:00 | 2023-07-14 22:30 | Phos Permit Issuer | 23SD2
10806806 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10806806 - 15W Elec OLL Prog Wghr 48WIT11001 | 10806806 | 0010 | Issue Permit - 10806806 - 15W Elec OLL Prog Wghr 48WIT11001 | 0 | Task Dependent | 2023-07-14 19:00 | 2023-07-14 19:30 |  | 27 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 19:00 | 2023-07-14 19:30 | Phos Permit Issuer | 23SD2
10806806 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10806806 - 15W Elec OLL Prog Wghr 48WIT11001 | 10806806 | 0020 | Inspect/Service Belt Weigher | 0 | Task Dependent | 2023-07-14 19:30 | 2023-07-14 21:30 |  | 27 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-14 19:30 | 2023-07-14 21:30 | Elec 1 | 23SD2
10806806 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10806806 - 15W Elec OLL Prog Wghr 48WIT11001 | 10806806 | 0030 | Close Permit - 10806806 - 15W Elec OLL Prog Wghr 48WIT11001 | 0 | Task Dependent | 2023-07-14 21:30 | 2023-07-14 22:00 |  | 27 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 21:30 | 2023-07-14 22:00 | Phos Permit Issuer | 23SD2
10806807 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10806807 - 15W Elec INT Prog Wghr 48WIT11001 | 10806807 | 0010 | Issue Permit - 10806807 - 15W Elec INT Prog Wghr 48WIT11001 | 0 | Task Dependent | 2023-07-14 19:00 | 2023-07-14 19:30 |  | 28 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 19:00 | 2023-07-14 19:30 | Phos Permit Issuer | 23SD2
10806807 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10806807 - 15W Elec INT Prog Wghr 48WIT11001 | 10806807 | 0020 | Inspect/Service Belt Weigher | 0 | Task Dependent | 2023-07-14 19:30 | 2023-07-14 20:30 |  | 28 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-14 19:30 | 2023-07-14 20:30 | Elec 1 | 23SD2
10806807 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10806807 - 15W Elec INT Prog Wghr 48WIT11001 | 10806807 | 0030 | Close Permit - 10806807 - 15W Elec INT Prog Wghr 48WIT11001 | 0 | Task Dependent | 2023-07-14 20:30 | 2023-07-14 21:00 |  | 28 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 20:30 | 2023-07-14 21:00 | Phos Permit Issuer | 23SD2
10807389 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4410 | ELEC | Phos Acid | 10807389 - Replace cable, include service loop | 10807389 | 0010 | Replace cable, include service loop | 0 | Task Dependent | 2023-07-16 01:30 | 2023-07-16 19:30 |  | 22 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-16 01:30 | 2023-07-16 19:30 | Elec 3 | 23SD2
10807417 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4480 | ELEC | Phos Acid | 10807417 - Install Cable labels | 10807417 | 0010 | Install Cable labels | 0 | Task Dependent | 2023-07-16 01:30 | 2023-07-16 19:30 |  | 9 | 4 | 4 | 4 | 4 | 0 |  |  | 2023-07-16 01:30 | 2023-07-16 19:30 | Elec 1 | 23SD2
10807421 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10807421 - MOD - Granulator Starter A/B Interlock | 10807421 | 0010 | MOD - Granulator Starter A/B Interlock | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-14 07:30 |  | 17 | 10 | 10 | 10 | 10 | 0 |  |  | 2023-07-13 07:30 | 2023-07-14 07:30 | Elec 3 | 23SD2
10807421 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10807421 - MOD - Granulator Starter A/B Interlock | 10807421 | 0020 | Comission | 0 | Task Dependent | 2023-07-14 07:30 | 2023-07-14 09:00 |  | 17 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-14 07:30 | 2023-07-14 09:00 | Elec 3 | 23SD2
10807558 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4485 | BMW | Phos Acid | 10807558 - Install gaurding on overland conveyor. | 10807558 | 0010 | Walk down job & issue permit | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 07:30 |  | 63.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 07:30 | Phos Permit Issuer | 23SD2
10807558 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4485 | BMW | Phos Acid | 10807558 - Install gaurding on overland conveyor. | 10807558 | 0020 | Install gaurding on overland conveyor. | 0 | Task Dependent | 2023-07-14 07:30 | 2023-07-14 09:30 |  | 63.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-14 07:30 | 2023-07-14 09:30 | BMW | 23SD2
10807558 - 0070 | Not Started | GLSTest-01.PHOS.MAINT.4485 | BMW | Phos Acid | 10807558 - Install gaurding on overland conveyor. | 10807558 | 0070 | Walk down job & close out permit. | 0 | Task Dependent | 2023-07-14 09:30 | 2023-07-14 10:00 |  | 63.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 09:30 | 2023-07-14 10:00 | Phos Permit Issuer | 23SD2
10807989 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4623 | RUBBER | Granulation | 10807989 - 30W MFit Rplc TrckngRlrs GranSD 46CB2401 | 10807989 | 0010 | Issue Permit - 10807989 - 30W MFit Rplc TrckngRlrs GranSD 46CB2401 | 0 | Task Dependent | 2023-07-13 09:00 | 2023-07-13 09:30 |  | 43 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 09:00 | 2023-07-13 09:30 | Gran Permit Issuer | 23SD2
10807989 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4623 | RUBBER | Granulation | 10807989 - 30W MFit Rplc TrckngRlrs GranSD 46CB2401 | 10807989 | 0020 | Replace tracking rollers | 0 | Task Dependent | 2023-07-13 09:30 | 2023-07-13 13:30 |  | 43 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-13 09:30 | 2023-07-13 13:30 | T/A, Rubber | 23SD2
10807989 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4623 | RUBBER | Granulation | 10807989 - 30W MFit Rplc TrckngRlrs GranSD 46CB2401 | 10807989 | 0040 | Close Permit - 10807989 - 30W MFit Rplc TrckngRlrs GranSD 46CB2401 | 0 | Task Dependent | 2023-07-13 13:30 | 2023-07-13 14:00 |  | 43 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 13:30 | 2023-07-13 14:00 | Gran Permit Issuer | 23SD2
10807995 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4629 | GRAN | Granulation | 10807995 - 15W Prod Rplc GranSD CE0001 | 10807995 | 0010 | Remove Chiller Bags | 0 | Task Dependent | 2023-07-13 03:00 | 2023-07-13 06:00 |  | 14 | 3 | 3 | 9 | 9 | 0 |  |  | 2023-07-13 03:00 | 2023-07-13 06:00 | Gran Ops | 23SD2
10808067 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4480 | ELEC | Phos Acid | 10808067 - 15W Elec OLL Stat Lnyd 44CB8001 | 10808067 | 0010 | Issue Permit - 10808067 - 15W Elec OLL Stat Lnyd 44CB8001 | 0 | Task Dependent | 2023-07-16 07:00 | 2023-07-16 07:30 |  | 9.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 07:00 | 2023-07-16 07:30 | Phos Permit Issuer | 23SD2
10808067 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4480 | ELEC | Phos Acid | 10808067 - 15W Elec OLL Stat Lnyd 44CB8001 | 10808067 | 0020 | Inspect/Test Belt Instrumentation. | 0 | Task Dependent | 2023-07-16 07:30 | 2023-07-16 09:00 |  | 9.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-16 07:30 | 2023-07-16 09:00 | Elec 4 | 23SD2
10808067 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4480 | ELEC | Phos Acid | 10808067 - 15W Elec OLL Stat Lnyd 44CB8001 | 10808067 | 0030 | Close Permit - 10808067 - 15W Elec OLL Stat Lnyd 44CB8001 | 0 | Task Dependent | 2023-07-16 09:00 | 2023-07-16 09:30 |  | 9.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 09:00 | 2023-07-16 09:30 | Phos Permit Issuer | 23SD2
10808068 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4480 | ELEC | Phos Acid | 10808068 - 15W Elec OLL Stat Lnyd 44CB8003 | 10808068 | 0010 | Issue Permit - 10808068 - 15W Elec OLL Stat Lnyd 44CB8003 | 0 | Task Dependent | 2023-07-15 09:00 | 2023-07-15 09:30 |  | 17.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 09:00 | 2023-07-15 09:30 | Phos Permit Issuer | 23SD2
10808068 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4480 | ELEC | Phos Acid | 10808068 - 15W Elec OLL Stat Lnyd 44CB8003 | 10808068 | 0020 | Inspect/Test Belt Instrumentation. | 0 | Task Dependent | 2023-07-15 09:30 | 2023-07-15 11:00 |  | 17.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-15 09:30 | 2023-07-15 11:00 | Elec 4 | 23SD2
10808068 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4480 | ELEC | Phos Acid | 10808068 - 15W Elec OLL Stat Lnyd 44CB8003 | 10808068 | 0030 | Close Permit - 10808068 - 15W Elec OLL Stat Lnyd 44CB8003 | 0 | Task Dependent | 2023-07-15 11:00 | 2023-07-15 11:30 |  | 17.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 11:00 | 2023-07-15 11:30 | Phos Permit Issuer | 23SD2
10808072 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4420 | ELEC | Phos Acid | 10808072 - 15W Elec OLL Prog Wghr 41WIT20001 | 10808072 | 0010 | Issue Permit - 10808072 - 15W Elec OLL Prog Wghr 41WIT20001 | 0 | Task Dependent | 2023-07-16 07:00 | 2023-07-16 07:30 |  | 9 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 07:00 | 2023-07-16 07:30 | Phos Permit Issuer | 23SD2
10808072 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4420 | ELEC | Phos Acid | 10808072 - 15W Elec OLL Prog Wghr 41WIT20001 | 10808072 | 0020 | Inspect/Service Belt Weigher | 0 | Task Dependent | 2023-07-16 07:30 | 2023-07-16 09:30 |  | 19 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-16 07:30 | 2023-07-16 09:30 | Elec 3 | 23SD2
10808072 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4420 | ELEC | Phos Acid | 10808072 - 15W Elec OLL Prog Wghr 41WIT20001 | 10808072 | 0030 | Close Permit - 10808072 - 15W Elec OLL Prog Wghr 41WIT20001 | 0 | Task Dependent | 2023-07-16 09:30 | 2023-07-16 10:00 |  | 19 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 09:30 | 2023-07-16 10:00 | Phos Permit Issuer | 23SD2
10808073 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4420 | ELEC | Phos Acid | 10808073 - 15W Elec INT Prog Wghr 41WIT20001 | 10808073 | 0010 | Issue Permit - 10808073 - 15W Elec INT Prog Wghr 41WIT20001 | 0 | Task Dependent | 2023-07-16 10:00 | 2023-07-16 10:30 |  | 7 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 10:00 | 2023-07-16 10:30 | Phos Permit Issuer | 23SD2
10808073 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4420 | ELEC | Phos Acid | 10808073 - 15W Elec INT Prog Wghr 41WIT20001 | 10808073 | 0020 | Inspect/Service Belt Weigher | 0 | Task Dependent | 2023-07-16 10:30 | 2023-07-16 11:30 |  | 20 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-16 10:30 | 2023-07-16 11:30 | Elec 3 | 23SD2
10808073 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4420 | ELEC | Phos Acid | 10808073 - 15W Elec INT Prog Wghr 41WIT20001 | 10808073 | 0030 | Close Permit - 10808073 - 15W Elec INT Prog Wghr 41WIT20001 | 0 | Task Dependent | 2023-07-16 11:30 | 2023-07-16 12:00 |  | 20 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 11:30 | 2023-07-16 12:00 | Phos Permit Issuer | 23SD2
10808074 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4420 | ELEC | Phos Acid | 10808074 - 15W Elec OLL Stat Lnyd 44CB2001 | 10808074 | 0010 | Issue Permit - 10808074 - 15W Elec OLL Stat Lnyd 44CB2001 | 0 | Task Dependent | 2023-07-16 09:00 | 2023-07-16 09:30 |  | 7.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 09:00 | 2023-07-16 09:30 | Phos Permit Issuer | 23SD2
10808074 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4420 | ELEC | Phos Acid | 10808074 - 15W Elec OLL Stat Lnyd 44CB2001 | 10808074 | 0020 | Inspect/Test Belt Instrumentation. | 0 | Task Dependent | 2023-07-16 09:30 | 2023-07-16 11:00 |  | 19.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-16 09:30 | 2023-07-16 11:00 | Elec 3 | 23SD2
10808074 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4420 | ELEC | Phos Acid | 10808074 - 15W Elec OLL Stat Lnyd 44CB2001 | 10808074 | 0030 | Close Permit - 10808074 - 15W Elec OLL Stat Lnyd 44CB2001 | 0 | Task Dependent | 2023-07-16 11:00 | 2023-07-16 11:30 |  | 19.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 11:00 | 2023-07-16 11:30 | Phos Permit Issuer | 23SD2
10808087 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4425 | ELEC | Phos Acid | 10808087 - 75W Elec INT Prog DrvVTM 44XV2503 | 10808087 | 0010 | Issue Permit - 10808087 - 75W Elec INT Prog DrvVTM 44XV2503 | 0 | Task Dependent | 2023-07-14 20:30 | 2023-07-14 21:00 |  | 24.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 20:30 | 2023-07-14 21:00 | Phos Permit Issuer | 23SD2
10808087 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4425 | ELEC | Phos Acid | 10808087 - 75W Elec INT Prog DrvVTM 44XV2503 | 10808087 | 0020 | Inspect/Service VTM Actuator | 0 | Task Dependent | 2023-07-14 21:00 | 2023-07-15 |  | 24.5 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-14 21:00 | 2023-07-15 | 60ft EWP, Elec 1 | 23SD2
10808087 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4425 | ELEC | Phos Acid | 10808087 - 75W Elec INT Prog DrvVTM 44XV2503 | 10808087 | 0040 | Close Permit - 10808087 - 75W Elec INT Prog DrvVTM 44XV2503 | 0 | Task Dependent | 2023-07-15 | 2023-07-15 00:30 |  | 24.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 | 2023-07-15 00:30 | Phos Permit Issuer | 23SD2
10808098 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4438 | ELEC | Phos Acid | 10808098 - 120W Elec OLL Prog CVlv 44TK3806 | 10808098 | 0010 | Issue Permit - 10808098 - 120W Elec OLL Prog CVlv 44TK3806 | 0 | Task Dependent | 2023-07-14 22:00 | 2023-07-14 22:30 |  | 18 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 22:00 | 2023-07-14 22:30 | Phos Permit Issuer | 23SD2
10808098 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4438 | ELEC | Phos Acid | 10808098 - 120W Elec OLL Prog CVlv 44TK3806 | 10808098 | 0020 | Inspect/Service Control Valve | 0 | Task Dependent | 2023-07-14 22:30 | 2023-07-15 20:30 |  | 18 | 8 | 8 | 8 | 8 | 0 |  |  | 2023-07-14 22:30 | 2023-07-15 20:30 | Elec 1 | 23SD2
10808098 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4438 | ELEC | Phos Acid | 10808098 - 120W Elec OLL Prog CVlv 44TK3806 | 10808098 | 0030 | EWP - 45ft | 0 | Task Dependent | 2023-07-14 22:30 | 2023-07-15 00:30 |  | 24 | 2 | 2 | 0 | 0 | 0 |  |  | 2023-07-14 22:30 | 2023-07-15 00:30 | 45ft EWP | 23SD2
10808098 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4438 | ELEC | Phos Acid | 10808098 - 120W Elec OLL Prog CVlv 44TK3806 | 10808098 | 0040 | Close Permit - 10808098 - 120W Elec OLL Prog CVlv 44TK3806 | 0 | Task Dependent | 2023-07-15 20:30 | 2023-07-15 21:00 |  | 18 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 20:30 | 2023-07-15 21:00 | Phos Permit Issuer | 23SD2
10808099 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4438 | ELEC | Phos Acid | 10808099 - 120W Elec OLL Prog CVlv 44TK3807 | 10808099 | 0010 | Issue Permit - 10808099 - 120W Elec OLL Prog CVlv 44TK3807 | 0 | Task Dependent | 2023-07-14 22:00 | 2023-07-14 22:30 |  | 22 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 22:00 | 2023-07-14 22:30 | Phos Permit Issuer | 23SD2
10808099 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4438 | ELEC | Phos Acid | 10808099 - 120W Elec OLL Prog CVlv 44TK3807 | 10808099 | 0020 | Inspect/Service Control Valve | 0 | Task Dependent | 2023-07-14 22:30 | 2023-07-15 02:30 |  | 22 | 4 | 4 | 4 | 4 | 0 |  |  | 2023-07-14 22:30 | 2023-07-15 02:30 | Elec 1 | 23SD2
10808099 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4438 | ELEC | Phos Acid | 10808099 - 120W Elec OLL Prog CVlv 44TK3807 | 10808099 | 0030 | Close Permit - 10808099 - 120W Elec OLL Prog CVlv 44TK3807 | 0 | Task Dependent | 2023-07-15 02:30 | 2023-07-15 03:00 |  | 22 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 02:30 | 2023-07-15 03:00 | Phos Permit Issuer | 23SD2
10808637 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4485 | DAWSON3 | Phos Acid | 10808637 - Replace Luki Spacer Plates with SS | 10808637 | 0010 | Issue Permit - 10808637 - Replace Luki Spacer Plates with SS | 0 | Task Dependent | 2023-07-14 22:30 | 2023-07-14 23:00 |  | 18 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 22:30 | 2023-07-14 23:00 | Phos Permit Issuer | 23SD2
10808637 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4485 | DAWSON3 | Phos Acid | 10808637 - Replace Luki Spacer Plates with SS | 10808637 | 0020 | Remove valve bolts | 0 | Task Dependent | 2023-07-14 23:00 | 2023-07-15 02:00 |  | 18 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-14 23:00 | 2023-07-15 02:00 | Fitter | 23SD2
10808637 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4485 | DAWSON3 | Phos Acid | 10808637 - Replace Luki Spacer Plates with SS | 10808637 | 0030 | Remove valve & transport to w/shop | 0 | Task Dependent | 2023-07-14 23:00 | 2023-07-15 01:00 |  | 25 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-14 23:00 | 2023-07-15 01:00 | Rigger, Crane Operator, Franna | 23SD2
10808637 - 0060 | Not Started | GLSTest-01.PHOS.MAINT.4485 | DAWSON3 | Phos Acid | 10808637 - Replace Luki Spacer Plates with SS | 10808637 | 0060 | Replace spacer plate | 0 | Task Dependent | 2023-07-15 09:00 | 2023-07-15 12:30 |  | 19 | 3.5 | 3.5 | 7 | 7 | 0 |  |  | 2023-07-15 09:00 | 2023-07-15 12:30 | Fitter | 23SD2
10808637 - 0080 | Not Started | GLSTest-01.PHOS.MAINT.4485 | DAWSON3 | Phos Acid | 10808637 - Replace Luki Spacer Plates with SS | 10808637 | 0080 | Transport valve to jobsite & re-install | 0 | Task Dependent | 2023-07-15 12:30 | 2023-07-15 14:30 |  | 19 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-15 12:30 | 2023-07-15 14:30 | Rigger, Crane Operator, Franna | 23SD2
10808637 - 0110 | Not Started | GLSTest-01.PHOS.MAINT.4485 | DAWSON3 | Phos Acid | 10808637 - Replace Luki Spacer Plates with SS | 10808637 | 0110 | Re-instate all bolts | 0 | Task Dependent | 2023-07-15 12:30 | 2023-07-15 16:30 |  | 19 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-15 12:30 | 2023-07-15 16:30 | Fitter | 23SD2
10808637 - 0120 | Not Started | GLSTest-01.PHOS.MAINT.4485 | DAWSON3 | Phos Acid | 10808637 - Replace Luki Spacer Plates with SS | 10808637 | 0120 | Close Permit - 10808637 - Replace Luki Spacer Plates with SS | 0 | Task Dependent | 2023-07-15 16:30 | 2023-07-15 17:00 |  | 19 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 16:30 | 2023-07-15 17:00 | Phos Permit Issuer | 23SD2
10808958 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10808958 - 15W Elec INT Rplc Wghr 46WIT24001 | 10808958 | 0010 | Issue Permit - 10808958 - 15W Elec INT Rplc Wghr 46WIT24001 | 0 | Task Dependent | 2023-07-13 21:00 | 2023-07-13 21:30 |  | 16.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 21:00 | 2023-07-13 21:30 | Gran Permit Issuer | 23SD2
10808958 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10808958 - 15W Elec INT Rplc Wghr 46WIT24001 | 10808958 | 0020 | Inspect/Service Belt Weigher | 0 | Task Dependent | 2023-07-13 21:30 | 2023-07-13 22:00 |  | 23.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 21:30 | 2023-07-13 22:00 | Elec 3 | 23SD2
10808958 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4623 | ELEC | Granulation | 10808958 - 15W Elec INT Rplc Wghr 46WIT24001 | 10808958 | 0030 | Close Permit - 10808958 - 15W Elec INT Rplc Wghr 46WIT24001 | 0 | Task Dependent | 2023-07-13 22:00 | 2023-07-13 22:30 |  | 23.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 22:00 | 2023-07-13 22:30 | Gran Permit Issuer | 23SD2
10809655 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4485 | DAWSON3 | Phos Acid | 10809655 - FI- Valve not functional | 10809655 | 0010 | Remove Valve | 0 | Task Dependent | 2023-07-15 02:30 | 2023-07-15 04:30 |  | 19 | 2 | 2 | 6 | 6 | 0 |  |  | 2023-07-15 02:30 | 2023-07-15 04:30 | Fitter | 23SD2
10809655 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4485 | DAWSON3 | Phos Acid | 10809655 - FI- Valve not functional | 10809655 | 0030 | Franna Team Assist Remove Valve | 0 | Task Dependent | 2023-07-15 02:30 | 2023-07-15 03:30 |  | 20 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-15 02:30 | 2023-07-15 03:30 | Rigger, Franna, Crane Operator | 23SD2
10809655 - 0050 | Not Started | GLSTest-01.PHOS.MAINT.4485 | DAWSON3 | Phos Acid | 10809655 - FI- Valve not functional | 10809655 | 0050 | Reinstate Valve | 0 | Task Dependent | 2023-07-15 04:30 | 2023-07-15 08:30 |  | 19 | 2 | 2 | 6 | 6 | 0 |  |  | 2023-07-15 04:30 | 2023-07-15 08:30 | Fitter | 23SD2
10809655 - 0070 | Not Started | GLSTest-01.PHOS.MAINT.4485 | DAWSON3 | Phos Acid | 10809655 - FI- Valve not functional | 10809655 | 0070 | Franna Team Assist Reinstate Valve | 0 | Task Dependent | 2023-07-15 04:30 | 2023-07-15 07:30 |  | 20 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-15 04:30 | 2023-07-15 07:30 | Rigger, Franna, Crane Operator | 23SD2
10809921 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10809921 - 15W Elec OLL Stat Lnyd CB2301 | 10809921 | 0010 | Issue Permit - 10809921 - 15W Elec OLL Stat Lnyd CB2301 | 0 | Task Dependent | 2023-07-13 15:00 | 2023-07-13 15:30 |  | 19.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 15:00 | 2023-07-13 15:30 | Gran Permit Issuer | 23SD2
10809921 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10809921 - 15W Elec OLL Stat Lnyd CB2301 | 10809921 | 0020 | Inspect/Test Belt Instrumentation. | 0 | Task Dependent | 2023-07-13 15:30 | 2023-07-13 16:30 |  | 27.5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-13 15:30 | 2023-07-13 16:30 | Elec 1 | 23SD2
10809921 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10809921 - 15W Elec OLL Stat Lnyd CB2301 | 10809921 | 0030 | Close Permit - 10809921 - 15W Elec OLL Stat Lnyd CB2301 | 0 | Task Dependent | 2023-07-13 16:30 | 2023-07-13 17:00 |  | 27.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 16:30 | 2023-07-13 17:00 | Gran Permit Issuer | 23SD2
10810277 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | PROJECT | Granulation | 10810277 - Installation of Chute Nozzles | 10810277 | 0020 | Issue Permit - 10810277 - Installation of Chute Nozzles | 0 | Task Dependent | 2023-07-13 19:30 | 2023-07-13 20:00 |  | 9 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 19:30 | 2023-07-13 20:00 | Phos Permit Issuer | 23SD2
10810277 - 0110 | Not Started | GLSTest-01.GRAN.MAINT.4622 | PROJECT | Granulation | 10810277 - Installation of Chute Nozzles | 10810277 | 0110 | Close Permit - 10810277 - Installation of Chute Nozzles | 0 | Task Dependent | 2023-07-15 04:00 | 2023-07-15 04:30 |  | 9 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 04:00 | 2023-07-15 04:30 | Phos Permit Issuer | 23SD2
10810294 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4485 | RUBBER | Phos Acid | 10810294 - RW overlander replace tracking frame | 10810294 | 0010 | RW overlander replace tracking frame | 0 | Task Dependent | 2023-07-14 07:30 | 2023-07-14 11:30 |  | 61.5 | 4 | 4 | 4 | 4 | 0 |  |  | 2023-07-14 07:30 | 2023-07-14 11:30 | Rubber | 23SD2
10810294 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4485 | RUBBER | Phos Acid | 10810294 - RW overlander replace tracking frame | 10810294 | 0030 | Franna Team Assist with Frame | 0 | Task Dependent | 2023-07-14 07:30 | 2023-07-14 08:30 |  | 64.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-14 07:30 | 2023-07-14 08:30 | Rigger, Franna, Crane Operator | 23SD2
10810886 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4485 | RUBBER | Phos Acid | 10810886 - 15W MFit Rplc PhosSD 44CB1101 | 10810886 | 0010 | Issue Permit - 10810886 - 15W MFit Rplc PhosSD 44CB1101 | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 07:30 |  | 49.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 07:30 | Phos Permit Issuer | 23SD2
10810886 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4485 | RUBBER | Phos Acid | 10810886 - 15W MFit Rplc PhosSD 44CB1101 | 10810886 | 0020 | 15W Mech Insp Overland Conveyor Shut | 0 | Task Dependent | 2023-07-14 07:30 | 2023-07-14 12:30 |  | 49.5 | 5 | 5 | 10 | 10 | 0 |  |  | 2023-07-14 07:30 | 2023-07-14 12:30 | Rubber | 23SD2
10810886 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4485 | RUBBER | Phos Acid | 10810886 - 15W MFit Rplc PhosSD 44CB1101 | 10810886 | 0030 | 15W Mech Rplc Overland Cv Scrapers Shut | 0 | Task Dependent | 2023-07-14 12:30 | 2023-07-14 20:30 |  | 49.5 | 6 | 6 | 12 | 12 | 0 |  |  | 2023-07-14 12:30 | 2023-07-14 20:30 | Rubber | 23SD2
10810886 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4485 | RUBBER | Phos Acid | 10810886 - 15W MFit Rplc PhosSD 44CB1101 | 10810886 | 0040 | 15W Mech Rplc Overland Cv Rollers Shut | 0 | Task Dependent | 2023-07-14 20:30 | 2023-07-15 01:30 |  | 49.5 | 5 | 5 | 20 | 20 | 0 |  |  | 2023-07-14 20:30 | 2023-07-15 01:30 | 80ft EWP, Rubber | 23SD2
10810886 - 0060 | Not Started | GLSTest-01.PHOS.MAINT.4485 | RUBBER | Phos Acid | 10810886 - 15W MFit Rplc PhosSD 44CB1101 | 10810886 | 0060 | Close Permit - 10810886 - 15W MFit Rplc PhosSD 44CB1101 | 0 | Task Dependent | 2023-07-15 01:30 | 2023-07-15 02:00 |  | 49.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 01:30 | 2023-07-15 02:00 | Phos Permit Issuer | 23SD2
10811344 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4425 | RUBBER | Phos Acid | 10811344 - Spray bar holed | 10811344 | 0010 | Issue Permit - 10811344 - Spray bar holed | 0 | Task Dependent | 2023-07-16 12:00 | 2023-07-16 12:30 |  | 15 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 12:00 | 2023-07-16 12:30 | Phos Permit Issuer | 23SD2
10811344 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4425 | RUBBER | Phos Acid | 10811344 - Spray bar holed | 10811344 | 0020 | Remove old spray bar | 0 | Task Dependent | 2023-07-16 12:30 | 2023-07-16 14:00 |  | 15 | 1.5 | 1.5 | 3 | 3 | 0 |  |  | 2023-07-16 12:30 | 2023-07-16 14:00 | Rubber | 23SD2
10811344 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4425 | RUBBER | Phos Acid | 10811344 - Spray bar holed | 10811344 | 0030 | Fabricate new spray bar | 0 | Task Dependent | 2023-07-16 14:00 | 2023-07-16 16:00 |  | 15 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-16 14:00 | 2023-07-16 16:00 | Rubber | 23SD2
10811344 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4425 | RUBBER | Phos Acid | 10811344 - Spray bar holed | 10811344 | 0040 | Install new spray bar | 0 | Task Dependent | 2023-07-16 16:00 | 2023-07-16 19:30 |  | 15 | 1.5 | 1.5 | 3 | 3 | 0 |  |  | 2023-07-16 16:00 | 2023-07-16 19:30 | Rubber | 23SD2
10811344 - 0050 | Not Started | GLSTest-01.PHOS.MAINT.4425 | RUBBER | Phos Acid | 10811344 - Spray bar holed | 10811344 | 0050 | Close Permit - 10811344 - Spray bar holed | 0 | Task Dependent | 2023-07-16 19:30 | 2023-07-16 20:00 |  | 15 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 19:30 | 2023-07-16 20:00 | Phos Permit Issuer | 23SD2
10811732 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4480 | DAWSON2 | Phos Acid | 10811732 - Hazards from excessive chute blockages | 10811732 | 0030 | Franna Team Assist Scaffold Build | 0 | Task Dependent | 2023-07-15 03:00 | 2023-07-15 04:00 |  | 10 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-15 03:00 | 2023-07-15 04:00 | Crane Operator, Rigger, Franna | 23SD2
10811732 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4480 | DAWSON2 | Phos Acid | 10811732 - Hazards from excessive chute blockages | 10811732 | 0040 | Erect Scaffold Access | 0 | Task Dependent | 2023-07-15 03:00 | 2023-07-15 11:00 |  | 10 | 6 | 6 | 12 | 12 | 0 |  |  | 2023-07-15 03:00 | 2023-07-15 11:00 | Scaffolder | 23SD2
10811732 - 0050 | Not Started | GLSTest-01.PHOS.MAINT.4480 | CLEAN 2 | Phos Acid | 10811732 - Hazards from excessive chute blockages | 10811732 | 0050 | HPWB Motor and work area | 0 | Task Dependent | 2023-07-15 23:00 | 2023-07-16 01:00 |  | 10 | 2 | 2 | 6 | 6 | 0 |  |  | 2023-07-15 23:00 | 2023-07-16 01:00 | Waterblast Truck, Cleaning Ops | 23SD2
10811732 - 0070 | Not Started | GLSTest-01.PHOS.MAINT.4480 | DAWSON2 | Phos Acid | 10811732 - Hazards from excessive chute blockages | 10811732 | 0070 | Change-out 2 x Motors & Test | 0 | Task Dependent | 2023-07-16 01:00 | 2023-07-16 11:00 |  | 14.5 | 8 | 8 | 32 | 32 | 0 |  |  | 2023-07-16 01:00 | 2023-07-16 11:00 | Fitter, Elec 2 | 23SD2
10811732 - 0080 | Not Started | GLSTest-01.PHOS.MAINT.4480 | DAWSON2 | Phos Acid | 10811732 - Hazards from excessive chute blockages | 10811732 | 0080 | Ensure weights are set correctly | 0 | Task Dependent | 2023-07-16 11:00 | 2023-07-16 15:00 |  | 14.5 | 4 | 4 | 4 | 4 | 0 |  |  | 2023-07-16 11:00 | 2023-07-16 15:00 | Maintenance Engineer | 23SD2
10811732 - 0090 | Not Started | GLSTest-01.PHOS.MAINT.4480 | DAWSON2 | Phos Acid | 10811732 - Hazards from excessive chute blockages | 10811732 | 0090 | Dismantle Scaffold Access | 0 | Task Dependent | 2023-07-16 15:00 | 2023-07-16 21:00 |  | 14.5 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-16 15:00 | 2023-07-16 21:00 | Scaffolder | 23SD2
10811732 - 0120 | Not Started | GLSTest-01.PHOS.MAINT.4480 | DAWSON2 | Phos Acid | 10811732 - Hazards from excessive chute blockages | 10811732 | 0120 | Franna Team Assist Dismantle | 0 | Task Dependent | 2023-07-16 15:00 | 2023-07-16 16:00 |  | 17.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-16 15:00 | 2023-07-16 16:00 | Crane Operator, Rigger, Franna | 23SD2
10801196 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0010 | Issue Permit - 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 0 | Task Dependent | 2023-07-14 19:30 | 2023-07-14 20:00 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 19:30 | 2023-07-14 20:00 | Phos Permit Issuer | 23SD2
10801196 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0020 | Disconnect Temp & Pres Transmitter | 0 | Task Dependent | 2023-07-14 23:00 | 2023-07-15 01:00 |  | 11 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-14 23:00 | 2023-07-15 01:00 | Elec | 23SD2
10801196 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0030 | Remove Lobsterback Elbow | 0 | Task Dependent | 2023-07-14 20:00 | 2023-07-15 |  | 0 | 4 | 4 | 28 | 28 | 0 |  |  | 2023-07-14 20:00 | 2023-07-15 | 130ft EWP, 200t Crane, Crane Operator, T/A, Rigger, Fitter | 23SD2
10801196 - 0090 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0090 | Remove Downleg & Elbow | 0 | Task Dependent | 2023-07-15 | 2023-07-15 03:00 |  | 0 | 3 | 3 | 21 | 21 | 0 |  |  | 2023-07-15 | 2023-07-15 03:00 | 130ft EWP, 200t Crane, Crane Operator, T/A, Rigger, Fitter | 23SD2
10801196 - 0150 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0150 | Remove Reducing Spool | 0 | Task Dependent | 2023-07-15 08:00 | 2023-07-15 11:00 |  | 0 | 3 | 3 | 21 | 21 | 0 |  |  | 2023-07-15 08:00 | 2023-07-15 11:00 | 130ft EWP, 200t Crane, Crane Operator, T/A, Rigger, Fitter | 23SD2
10801196 - 0210 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0210 | Remove "S Bend" Pipe | 0 | Task Dependent | 2023-07-15 11:00 | 2023-07-15 14:00 |  | 0 | 3 | 3 | 21 | 21 | 0 |  |  | 2023-07-15 11:00 | 2023-07-15 14:00 | 130ft EWP, 200t Crane, Crane Operator, T/A, Rigger, Fitter | 23SD2
10801196 - 0270 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0270 | Remove MS to Vac Pump Vertical Pipe | 0 | Task Dependent | 2023-07-15 03:00 | 2023-07-15 05:00 |  | 1 | 2 | 2 | 14 | 14 | 0 |  |  | 2023-07-15 03:00 | 2023-07-15 05:00 | 130ft EWP, 200t Crane, Crane Operator, T/A, Rigger, Fitter | 23SD2
10801196 - 0330 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0330 | Remove MS Downleg Blinds | 0 | Task Dependent | 2023-07-15 14:00 | 2023-07-15 16:00 |  | 0 | 2 | 2 | 6 | 6 | 0 |  |  | 2023-07-15 14:00 | 2023-07-15 16:00 | 130ft EWP, T/A, Fitter | 23SD2
10801196 - 0360 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0360 | Remove Hatch MistSep | 0 | Task Dependent | 2023-07-15 16:00 | 2023-07-15 19:30 |  | 6 | 1.5 | 1.5 | 3 | 3 | 0 |  |  | 2023-07-15 16:00 | 2023-07-15 19:30 | Fitter | 23SD2
10801196 - 0390 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0390 | Remove VacPump Spool | 0 | Task Dependent | 2023-07-15 19:30 | 2023-07-15 21:00 |  | 6 | 1.5 | 1.5 | 3 | 3 | 0 |  |  | 2023-07-15 19:30 | 2023-07-15 21:00 | Fitter | 23SD2
10801196 - 0400 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0400 | Remove Hatch Condenser | 0 | Task Dependent | 2023-07-15 16:00 | 2023-07-15 19:30 |  | 6 | 1.5 | 1.5 | 3 | 3 | 0 |  |  | 2023-07-15 16:00 | 2023-07-15 19:30 | Fitter | 23SD2
10801196 - 0410 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0410 | Remove Seal Pot Hatch | 0 | Task Dependent | 2023-07-15 19:30 | 2023-07-15 20:30 |  | 6 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-15 19:30 | 2023-07-15 20:30 | Fitter | 23SD2
10801196 - 0420 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0420 | Hard Barricade Vessel Opening | 0 | Task Dependent | 2023-07-15 | 2023-07-15 01:30 |  | 1.5 | 1.5 | 1.5 | 6 | 6 | 0 |  |  | 2023-07-15 | 2023-07-15 01:30 | 130ft EWP, T/A, Scaffolder | 23SD2
10801196 - 0450 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0450 | Remove Vessel Opening Buildup | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 09:00 |  | 17 | 2 | 2 | 6 | 6 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 09:00 | Waterblast Truck, Cleaning Ops | 23SD2
10801196 - 0470 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0470 | Pre-clean Inspection | 0 | Task Dependent | 2023-07-15 21:00 | 2023-07-15 22:00 |  | 6 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-15 21:00 | 2023-07-15 22:00 | Phos Acid Engineer | 23SD2
10801196 - 0480 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0480 | Clean Vacuum Pipes | 0 | Task Dependent | 2023-07-16 04:00 | 2023-07-16 12:00 |  | 0 | 6 | 6 | 18 | 18 | 0 |  |  | 2023-07-16 04:00 | 2023-07-16 12:00 | Waterblast Truck, Cleaning Ops | 23SD2
10801196 - 0500 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0500 | Post-clean Inspection | 0 | Task Dependent | 2023-07-16 12:00 | 2023-07-16 13:00 |  | 0 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-16 12:00 | 2023-07-16 13:00 | Phos Acid Engineer | 23SD2
10801196 - 0510 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0510 | Remove Hard Barricade | 0 | Task Dependent | 2023-07-16 13:00 | 2023-07-16 14:30 |  | 0 | 1.5 | 1.5 | 6 | 6 | 0 |  |  | 2023-07-16 13:00 | 2023-07-16 14:30 | 130ft EWP, T/A, Scaffolder | 23SD2
10801196 - 0540 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0540 | Re-instate Lobsterback Elbows | 0 | Task Dependent | 2023-07-17 08:30 | 2023-07-17 13:30 |  | 0 | 5 | 5 | 40 | 40 | 0 |  |  | 2023-07-17 08:30 | 2023-07-17 13:30 | 130ft EWP, 200t Crane, Crane Operator, T/A, Rigger, Fitter | 23SD2
10801196 - 0600 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0600 | Re-Instate Downleg & Elbow | 0 | Task Dependent | 2023-07-17 03:30 | 2023-07-17 08:30 |  | 0 | 3 | 3 | 24 | 24 | 0 |  |  | 2023-07-17 03:30 | 2023-07-17 08:30 | 130ft EWP, 200t Crane, Crane Operator, T/A, Rigger, Fitter | 23SD2
10801196 - 0660 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0660 | Re-Instate Reducing Spool | 0 | Task Dependent | 2023-07-17 00:30 | 2023-07-17 03:30 |  | 0 | 3 | 3 | 24 | 24 | 0 |  |  | 2023-07-17 00:30 | 2023-07-17 03:30 | 130ft EWP, 200t Crane, Crane Operator, T/A, Rigger, Fitter | 23SD2
10801196 - 0720 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0720 | Re-instate "S Bend" Pipe | 0 | Task Dependent | 2023-07-16 21:30 | 2023-07-17 00:30 |  | 0 | 3 | 3 | 24 | 24 | 0 |  |  | 2023-07-16 21:30 | 2023-07-17 00:30 | 130ft EWP, 200t Crane, Crane Operator, T/A, Rigger, Fitter | 23SD2
10801196 - 0780 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0780 | Re-instate MS to Vac Pump Vertical Pipe | 0 | Task Dependent | 2023-07-16 14:30 | 2023-07-16 16:30 |  | 0 | 2 | 2 | 14 | 14 | 0 |  |  | 2023-07-16 14:30 | 2023-07-16 16:30 | 130ft EWP, 200t Crane, Crane Operator, T/A, Rigger, Fitter | 23SD2
10801196 - 0840 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0840 | Re-instate MS Downleg Blinds | 0 | Task Dependent | 2023-07-16 13:00 | 2023-07-16 15:00 |  | 1.5 | 2 | 2 | 6 | 6 | 0 |  |  | 2023-07-16 13:00 | 2023-07-16 15:00 | 130ft EWP, T/A, Fitter | 23SD2
10801196 - 0900 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0900 | Re-instate Seal Pot Hatch | 0 | Task Dependent | 2023-07-16 20:00 | 2023-07-16 21:00 |  | 0.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-16 20:00 | 2023-07-16 21:00 | Fitter | 23SD2
10801196 - 0910 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0910 | Re-instate VacPump Spool | 0 | Task Dependent | 2023-07-16 20:00 | 2023-07-16 21:30 |  | 0 | 1.5 | 1.5 | 3 | 3 | 0 |  |  | 2023-07-16 20:00 | 2023-07-16 21:30 | Fitter | 23SD2
10801196 - 0920 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0920 | Re-instate Hatch Condenser | 0 | Task Dependent | 2023-07-16 16:30 | 2023-07-16 20:00 |  | 0 | 1.5 | 1.5 | 3 | 3 | 0 |  |  | 2023-07-16 16:30 | 2023-07-16 20:00 | Fitter | 23SD2
10801196 - 0930 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0930 | Re-instate Hatch MistSep | 0 | Task Dependent | 2023-07-16 16:30 | 2023-07-16 20:00 |  | 0 | 1.5 | 1.5 | 3 | 3 | 0 |  |  | 2023-07-16 16:30 | 2023-07-16 20:00 | Fitter | 23SD2
10801196 - 0940 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0940 | Re-connect TT & PT, cal check PT | 0 | Task Dependent | 2023-07-17 08:30 | 2023-07-17 10:30 |  | 13 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-17 08:30 | 2023-07-17 10:30 | Elec | 23SD2
10801196 - 0950 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0950 | Close Permit - 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 0 | Task Dependent | 2023-07-17 13:30 | 2023-07-17 14:00 |  | 10 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-17 13:30 | 2023-07-17 14:00 | Phos Permit Issuer | 23SD2
10801196 - 0145 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0420 | Modify Scaffold for Reducing Spool Removal | 0 | Task Dependent | 2023-07-15 03:00 | 2023-07-15 08:00 |  | 0 | 3 | 3 | 12 | 12 | 0 |  |  | 2023-07-15 03:00 | 2023-07-15 08:00 | 130ft EWP, T/A, Scaffolder | 23SD2
10801196 - 0485 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0480 | Vac Out Seal Pot | 0 | Task Dependent | 2023-07-16 04:00 | 2023-07-16 05:00 |  | 5 | 1 | 1 | 3 | 3 | 0 |  |  | 2023-07-16 04:00 | 2023-07-16 05:00 | Vac Truck, Cleaning Ops | 23SD2
10801196 - 0665 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10801196 - 30W HPWB Cln PhosSD 44HE2502 | 10801196 | 0420 | Modify Scaffold for Reducing Spool | 0 | Task Dependent | 2023-07-16 14:30 | 2023-07-16 19:30 |  | 0 | 3 | 3 | 12 | 12 | 0 |  |  | 2023-07-16 14:30 | 2023-07-16 19:30 | 130ft EWP, T/A, Scaffolder | 23SD2
10798142 - 0075 | Not Started | GLSTest-01.GRAN.MAINT.4628 | DAWSON1 | Granulation | 10798142 - 60W MFit Insp GranSD 46AR2802 | 10798142 | 0050 | Box Up | 0 | Task Dependent | 2023-07-14 02:00 | 2023-07-14 02:30 |  | 27.5 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-14 02:00 | 2023-07-14 02:30 | Fitter | 23SD2
PHOS.RU.6010 | Not Started | GLSTest-01.PHOS.RU | PHOS | Phos Acid | Ramp Up - Hemihydrate Reaction |  |  | Fill R1A to with 40% acid to operating capacity | 0 | Task Dependent | 2023-07-17 04:00 | 2023-07-17 06:30 |  | 0 | 2.5 | 2.5 | 2.5 | 2.5 | 0 |  |  | 2023-07-17 04:00 | 2023-07-17 06:30 | Phos Ops | 22SD1
10748609 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4430 | DAWSON3 | Phos Acid | 10748609 - A side clothwash tk steam valve | 10748609 | 0020 | Reconnect Electrical | 0 | Task Dependent | 2023-07-16 02:30 | 2023-07-16 03:30 |  | 19 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-16 02:30 | 2023-07-16 03:30 | Elec 1 | 23SD2
10804483 - 0055 | Not Started | GLSTest-01.BENE.MAINT.2142 | CLEAN 2 | Beneficiation | 10804483 - 15W HPWB Cln BeneSD 21TK4204 | 10804483 | 0020 | Close hatches for cleaning | 0 | Task Dependent | 2023-07-15 10:00 | 2023-07-15 11:00 |  | 24.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-15 10:00 | 2023-07-15 11:00 | Fitter | 23SD2
10797919 - 0101 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10797919 - 30W MFit Rplc Rtry GranSD MX2201 | 10797919 | 0110 | Remove Gridmesh | 0 | Task Dependent | 2023-07-13 13:00 | 2023-07-13 14:00 |  | 9 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-13 13:00 | 2023-07-13 14:00 | Rigger | 23SD2
10797919 - 0102 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10797919 - 30W MFit Rplc Rtry GranSD MX2201 | 10797919 | 0110 | Erect Hard Barricade | 0 | Task Dependent | 2023-07-13 14:00 | 2023-07-13 15:00 |  | 9 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-13 14:00 | 2023-07-13 15:00 | Scaffolder | 23SD2
10797919 - 0103 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10797919 - 30W MFit Rplc Rtry GranSD MX2201 | 10797919 | 0110 | Disconnect Air Cannon Hose | 0 | Task Dependent | 2023-07-13 15:00 | 2023-07-13 16:00 |  | 9 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-13 15:00 | 2023-07-13 16:00 | Rigger | 23SD2
10797919 - 0181 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10797919 - 30W MFit Rplc Rtry GranSD MX2201 | 10797919 | 0180 | Reconnect Air Cannon Hose | 0 | Task Dependent | 2023-07-14 13:30 | 2023-07-14 14:30 |  | 18 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-14 13:30 | 2023-07-14 14:30 | Rigger | 23SD2
10797919 - 0182 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10797919 - 30W MFit Rplc Rtry GranSD MX2201 | 10797919 | 0180 | Dismantle Hard Barricade | 0 | Task Dependent | 2023-07-14 14:30 | 2023-07-14 15:30 |  | 18 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-14 14:30 | 2023-07-14 15:30 | Rigger | 23SD2
10797919 - 0183 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10797919 - 30W MFit Rplc Rtry GranSD MX2201 | 10797919 | 0180 | Reinstate Gridmesh | 0 | Task Dependent | 2023-07-14 15:30 | 2023-07-14 16:30 |  | 18 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-14 15:30 | 2023-07-14 16:30 | Rigger | 23SD2
10797919 - 0135 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10797919 - 30W MFit Rplc Rtry GranSD MX2201 | 10797919 | 0130 | Close western access door | 0 | Task Dependent | 2023-07-15 04:30 | 2023-07-15 07:30 |  | 9 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-15 04:30 | 2023-07-15 07:30 | Fitter | 23SD2
10797950 - 0015 | Not Started | GLSTest-01.GRAN.MAINT.4622 | CLEAN 1 | Granulation | 10797950 - 15W HPWB Cln GranSD 46CK2401 | 10797950 | 0010 | Fitters Open Covers | 0 | Task Dependent | 2023-07-12 09:30 | 2023-07-12 10:30 |  | 3.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-12 09:30 | 2023-07-12 10:30 | Fitter | 23SD2
10797950 - 0025 | Not Started | GLSTest-01.GRAN.MAINT.4622 | CLEAN 1 | Granulation | 10797950 - 15W HPWB Cln GranSD 46CK2401 | 10797950 | 0010 | Fitters Close Covers | 0 | Task Dependent | 2023-07-13 02:30 | 2023-07-13 03:30 |  | 51 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-13 02:30 | 2023-07-13 03:30 | Fitter | 23SD2
10794307 - 80 | Not Started | GLSTest-01.PHOS.MAINT.4425 | CLEAN 1 | Phos Acid | 10794307 - 15W HPWB Cln Lndr PhosSD 44TK0026 | 10794307 | 0020 | Erect Hard Barricade | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 09:00 |  | 22.5 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 09:00 | Scaffolder | 23SD2
10787923 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4621 | BMW | Granulation | 10787923 - MF-Replace sulphuric acid pipe - PN | 10787923 | 0010 | Issue Permit - 10787923 - MF-Replace sulphuric acid pipe - PN | 0 | Task Dependent | 2023-07-13 22:00 | 2023-07-13 22:30 |  | 9.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 22:00 | 2023-07-13 22:30 | Phos Permit Issuer | 23SD2
10787923 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4621 | BMW | Granulation | 10787923 - MF-Replace sulphuric acid pipe - PN | 10787923 | 0020 | Install Sulphuric Acid Pipe - PN (CSE) | 0 | Task Dependent | 2023-07-14 02:30 | 2023-07-14 09:30 |  | 9.5 | 5 | 5 | 10 | 10 | 0 |  |  | 2023-07-14 02:30 | 2023-07-14 09:30 | T/A, BMW | 23SD2
10787923 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4621 | BMW | Granulation | 10787923 - MF-Replace sulphuric acid pipe - PN | 10787923 | 0030 | Install Sulphuric Acid Pipe - PN (CSE) | 0 | Task Dependent | 2023-07-14 02:30 | 2023-07-14 04:30 |  | 14.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-14 02:30 | 2023-07-14 04:30 | 55t Crane, Crane Operator, Rigger | 23SD2
10787923 - 0060 | Not Started | GLSTest-01.GRAN.MAINT.4621 | BMW | Granulation | 10787923 - MF-Replace sulphuric acid pipe - PN | 10787923 | 0060 | Close Permit - 10787923 - MF-Replace sulphuric acid pipe - PN | 0 | Task Dependent | 2023-07-14 11:30 | 2023-07-14 12:00 |  | 9.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 11:30 | 2023-07-14 12:00 | Phos Permit Issuer | 23SD2
10787923 - 0070 | Not Started | GLSTest-01.GRAN.MAINT.4621 | BMW | Granulation | 10787923 - MF-Replace sulphuric acid pipe - PN | 10787923 | 0070 | Franna to transport from w/shop | 0 | Task Dependent | 2023-07-13 22:30 | 2023-07-13 23:30 |  | 13.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-13 22:30 | 2023-07-13 23:30 | Rigger, Crane Operator, Franna | 23SD2
10788566 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 1 | Phos Acid | 10788566 - 15W HPWB Cln PhosSD 44FC4001 | 10788566 | 0010 | Clean Fan Casings | 0 | Task Dependent | 2023-07-15 19:00 | 2023-07-15 20:00 |  | 4 | 1 | 1 | 3 | 3 | 0 |  |  | 2023-07-15 19:00 | 2023-07-15 20:00 | Waterblast Truck, Cleaning Ops | 23SD2
10796693 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4623 | CLEAN 1 | Granulation | 10796693 - 15W HPWB Cln GranSD CK2402 | 10796693 | 0010 | Issue Permit - 10796693 - 15W HPWB Cln GranSD CK2402 | 0 | Task Dependent | 2023-07-12 09:00 | 2023-07-12 09:30 |  | 11 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 09:00 | 2023-07-12 09:30 | Gran Permit Issuer | 23SD2
10796693 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4623 | CLEAN 1 | Granulation | 10796693 - 15W HPWB Cln GranSD CK2402 | 10796693 | 0020 | HPWB Dry Side Ducting | 0 | Task Dependent | 2023-07-12 09:30 | 2023-07-12 21:30 |  | 11 | 10 | 10 | 30 | 30 | 0 |  |  | 2023-07-12 09:30 | 2023-07-12 21:30 | Waterblast Truck, Cleaning Ops | 23SD2
10796693 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4623 | GRAN | Granulation | 10796693 - 15W HPWB Cln GranSD CK2402 | 10796693 | 0040 | Inspect and advise cleaning crew | 0 | Task Dependent | 2023-07-12 09:30 | 2023-07-12 15:30 |  | 61 | 6 | 6 | 6 | 6 | 0 |  |  | 2023-07-12 09:30 | 2023-07-12 15:30 | Gran Ops | 23SD2
10796693 - 0050 | Not Started | GLSTest-01.GRAN.MAINT.4623 | CLEAN 1 | Granulation | 10796693 - 15W HPWB Cln GranSD CK2402 | 10796693 | 0050 | Close Permit - 10796693 - 15W HPWB Cln GranSD CK2402 | 0 | Task Dependent | 2023-07-12 21:30 | 2023-07-12 22:00 |  | 57 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 21:30 | 2023-07-12 22:00 | Gran Permit Issuer | 23SD2
10802929 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4425 | PROJECT | Phos Acid | 10802929 - FCA Change out Mist seperator Pipe Spools | 10802929 | 0010 | 55t Crane Install Spools | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 15:00 |  | 9 | 8 | 8 | 24 | 24 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 15:00 | 55t Crane, Crane Operator, Rigger | 23SD2
10802929 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4425 | PROJECT | Phos Acid | 10802929 - FCA Change out Mist seperator Pipe Spools | 10802929 | 0030 | Fitter Install Spools | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 17:00 |  | 20 | 10 | 10 | 30 | 30 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 17:00 | Contract Fitter | 23SD2
10802930 - 0050 | Not Started | GLSTest-01.PHOS.MAINT.4425 | PROJECT | Phos Acid | 10802930 - FCB Change out Mist seperator Pipe Spools | 10802930 | 0050 | Issue Permit - 10802930 - Change out Mist seperator Pipe Spools | 0 | Task Dependent | 2023-07-15 14:00 | 2023-07-15 14:30 |  | 39 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 14:00 | 2023-07-15 14:30 | Phos Permit Issuer | 23SD2
10802930 - 0070 | Not Started | GLSTest-01.PHOS.MAINT.4425 | PROJECT | Phos Acid | 10802930 - FCB Change out Mist seperator Pipe Spools | 10802930 | 0070 | Change out spools (Covered in 10801196) | 0 | Task Dependent | 2023-07-15 14:30 | 2023-07-16 02:30 |  | 39 | 10 | 10 | 0 | 0 | 0 |  |  | 2023-07-15 14:30 | 2023-07-16 02:30 |  | 23SD2
10802930 - 0090 | Not Started | GLSTest-01.PHOS.MAINT.4425 | PROJECT | Phos Acid | 10802930 - FCB Change out Mist seperator Pipe Spools | 10802930 | 0090 | Close Permit - 10802930 - Change out Mist seperator Pipe Spools | 0 | Task Dependent | 2023-07-16 02:30 | 2023-07-16 03:00 |  | 39 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 02:30 | 2023-07-16 03:00 | Phos Permit Issuer | 23SD2
10810641 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4420 | ELEC | Phos Acid | 10810641 - Repair cable tray between rock filters | 10810641 | 0010 | Repair cable tray between rock filters - Shift 1 | 0 | Task Dependent | 2023-07-14 20:00 | 2023-07-15 06:00 |  | 14 | 10 | 10 | 20 | 20 | 0 |  |  | 2023-07-14 20:00 | 2023-07-15 06:00 | Elec 4 | 23SD2
10812593 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4411 | PROJECT | Phos Acid | 10812593 - MOD - Replace Spare Cell MCCB [SPP23020] | 10812593 | 0010 | FWD Switch | 0 | Task Dependent | 2023-07-15 06:30 | 2023-07-15 08:30 |  | 31.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-15 06:30 | 2023-07-15 08:30 | Elec | 23SD2
10812593 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4411 | PROJECT | Phos Acid | 10812593 - MOD - Replace Spare Cell MCCB [SPP23020] | 10812593 | 0020 | Replace MCCB | 0 | Task Dependent | 2023-07-15 08:30 | 2023-07-15 16:30 |  | 31.5 | 8 | 8 | 16 | 16 | 0 |  |  | 2023-07-15 08:30 | 2023-07-15 16:30 | Elec | 23SD2
10812593 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4411 | PROJECT | Phos Acid | 10812593 - MOD - Replace Spare Cell MCCB [SPP23020] | 10812593 | 0030 | REV Switch | 0 | Task Dependent | 2023-07-15 16:30 | 2023-07-15 18:30 |  | 31.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-15 16:30 | 2023-07-15 18:30 | Elec | 23SD2
10813789 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10813789 - Replace Overlander Lanyard Wire Rope | 10813789 | 0010 | Replace Overlander Lanyard Wire Rope | 0 | Task Dependent | 2023-07-14 07:30 | 2023-07-14 13:30 |  | 25 | 6 | 6 | 6 | 6 | 0 |  |  | 2023-07-14 07:30 | 2023-07-14 13:30 | Elec 4 | 23SD2
10813790 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10813790 - Replace Overlander Lanyard Wire Rope | 10813790 | 0010 | Replace Overlander Lanyard Wire Rope | 0 | Task Dependent | 2023-07-14 07:30 | 2023-07-14 13:30 |  | 25 | 6 | 6 | 6 | 6 | 0 |  |  | 2023-07-14 07:30 | 2023-07-14 13:30 | Elec 4 | 23SD2
10787923 - 0075 | Not Started | GLSTest-01.GRAN.MAINT.4621 | BMW | Granulation | 10787923 - MF-Replace sulphuric acid pipe - PN | 10787923 | 0070 | Franna to transport to w/shop | 0 | Task Dependent | 2023-07-14 09:30 | 2023-07-14 10:30 |  | 10.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-14 09:30 | 2023-07-14 10:30 | Rigger, Crane Operator, Franna | 23SD2
10772935 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.MISC | ELEC | Phos Acid | 10772935 - 2Y Elec Srv ISO Acid MCC | 10772935 | 0005 | Issue Permit - 10772935 - 2Y Elec Srv ISO Acid MCC | 0 | Task Dependent | 2023-07-15 11:00 | 2023-07-15 11:30 |  | 15.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 11:00 | 2023-07-15 11:30 | Phos Permit Issuer | 23SD2
10789290 - 0005 | Not Started | GLSTest-01.ACID.MAINT.4310 | DAWSON3 | Phos Acid | 10789290 - FI-Replace PSV 43PSV10009 | 10789290 | 0005 | Issue Permit - 10789290 - FI-Replace PSV 43PSV10009 | 0 | Task Dependent | 2023-07-15 19:00 | 2023-07-15 19:30 |  | 19 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 19:00 | 2023-07-15 19:30 | Phos Permit Issuer | 23SD2
10772935 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.MISC | ELEC | Phos Acid | 10772935 - 2Y Elec Srv ISO Acid MCC | 10772935 | 0020 | Close Permit - 10772935 - 2Y Elec Srv ISO Acid MCC | 0 | Task Dependent | 2023-07-15 13:00 | 2023-07-15 13:30 |  | 19.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 13:00 | 2023-07-15 13:30 | Phos Permit Issuer | 23SD2
10789290 - 0020 | Not Started | GLSTest-01.ACID.MAINT.4310 | DAWSON3 | Phos Acid | 10789290 - FI-Replace PSV 43PSV10009 | 10789290 | 0020 | Close Permit - 10789290 - FI-Replace PSV 43PSV10009 | 0 | Task Dependent | 2023-07-15 23:30 | 2023-07-16 |  | 19 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 23:30 | 2023-07-16 | Phos Permit Issuer | 23SD2
10772332 - 0005 | Not Started | GLSTest-01.BENE.MAINT.2411 | DAWSON2 | Beneficiation | 10772332 - MF-Make up water holed | 10772332 | 0005 | Issue Permit - 10772332 - MF-Make up water holed | 0 | Task Dependent | 2023-07-16 01:00 | 2023-07-16 01:30 |  | 11 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 01:00 | 2023-07-16 01:30 | Bene Permit Issuer | 23SD2
10800865 - 0005 | Not Started | GLSTest-01.BENE.MAINT.2111 | ELEC | Beneficiation | 10800865 - EL change precision rollers jaw feed con | 10800865 | 0005 | Issue Permit - 10800865 - EL change precision rollers jaw feed con | 0 | Task Dependent | 2023-07-14 06:30 | 2023-07-14 07:00 |  | 48 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 06:30 | 2023-07-14 07:00 | Bene Permit Issuer | 23SD2
10804579 - 0005 | Not Started | GLSTest-01.BENE.MAINT.2430 | ELEC | Beneficiation | 10804579 - 30W Elec SIS Srv UPS BENE | 10804579 | 0005 | Issue Permit - 10804579 - 30W Elec SIS Srv UPS BENE | 0 | Task Dependent | 2023-07-14 22:00 | 2023-07-14 22:30 |  | 23.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 22:00 | 2023-07-14 22:30 | Bene Permit Issuer | 23SD2
10692425 - 0200 | Not Started | GLSTest-01.BENE.MAINT.2122 | DAWSON2 | Beneficiation | 10692425 - cyclone cluster product downleg holed | 10692425 | 0200 | Close Permit - 10692425 - cyclone cluster product downleg holed | 0 | Task Dependent | 2023-07-16 21:30 | 2023-07-16 22:00 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 21:30 | 2023-07-16 22:00 | Bene Permit Issuer | 23SD2
10772332 - 0100 | Not Started | GLSTest-01.BENE.MAINT.2411 | DAWSON2 | Beneficiation | 10772332 - MF-Make up water holed | 10772332 | 0100 | Close Permit - 10772332 - MF-Make up water holed | 0 | Task Dependent | 2023-07-16 07:30 | 2023-07-16 08:00 |  | 11 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 07:30 | 2023-07-16 08:00 | Bene Permit Issuer | 23SD2
10800865 - 0050 | Not Started | GLSTest-01.BENE.MAINT.2111 | ELEC | Beneficiation | 10800865 - EL change precision rollers jaw feed con | 10800865 | 0050 | Close Permit - 10800865 - EL change precision rollers jaw feed con | 0 | Task Dependent | 2023-07-14 17:00 | 2023-07-14 17:30 |  | 54 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 17:00 | 2023-07-14 17:30 | Bene Permit Issuer | 23SD2
10804579 - 0030 | Not Started | GLSTest-01.BENE.MAINT.2430 | ELEC | Beneficiation | 10804579 - 30W Elec SIS Srv UPS BENE | 10804579 | 0030 | Close Permit - 10804579 - 30W Elec SIS Srv UPS BENE | 0 | Task Dependent | 2023-07-15 01:00 | 2023-07-15 01:30 |  | 23.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 01:00 | 2023-07-15 01:30 | Bene Permit Issuer | 23SD2
10789789 - 0005 | Not Started | GLSTest-01.GRAN.MAINT.4911 | ELEC | Granulation | 10789789 - 60W Elec Srv GranSD Weigh Strg Shd Cnv | 10789789 | 0005 | Issue Permit - 10789789 - 60W Elec Srv GranSD Weigh Strg Shd Cnv | 0 | Task Dependent | 2023-07-13 13:00 | 2023-07-13 13:30 |  | 19.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 13:00 | 2023-07-13 13:30 | Gran Permit Issuer | 23SD2
10806534 - 0005 | Not Started | GLSTest-01.GRAN.MAINT.4911 | ELEC | Granulation | 10806534 - 3M Elec Insp ISO Product Tripper Cnv | 10806534 | 0005 | Issue Permit - 10806534 - 3M Elec Insp ISO Product Tripper Cnv | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 07:30 |  | 28.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 07:30 | Gran Permit Issuer | 23SD2
10789789 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4911 | ELEC | Granulation | 10789789 - 60W Elec Srv GranSD Weigh Strg Shd Cnv | 10789789 | 0020 | Close Permit - 10789789 - 60W Elec Srv GranSD Weigh Strg Shd Cnv | 0 | Task Dependent | 2023-07-13 16:30 | 2023-07-13 17:00 |  | 25.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 16:30 | 2023-07-13 17:00 | Gran Permit Issuer | 23SD2
10806534 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4911 | ELEC | Granulation | 10806534 - 3M Elec Insp ISO Product Tripper Cnv | 10806534 | 0020 | Close Permit - 10806534 - 3M Elec Insp ISO Product Tripper Cnv | 0 | Task Dependent | 2023-07-13 07:42 | 2023-07-13 08:12 |  | 28.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:42 | 2023-07-13 08:12 | Gran Permit Issuer | 23SD2
10796624 - 0005 | Not Started | GLSTest-01.GRAN.MAINT.4625 | GRAN | Granulation | 10796624 - 15W Prod Insp GranSD HE2501 | 10796624 | 0005 | Issue Permit - 10796624 - 15W Prod Insp GranSD HE2501 | 0 | Task Dependent | 2023-07-13 21:00 | 2023-07-13 21:30 |  | 36 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 21:00 | 2023-07-13 21:30 | Gran Permit Issuer | 23SD2
10797957 - 0005 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10797957 - 30W Elec INT Srv DrvMtr FH2301 | 10797957 | 0005 | Issue Permit - 10797957 - 30W Elec INT Srv DrvMtr FH2301 | 0 | Task Dependent | 2023-07-13 03:00 | 2023-07-13 03:30 |  | 19.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 03:00 | 2023-07-13 03:30 | Gran Permit Issuer | 23SD2
10797978 - 0005 | Not Started | GLSTest-01.GRAN.MAINT.4622 | BMW | Granulation | 10797978 - 60W MFab Insp GranSD FH2301 | 10797978 | 0005 | Issue Permit - 10797978 - 60W MFab Insp GranSD FH2301 | 0 | Task Dependent | 2023-07-13 | 2023-07-13 00:30 |  | 49 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 | 2023-07-13 00:30 | Gran Permit Issuer | 23SD2
10798123 - 0005 | Not Started | GLSTest-01.GRAN.MAINT.4628 | GRAN | Granulation | 10798123 - 30W Prod Mont PROC GranSD Scrbbng | 10798123 | 0005 | Issue Permit - 10798123 - 30W Prod Mont PROC GranSD Scrbbng | 0 | Task Dependent | 2023-07-13 16:30 | 2023-07-13 17:00 |  | 28.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 16:30 | 2023-07-13 17:00 | Gran Permit Issuer | 23SD2
10798378 - 0005 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10798378 - 30W Elec Rplc Brnr Mjr GranSD Grnltn | 10798378 | 0005 | Issue Permit - 10798378 - 30W Elec Rplc Brnr Mjr GranSD Grnltn | 0 | Task Dependent | 2023-07-13 | 2023-07-13 00:30 |  | 20 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 | 2023-07-13 00:30 | Gran Permit Issuer | 23SD2
10802408 - 0005 | Not Started | GLSTest-01.GRAN.MAINT.4626 | GRAN | Granulation | 10802408 - 15W Prod Insp GranSD PlshngCtng | 10802408 | 0005 | Issue Permit - 10802408 - 15W Prod Insp GranSD PlshngCtng | 0 | Task Dependent | 2023-07-14 04:00 | 2023-07-14 04:30 |  | 29 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 04:00 | 2023-07-14 04:30 | Gran Permit Issuer | 23SD2
10802427 - 0005 | Not Started | GLSTest-01.GRAN.MAINT.4624 | GRAN | Granulation | 10802427 - 15W Prod Insp GranSD PrdctScrnng | 10802427 | 0005 | Issue Permit - 10802427 - 15W Prod Insp GranSD PrdctScrnng | 0 | Task Dependent | 2023-07-13 23:00 | 2023-07-13 23:30 |  | 29 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 23:00 | 2023-07-13 23:30 | Gran Permit Issuer | 23SD2
10802432 - 0005 | Not Started | GLSTest-01.GRAN.MAINT.4629 | GRAN | Granulation | 10802432 - 30W Prod Mont PROC GranSD NH3Systm | 10802432 | 0005 | Issue Permit - 10802432 - 30W Prod Mont PROC GranSD NH3Systm | 0 | Task Dependent | 2023-07-13 20:30 | 2023-07-13 21:00 |  | 28.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 20:30 | 2023-07-13 21:00 | Gran Permit Issuer | 23SD2
10802436 - 0005 | Not Started | GLSTest-01.GRAN.MAINT.4611 | ELEC | Granulation | 10802436 - 30W Elec SIS Srv UPS GRAN | 10802436 | 0005 | Issue Permit - 10802436 - 30W Elec SIS Srv UPS GRAN | 0 | Task Dependent | 2023-07-13 11:30 | 2023-07-13 12:00 |  | 21.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 11:30 | 2023-07-13 12:00 | Gran Permit Issuer | 23SD2
10807421 - 0005 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10807421 - MOD - Granulator Starter A/B Interlock | 10807421 | 0005 | Issue Permit - 10807421 - MOD - Granulator Starter A/B Interlock | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 07:30 |  | 17 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 07:30 | Gran Permit Issuer | 23SD2
10807995 - 0005 | Not Started | GLSTest-01.GRAN.MAINT.4629 | GRAN | Granulation | 10807995 - 15W Prod Rplc GranSD CE0001 | 10807995 | 0005 | Issue Permit - 10807995 - 15W Prod Rplc GranSD CE0001 | 0 | Task Dependent | 2023-07-13 02:30 | 2023-07-13 03:00 |  | 14 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 02:30 | 2023-07-13 03:00 | Gran Permit Issuer | 23SD2
10796624 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4625 | GRAN | Granulation | 10796624 - 15W Prod Insp GranSD HE2501 | 10796624 | 0020 | Close Permit - 10796624 - 15W Prod Insp GranSD HE2501 | 0 | Task Dependent | 2023-07-13 22:30 | 2023-07-13 23:00 |  | 36 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 22:30 | 2023-07-13 23:00 | Gran Permit Issuer | 23SD2
10797957 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10797957 - 30W Elec INT Srv DrvMtr FH2301 | 10797957 | 0020 | Close Permit - 10797957 - 30W Elec INT Srv DrvMtr FH2301 | 0 | Task Dependent | 2023-07-13 19:00 | 2023-07-13 19:30 |  | 22.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 19:00 | 2023-07-13 19:30 | Gran Permit Issuer | 23SD2
10797978 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | BMW | Granulation | 10797978 - 60W MFab Insp GranSD FH2301 | 10797978 | 0030 | Close Permit - 10797978 - 60W MFab Insp GranSD FH2301 | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 08:00 |  | 49 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 08:00 | Gran Permit Issuer | 23SD2
10798123 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4628 | GRAN | Granulation | 10798123 - 30W Prod Mont PROC GranSD Scrbbng | 10798123 | 0020 | Close Permit - 10798123 - 30W Prod Mont PROC GranSD Scrbbng | 0 | Task Dependent | 2023-07-13 20:00 | 2023-07-13 20:30 |  | 28.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 20:00 | 2023-07-13 20:30 | Gran Permit Issuer | 23SD2
10798378 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10798378 - 30W Elec Rplc Brnr Mjr GranSD Grnltn | 10798378 | 0040 | Close Permit - 10798378 - 30W Elec Rplc Brnr Mjr GranSD Grnltn | 0 | Task Dependent | 2023-07-13 22:00 | 2023-07-13 22:30 |  | 20 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 22:00 | 2023-07-13 22:30 | Gran Permit Issuer | 23SD2
10802408 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4626 | GRAN | Granulation | 10802408 - 15W Prod Insp GranSD PlshngCtng | 10802408 | 0020 | Close Permit - 10802408 - 15W Prod Insp GranSD PlshngCtng | 0 | Task Dependent | 2023-07-14 07:30 | 2023-07-14 08:00 |  | 29 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 07:30 | 2023-07-14 08:00 | Gran Permit Issuer | 23SD2
10802427 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4624 | GRAN | Granulation | 10802427 - 15W Prod Insp GranSD PrdctScrnng | 10802427 | 0020 | Close Permit - 10802427 - 15W Prod Insp GranSD PrdctScrnng | 0 | Task Dependent | 2023-07-14 00:30 | 2023-07-14 01:00 |  | 29 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 00:30 | 2023-07-14 01:00 | Gran Permit Issuer | 23SD2
10802432 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4629 | GRAN | Granulation | 10802432 - 30W Prod Mont PROC GranSD NH3Systm | 10802432 | 0020 | Close Permit - 10802432 - 30W Prod Mont PROC GranSD NH3Systm | 0 | Task Dependent | 2023-07-13 22:00 | 2023-07-13 22:30 |  | 28.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 22:00 | 2023-07-13 22:30 | Gran Permit Issuer | 23SD2
10802436 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4611 | ELEC | Granulation | 10802436 - 30W Elec SIS Srv UPS GRAN | 10802436 | 0020 | Close Permit - 10802436 - 30W Elec SIS Srv UPS GRAN | 0 | Task Dependent | 2023-07-13 14:30 | 2023-07-13 15:00 |  | 26 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 14:30 | 2023-07-13 15:00 | Gran Permit Issuer | 23SD2
10807421 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10807421 - MOD - Granulator Starter A/B Interlock | 10807421 | 0030 | Close Permit - 10807421 - MOD - Granulator Starter A/B Interlock | 0 | Task Dependent | 2023-07-14 09:00 | 2023-07-14 09:30 |  | 17 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 09:00 | 2023-07-14 09:30 | Gran Permit Issuer | 23SD2
10807995 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4629 | GRAN | Granulation | 10807995 - 15W Prod Rplc GranSD CE0001 | 10807995 | 0020 | Close Permit - 10807995 - 15W Prod Rplc GranSD CE0001 | 0 | Task Dependent | 2023-07-14 23:00 | 2023-07-14 23:30 |  | 14 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 23:00 | 2023-07-14 23:30 | Gran Permit Issuer | 23SD2
10677226 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4411 | ELEC | Phos Acid | 10677226 - Investigate indication lamp fault | 10677226 | 0005 | Issue Permit - 10677226 - Investigate indication lamp fault | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 07:30 |  | 17 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 07:30 | Phos Permit Issuer | 23SD2
10735951 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4440 | FG | Phos Acid | 10735951 - Filter b fume duct hatch | 10735951 | 0005 | Issue Permit - 10735951 - Filter b fume duct hatch | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 07:30 |  | 28 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 07:30 | Phos Permit Issuer | 23SD2
10748609 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4430 | DAWSON3 | Phos Acid | 10748609 - A side clothwash tk steam valve | 10748609 | 0005 | Issue Permit - 10748609 - A side clothwash tk steam valve | 0 | Task Dependent | 2023-07-16 | 2023-07-16 00:30 |  | 19 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 | 2023-07-16 00:30 | Phos Permit Issuer | 23SD2
10764498 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4420 | DAWSON3 | Phos Acid | 10764498 - Install New Poly Line | 10764498 | 0005 | Issue Permit - 10764498 - Install New Poly Line | 0 | Task Dependent | 2023-07-16 19:30 | 2023-07-16 20:00 |  | 9 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 19:30 | 2023-07-16 20:00 | Phos Permit Issuer | 23SD2
10773343 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4438 | ELEC | Phos Acid | 10773343 - 60W Elec OLL Prog XVlv 44PF3808 | 10773343 | 0005 | Issue Permit - 10773343 - 60W Elec OLL Prog XVlv 44PF3808 | 0 | Task Dependent | 2023-07-14 22:00 | 2023-07-14 22:30 |  | 24 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 22:00 | 2023-07-14 22:30 | Phos Permit Issuer | 23SD2
10785429 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4420 | DAWSON2 | Phos Acid | 10785429 - FI-2008 discharge line wrapped | 10785429 | 0005 | Issue Permit - 10785429 - FI-2008 discharge line wrapped | 0 | Task Dependent | 2023-07-15 02:30 | 2023-07-15 03:00 |  | 38 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 02:30 | 2023-07-15 03:00 | Phos Permit Issuer | 23SD2
10788566 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 2 | Phos Acid | 10788566 - 15W HPWB Cln PhosSD 44FC4001 | 10788566 | 0005 | Issue Permit - 10788566 - 15W HPWB Cln PhosSD 44FC4001 | 0 | Task Dependent | 2023-07-15 16:30 | 2023-07-15 17:00 |  | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 16:30 | 2023-07-15 17:00 | Phos Permit Issuer | 23SD2
10788629 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4425 | PHOS | Phos Acid | 10788629 - 15W Prod Insp Pump Skid PhosSD HHR | 10788629 | 0005 | Issue Permit - 10788629 - 15W Prod Insp Pump Skid PhosSD HHR | 0 | Task Dependent | 2023-07-14 23:30 | 2023-07-15 |  | 36 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 23:30 | 2023-07-15 | Phos Permit Issuer | 23SD2
10789707 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON1 | Phos Acid | 10789707 - 15W MFit Rmv PhosSD Reactor Spargers | 10789707 | 0005 | Issue Permit - 10789707 - 15W MFit Rmv PhosSD Reactor Spargers | 0 | Task Dependent | 2023-07-16 19:00 | 2023-07-16 19:30 |  | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 19:00 | 2023-07-16 19:30 | Phos Permit Issuer | 23SD2
10793809 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4445 | DAWSON3 | Phos Acid | 10793809 - FI-Pump bypass line blocked | 10793809 | 0005 | Issue Permit - 10793809 - FI-Pump bypass line blocked | 0 | Task Dependent | 2023-07-16 10:30 | 2023-07-16 11:00 |  | 9 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 10:30 | 2023-07-16 11:00 | Phos Permit Issuer | 23SD2
10796135 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4420 | RUBBER | Phos Acid | 10796135 - RW-Replace broken roller #13 | 10796135 | 0005 | Issue Permit - 10796135 - RW-Replace broken roller #13 | 0 | Task Dependent | 2023-07-15 00:30 | 2023-07-15 01:00 |  | 46.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 00:30 | 2023-07-15 01:00 | Phos Permit Issuer | 23SD2
10796254 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10796254 - Replace electrical box door and hinges | 10796254 | 0005 | Issue Permit - 10796254 - Replace electrical box door and hinges | 0 | Task Dependent | 2023-07-14 19:00 | 2023-07-14 19:30 |  | 13 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 19:00 | 2023-07-14 19:30 | Phos Permit Issuer | 23SD2
10798685 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10798685 - Replace Leaking Regulator | 10798685 | 0005 | Issue Permit - 10798685 - Replace Leaking Regulator | 0 | Task Dependent | 2023-07-15 23:00 | 2023-07-15 23:30 |  | 13 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 23:00 | 2023-07-15 23:30 | Phos Permit Issuer | 23SD2
10802929 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4425 | PROJECT | Phos Acid | 10802929 - FCA Change out Mist seperator Pipe Spools | 10802929 | 0005 | Issue Permit - 10802929 - FCA Change out Mist seperator Pipe Spools | 0 | Task Dependent | 2023-07-15 04:30 | 2023-07-15 05:00 |  | 9 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 04:30 | 2023-07-15 05:00 | Phos Permit Issuer | 23SD2
10804322 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4480 | CLEAN 2 | Phos Acid | 10804322 - 15W HPWB Cln PhosSD 44CB8003 | 10804322 | 0005 | Issue Permit - 10804322 - 15W HPWB Cln PhosSD 44CB8003 | 0 | Task Dependent | 2023-07-15 02:00 | 2023-07-15 02:30 |  | 11.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 02:00 | 2023-07-15 02:30 | Phos Permit Issuer | 23SD2
10806644 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4440 | ENG | Phos Acid | 10806644 - 15W REng Insp PhosSD 44FC4002 | 10806644 | 0005 | Issue Permit - 10806644 - 15W REng Insp PhosSD 44FC4002 | 0 | Task Dependent | 2023-07-16 04:00 | 2023-07-16 04:30 |  | 17.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 04:00 | 2023-07-16 04:30 | Phos Permit Issuer | 23SD2
10806645 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4440 | ENG | Phos Acid | 10806645 - 15W REng Insp PhosSD 44FC4001 | 10806645 | 0005 | Issue Permit - 10806645 - 15W REng Insp PhosSD 44FC4001 | 0 | Task Dependent | 2023-07-15 03:00 | 2023-07-15 03:30 |  | 38.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 03:00 | 2023-07-15 03:30 | Phos Permit Issuer | 23SD2
10807389 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4410 | ELEC | Phos Acid | 10807389 - Replace cable, include service loop | 10807389 | 0005 | Issue Permit - 10807389 - Replace cable, include service loop | 0 | Task Dependent | 2023-07-16 01:00 | 2023-07-16 01:30 |  | 9 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 01:00 | 2023-07-16 01:30 | Phos Permit Issuer | 23SD2
10807417 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4480 | ELEC | Phos Acid | 10807417 - Install Cable labels | 10807417 | 0005 | Issue Permit - 10807417 - Install Cable labels | 0 | Task Dependent | 2023-07-16 01:00 | 2023-07-16 01:30 |  | 9 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 01:00 | 2023-07-16 01:30 | Phos Permit Issuer | 23SD2
10809655 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4485 | DAWSON3 | Phos Acid | 10809655 - FI- Valve not functional | 10809655 | 0005 | Issue Permit - 10809655 - FI- Valve not functional | 0 | Task Dependent | 2023-07-15 02:00 | 2023-07-15 02:30 |  | 19 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 02:00 | 2023-07-15 02:30 | Phos Permit Issuer | 23SD2
10810294 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4485 | RUBBER | Phos Acid | 10810294 - RW overlander replace tracking frame | 10810294 | 0005 | Issue Permit - 10810294 - RW overlander replace tracking frame | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 07:30 |  | 61.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 07:30 | Phos Permit Issuer | 23SD2
10810641 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4420 | ELEC | Phos Acid | 10810641 - Repair cable tray between rock filters | 10810641 | 0005 | Issue Permit - 10810641 - Repair cable tray between rock filters | 0 | Task Dependent | 2023-07-14 19:30 | 2023-07-14 20:00 |  | 14 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 19:30 | 2023-07-14 20:00 | Phos Permit Issuer | 23SD2
10811732 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4480 | DAWSON2 | Phos Acid | 10811732 - Hazards from excessive chute blockages | 10811732 | 0005 | Issue Permit - 10811732 - Hazards from excessive chute blockages | 0 | Task Dependent | 2023-07-15 02:30 | 2023-07-15 03:00 |  | 10 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 02:30 | 2023-07-15 03:00 | Phos Permit Issuer | 23SD2
10812593 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4411 | PROJECT | Phos Acid | 10812593 - MOD - Replace Spare Cell MCCB [SPP23020] | 10812593 | 0005 | Issue Permit - 10812593 - MOD - Replace Spare Cell MCCB [SPP23020] | 0 | Task Dependent | 2023-07-15 06:00 | 2023-07-15 06:30 |  | 31.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 06:00 | 2023-07-15 06:30 | Phos Permit Issuer | 23SD2
10813789 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10813789 - Replace Overlander Lanyard Wire Rope | 10813789 | 0005 | Issue Permit - 10813789 - Replace Overlander Lanyard Wire Rope | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 07:30 |  | 25 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 07:30 | Phos Permit Issuer | 23SD2
10813790 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10813790 - Replace Overlander Lanyard Wire Rope | 10813790 | 0005 | Issue Permit - 10813790 - Replace Overlander Lanyard Wire Rope | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 07:30 |  | 25 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 07:30 | Phos Permit Issuer | 23SD2
10677226 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4411 | ELEC | Phos Acid | 10677226 - Investigate indication lamp fault | 10677226 | 0020 | Close Permit - 10677226 - Investigate indication lamp fault | 0 | Task Dependent | 2023-07-15 11:30 | 2023-07-15 12:00 |  | 17 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 11:30 | 2023-07-15 12:00 | Phos Permit Issuer | 23SD2
10735951 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4440 | FG | Phos Acid | 10735951 - Filter b fume duct hatch | 10735951 | 0020 | Close Permit - 10735951 - Filter b fume duct hatch | 0 | Task Dependent | 2023-07-15 16:30 | 2023-07-15 17:00 |  | 28 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 16:30 | 2023-07-15 17:00 | Phos Permit Issuer | 23SD2
10748609 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4430 | DAWSON3 | Phos Acid | 10748609 - A side clothwash tk steam valve | 10748609 | 0030 | Close Permit - 10748609 - A side clothwash tk steam valve | 0 | Task Dependent | 2023-07-16 03:30 | 2023-07-16 04:00 |  | 19 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 03:30 | 2023-07-16 04:00 | Phos Permit Issuer | 23SD2
10764498 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4420 | DAWSON3 | Phos Acid | 10764498 - Install New Poly Line | 10764498 | 0020 | Close Permit - 10764498 - Install New Poly Line | 0 | Task Dependent | 2023-07-17 02:00 | 2023-07-17 02:30 |  | 9 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-17 02:00 | 2023-07-17 02:30 | Phos Permit Issuer | 23SD2
10773343 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4438 | ELEC | Phos Acid | 10773343 - 60W Elec OLL Prog XVlv 44PF3808 | 10773343 | 0020 | Close Permit - 10773343 - 60W Elec OLL Prog XVlv 44PF3808 | 0 | Task Dependent | 2023-07-15 00:30 | 2023-07-15 01:00 |  | 24 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 00:30 | 2023-07-15 01:00 | Phos Permit Issuer | 23SD2
10785429 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4420 | DAWSON2 | Phos Acid | 10785429 - FI-2008 discharge line wrapped | 10785429 | 0040 | Close Permit - 10785429 - FI-2008 discharge line wrapped | 0 | Task Dependent | 2023-07-15 15:00 | 2023-07-15 15:30 |  | 38 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 15:00 | 2023-07-15 15:30 | Phos Permit Issuer | 23SD2
10788566 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4440 | CLEAN 2 | Phos Acid | 10788566 - 15W HPWB Cln PhosSD 44FC4001 | 10788566 | 0030 | Close Permit - 10788566 - 15W HPWB Cln PhosSD 44FC4001 | 0 | Task Dependent | 2023-07-15 20:00 | 2023-07-15 20:30 |  | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 20:00 | 2023-07-15 20:30 | Phos Permit Issuer | 23SD2
10788588 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4420 | RUBBER | Phos Acid | 10788588 - 15W MFit Insp PhosSD 41CB2001 | 10788588 | 0040 | Close Permit - 10788588 - 15W MFit Insp PhosSD 41CB2001 | 0 | Task Dependent | 2023-07-15 | 2023-07-15 00:30 |  | 50.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 | 2023-07-15 00:30 | Phos Permit Issuer | 23SD2
10788629 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4425 | PHOS | Phos Acid | 10788629 - 15W Prod Insp Pump Skid PhosSD HHR | 10788629 | 0030 | Close Permit - 10788629 - 15W Prod Insp Pump Skid PhosSD HHR | 0 | Task Dependent | 2023-07-15 01:00 | 2023-07-15 01:30 |  | 36 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 01:00 | 2023-07-15 01:30 | Phos Permit Issuer | 23SD2
10789707 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON1 | Phos Acid | 10789707 - 15W MFit Rmv PhosSD Reactor Spargers | 10789707 | 0030 | Close Permit - 10789707 - 15W MFit Rmv PhosSD Reactor Spargers | 0 | Task Dependent | 2023-07-17 20:00 | 2023-07-17 20:30 |  | 16.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-17 20:00 | 2023-07-17 20:30 | Phos Permit Issuer | 23SD2
10793809 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4445 | DAWSON3 | Phos Acid | 10793809 - FI-Pump bypass line blocked | 10793809 | 0020 | Close Permit - 10793809 - FI-Pump bypass line blocked | 0 | Task Dependent | 2023-07-16 19:00 | 2023-07-16 19:30 |  | 9 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 19:00 | 2023-07-16 19:30 | Phos Permit Issuer | 23SD2
10796135 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4420 | RUBBER | Phos Acid | 10796135 - RW-Replace broken roller #13 | 10796135 | 0020 | Close Permit - 10796135 - RW-Replace broken roller #13 | 0 | Task Dependent | 2023-07-15 04:00 | 2023-07-15 04:30 |  | 46.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 04:00 | 2023-07-15 04:30 | Phos Permit Issuer | 23SD2
10796254 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10796254 - Replace electrical box door and hinges | 10796254 | 0020 | Close Permit - 10796254 - Replace electrical box door and hinges | 0 | Task Dependent | 2023-07-16 01:30 | 2023-07-16 02:00 |  | 13 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 01:30 | 2023-07-16 02:00 | Phos Permit Issuer | 23SD2
10798685 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10798685 - Replace Leaking Regulator | 10798685 | 0020 | Close Permit - 10798685 - Replace Leaking Regulator | 0 | Task Dependent | 2023-07-16 01:30 | 2023-07-16 02:00 |  | 17 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 01:30 | 2023-07-16 02:00 | Phos Permit Issuer | 23SD2
10802929 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4425 | PROJECT | Phos Acid | 10802929 - FCA Change out Mist seperator Pipe Spools | 10802929 | 0040 | Close Permit - 10802929 - FCA Change out Mist seperator Pipe Spools | 0 | Task Dependent | 2023-07-15 19:00 | 2023-07-15 19:30 |  | 46.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 19:00 | 2023-07-15 19:30 | Phos Permit Issuer | 23SD2
10804322 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4480 | CLEAN 2 | Phos Acid | 10804322 - 15W HPWB Cln PhosSD 44CB8003 | 10804322 | 0020 | Close Permit - 10804322 - 15W HPWB Cln PhosSD 44CB8003 | 0 | Task Dependent | 2023-07-15 08:30 | 2023-07-15 09:00 |  | 26.9 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 08:30 | 2023-07-15 09:00 | Phos Permit Issuer | 23SD2
10806644 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4440 | ENG | Phos Acid | 10806644 - 15W REng Insp PhosSD 44FC4002 | 10806644 | 0020 | Close Permit - 10806644 - 15W REng Insp PhosSD 44FC4002 | 0 | Task Dependent | 2023-07-16 07:00 | 2023-07-16 07:30 |  | 17.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 07:00 | 2023-07-16 07:30 | Phos Permit Issuer | 23SD2
10806645 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4440 | ENG | Phos Acid | 10806645 - 15W REng Insp PhosSD 44FC4001 | 10806645 | 0020 | Close Permit - 10806645 - 15W REng Insp PhosSD 44FC4001 | 0 | Task Dependent | 2023-07-15 04:00 | 2023-07-15 04:30 |  | 38.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 04:00 | 2023-07-15 04:30 | Phos Permit Issuer | 23SD2
10807389 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4410 | ELEC | Phos Acid | 10807389 - Replace cable, include service loop | 10807389 | 0020 | Close Permit - 10807389 - Replace cable, include service loop | 0 | Task Dependent | 2023-07-16 19:30 | 2023-07-16 20:00 |  | 22 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 19:30 | 2023-07-16 20:00 | Phos Permit Issuer | 23SD2
10807417 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4480 | ELEC | Phos Acid | 10807417 - Install Cable labels | 10807417 | 0020 | Close Permit - 10807417 - Install Cable labels | 0 | Task Dependent | 2023-07-16 19:30 | 2023-07-16 20:00 |  | 9 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 19:30 | 2023-07-16 20:00 | Phos Permit Issuer | 23SD2
10809655 - 0080 | Not Started | GLSTest-01.PHOS.MAINT.4485 | DAWSON3 | Phos Acid | 10809655 - FI- Valve not functional | 10809655 | 0080 | Close Permit - 10809655 - FI- Valve not functional | 0 | Task Dependent | 2023-07-15 08:30 | 2023-07-15 09:00 |  | 19 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 08:30 | 2023-07-15 09:00 | Phos Permit Issuer | 23SD2
10810294 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4485 | RUBBER | Phos Acid | 10810294 - RW overlander replace tracking frame | 10810294 | 0040 | Close Permit - 10810294 - RW overlander replace tracking frame | 0 | Task Dependent | 2023-07-14 11:30 | 2023-07-14 12:00 |  | 61.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 11:30 | 2023-07-14 12:00 | Phos Permit Issuer | 23SD2
10810641 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4420 | ELEC | Phos Acid | 10810641 - Repair cable tray between rock filters | 10810641 | 0020 | Close Permit - 10810641 - Repair cable tray between rock filters | 0 | Task Dependent | 2023-07-16 02:00 | 2023-07-16 02:30 |  | 14 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 02:00 | 2023-07-16 02:30 | Phos Permit Issuer | 23SD2
10811732 - 0130 | Not Started | GLSTest-01.PHOS.MAINT.4480 | DAWSON2 | Phos Acid | 10811732 - Hazards from excessive chute blockages | 10811732 | 0130 | Close Permit - 10811732 - Hazards from excessive chute blockages | 0 | Task Dependent | 2023-07-16 21:00 | 2023-07-16 21:30 |  | 14.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 21:00 | 2023-07-16 21:30 | Phos Permit Issuer | 23SD2
10812593 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4411 | PROJECT | Phos Acid | 10812593 - MOD - Replace Spare Cell MCCB [SPP23020] | 10812593 | 0040 | Close Permit - 10812593 - MOD - Replace Spare Cell MCCB [SPP23020] | 0 | Task Dependent | 2023-07-15 18:00 | 2023-07-15 18:30 |  | 31.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 18:00 | 2023-07-15 18:30 | Phos Permit Issuer | 23SD2
10813789 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10813789 - Replace Overlander Lanyard Wire Rope | 10813789 | 0020 | Close Permit - 10813789 - Replace Overlander Lanyard Wire Rope | 0 | Task Dependent | 2023-07-14 13:30 | 2023-07-14 14:00 |  | 25 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 13:30 | 2023-07-14 14:00 | Phos Permit Issuer | 23SD2
10813790 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4485 | ELEC | Phos Acid | 10813790 - Replace Overlander Lanyard Wire Rope | 10813790 | 0020 | Close Permit - 10813790 - Replace Overlander Lanyard Wire Rope | 0 | Task Dependent | 2023-07-14 13:30 | 2023-07-14 14:00 |  | 25 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 13:30 | 2023-07-14 14:00 | Phos Permit Issuer | 23SD2
10715829 - 0005 | Not Started | GLSTest-01.PWR.MAINT.5422 | PWR | Power Station | 10715829 - GT2- Install Vent fan Vibration sensor | 10715829 | 0005 | Issue Permit - 10715829 - GT2- Install Vent fan Vibration sensor | 0 | Task Dependent | 2023-07-15 22:00 | 2023-07-15 22:30 |  | 40 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 22:00 | 2023-07-15 22:30 | Pwr Ops | 23SD2
10715830 - 0005 | Not Started | GLSTest-01.PWR.MAINT.5422 | PWR | Power Station | 10715830 - GT2- Install Lube oil cooler VIB Sensor | 10715830 | 0005 | Issue Permit - 10715830 - GT2- Install Lube oil cooler VIB Sensor | 0 | Task Dependent | 2023-07-16 01:00 | 2023-07-16 01:30 |  | 40 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 01:00 | 2023-07-16 01:30 | Pwr Ops | 23SD2
10715834 - 0005 | Not Started | GLSTest-01.PWR.MAINT.5442 | PWR | Power Station | 10715834 - GT4- Install Vent fan Vibration sensor | 10715834 | 0005 | Issue Permit - 10715834 - GT4- Install Vent fan Vibration sensor | 0 | Task Dependent | 2023-07-14 04:30 | 2023-07-14 05:00 |  | 50.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 04:30 | 2023-07-14 05:00 | Pwr Ops | 23SD2
10715835 - 0005 | Not Started | GLSTest-01.PWR.MAINT.5442 | PWR | Power Station | 10715835 - GT4- Install Lube oil Cooler VIB sensor | 10715835 | 0005 | Issue Permit - 10715835 - GT4- Install Lube oil Cooler VIB sensor | 0 | Task Dependent | 2023-07-13 02:00 | 2023-07-13 02:30 |  | 73 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 02:00 | 2023-07-13 02:30 | Pwr Ops | 23SD2
10766816 - 0005 | Not Started | GLSTest-01.PWR.MAINT.MISC | PWR | Power Station | 10766816 - Generator Elec Stat Testing | 10766816 | 0005 | Issue Permit - 10766816 - Generator Elec Stat Testing | 0 | Task Dependent | 2023-07-13 12:30 | 2023-07-13 13:00 |  | 89.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 12:30 | 2023-07-13 13:00 | Pwr Ops | 23SD2
10774353 - 0005 | Not Started | GLSTest-01.PWR.MAINT.5422 | PWR | Power Station | 10774353 - Local HMI Screen Not Displaying | 10774353 | 0005 | Issue Permit - 10774353 - Local HMI Screen Not Displaying | 0 | Task Dependent | 2023-07-15 22:00 | 2023-07-15 22:30 |  | 41 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 22:00 | 2023-07-15 22:30 | Pwr Ops | 23SD2
10793019 - 0005 | Not Started | GLSTest-01.PWR.MAINT.5442 | PWR | Power Station | 10793019 - 4Y Elec Ovhl PwrSD Trbn 4 Fuel Gas FCV | 10793019 | 0005 | Issue Permit - 10793019 - 4Y Elec Ovhl PwrSD Trbn 4 Fuel Gas FCV | 0 | Task Dependent | 2023-07-14 09:00 | 2023-07-14 09:30 |  | 40 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 09:00 | 2023-07-14 09:30 | Pwr Ops | 23SD2
10796451 - 0005 | Not Started | GLSTest-01.PWR.MAINT.5412 | PWR | Power Station | 10796451 - 18M MFit Rplc PwrSD GT 1 Air Filter | 10796451 | 0005 | Issue Permit - 10796451 - 18M MFit Rplc PwrSD GT 1 Air Filter | 0 | Task Dependent | 2023-07-16 10:00 | 2023-07-16 10:30 |  | 40 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 10:00 | 2023-07-16 10:30 | Pwr Ops | 23SD2
10715829 - 0020 | Not Started | GLSTest-01.PWR.MAINT.5422 | PWR | Power Station | 10715829 - GT2- Install Vent fan Vibration sensor | 10715829 | 0020 | Close Permit - 10715829 - GT2- Install Vent fan Vibration sensor | 0 | Task Dependent | 2023-07-16 00:30 | 2023-07-16 01:00 |  | 40 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 00:30 | 2023-07-16 01:00 | Pwr Ops | 23SD2
10715830 - 0020 | Not Started | GLSTest-01.PWR.MAINT.5422 | PWR | Power Station | 10715830 - GT2- Install Lube oil cooler VIB Sensor | 10715830 | 0020 | Close Permit - 10715830 - GT2- Install Lube oil cooler VIB Sensor | 0 | Task Dependent | 2023-07-16 03:30 | 2023-07-16 04:00 |  | 40 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 03:30 | 2023-07-16 04:00 | Pwr Ops | 23SD2
10715834 - 0020 | Not Started | GLSTest-01.PWR.MAINT.5442 | PWR | Power Station | 10715834 - GT4- Install Vent fan Vibration sensor | 10715834 | 0020 | Close Permit - 10715834 - GT4- Install Vent fan Vibration sensor | 0 | Task Dependent | 2023-07-14 09:00 | 2023-07-14 09:30 |  | 50.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 09:00 | 2023-07-14 09:30 | Pwr Ops | 23SD2
10715835 - 0020 | Not Started | GLSTest-01.PWR.MAINT.5442 | PWR | Power Station | 10715835 - GT4- Install Lube oil Cooler VIB sensor | 10715835 | 0020 | Close Permit - 10715835 - GT4- Install Lube oil Cooler VIB sensor | 0 | Task Dependent | 2023-07-13 04:30 | 2023-07-13 05:00 |  | 73 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 04:30 | 2023-07-13 05:00 | Pwr Ops | 23SD2
10766816 - 0030 | Not Started | GLSTest-01.PWR.MAINT.MISC | PWR | Power Station | 10766816 - Generator Elec Stat Testing | 10766816 | 0030 | Close Permit - 10766816 - Generator Elec Stat Testing | 0 | Task Dependent | 2023-07-16 16:00 | 2023-07-16 16:30 |  | 38.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 16:00 | 2023-07-16 16:30 | Pwr Ops | 23SD2
10774353 - 0020 | Not Started | GLSTest-01.PWR.MAINT.5422 | PWR | Power Station | 10774353 - Local HMI Screen Not Displaying | 10774353 | 0020 | Close Permit - 10774353 - Local HMI Screen Not Displaying | 0 | Task Dependent | 2023-07-16 02:30 | 2023-07-16 03:00 |  | 41 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 02:30 | 2023-07-16 03:00 | Pwr Ops | 23SD2
10793019 - 0020 | Not Started | GLSTest-01.PWR.MAINT.5442 | PWR | Power Station | 10793019 - 4Y Elec Ovhl PwrSD Trbn 4 Fuel Gas FCV | 10793019 | 0020 | Close Permit - 10793019 - 4Y Elec Ovhl PwrSD Trbn 4 Fuel Gas FCV | 0 | Task Dependent | 2023-07-14 21:30 | 2023-07-14 22:00 |  | 40 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 21:30 | 2023-07-14 22:00 | Pwr Ops | 23SD2
10796451 - 0020 | Not Started | GLSTest-01.PWR.MAINT.5412 | PWR | Power Station | 10796451 - 18M MFit Rplc PwrSD GT 1 Air Filter | 10796451 | 0020 | Close Permit - 10796451 - 18M MFit Rplc PwrSD GT 1 Air Filter | 0 | Task Dependent | 2023-07-16 12:30 | 2023-07-16 13:00 |  | 40 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 12:30 | 2023-07-16 13:00 | Pwr Ops | 23SD2
Wed_DS | Not Started | GLSTest-01.MLSTN.GEN |  |  | Key Dates |  |  | Wednesday Day Shift Start | 0 | Start Milestone | 2023-07-12 06:00 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-12 06:00 |  |  | 22SD1
Wed_NS | Not Started | GLSTest-01.MLSTN.GEN |  |  | Key Dates |  |  | Wednesday Night Shift Start | 0 | Start Milestone | 2023-07-12 18:00 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-12 18:00 |  |  | 22SD1
Thu_DS | Not Started | GLSTest-01.MLSTN.GEN |  |  | Key Dates |  |  | Thursday Day Shift Start | 0 | Start Milestone | 2023-07-13 06:00 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-13 06:00 |  |  | 22SD1
Thu_NS | Not Started | GLSTest-01.MLSTN.GEN |  |  | Key Dates |  |  | Thursday Night Shift Start | 0 | Start Milestone | 2023-07-13 18:00 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-13 18:00 |  |  | 22SD1
Fri_DS | Not Started | GLSTest-01.MLSTN.GEN |  |  | Key Dates |  |  | Friday Day Shift Start | 0 | Start Milestone | 2023-07-14 06:00 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-14 06:00 |  |  | 22SD1
Fri_NS | Not Started | GLSTest-01.MLSTN.GEN |  |  | Key Dates |  |  | Friday Night Shift Start | 0 | Start Milestone | 2023-07-14 18:00 |  |  | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-14 18:00 |  |  | 22SD1
Sat_DS | Not Started | GLSTest-01.MLSTN.GEN |  |  | Key Dates |  |  | Saturday Day Shift Start | 0 | Start Milestone | 2023-07-15 06:00 |  |  | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-15 06:00 |  |  | 22SD1
Sat_NS | Not Started | GLSTest-01.MLSTN.GEN |  |  | Key Dates |  |  | Saturday Night Shift Start | 0 | Start Milestone | 2023-07-15 18:00 |  |  | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-15 18:00 |  |  | 22SD1
Sun_DS | Not Started | GLSTest-01.MLSTN.GEN |  |  | Key Dates |  |  | Sunday Day Shift Start | 0 | Start Milestone | 2023-07-16 06:00 |  |  | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-16 06:00 |  |  | 22SD1
Sun_NS | Not Started | GLSTest-01.MLSTN.GEN |  |  | Key Dates |  |  | Sunday Night Shift Start | 0 | Start Milestone | 2023-07-16 18:00 |  |  | 5 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-16 18:00 |  |  | 22SD1
10721617 - 0010 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0010 | Issue Permit - 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 07:30 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 07:30 | Bene Permit Issuer | 23SD2
10721617 - 0020 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0020 | Remove Trunnion Liner and Feed Spout | 0 | Task Dependent | 2023-07-14 07:30 | 2023-07-14 09:00 |  | 0 | 1.5 | 1.5 | 6 | 6 | 0 |  |  | 2023-07-14 07:30 | 2023-07-14 09:00 | Contract Rigger, Crane Operator, 55t Crane, Contract Fitter | 23SD2
10721617 - 0060 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0060 | Move feed chute to workshop for repairs | 0 | Task Dependent | 2023-07-14 07:30 | 2023-07-14 08:30 |  | 0.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-14 07:30 | 2023-07-14 08:30 | Contract Rigger, Crane Operator, Franna | 23SD2
10721617 - 0090 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0090 | Knock in 1 shell row | 0 | Task Dependent | 2023-07-14 09:00 | 2023-07-14 09:30 |  | 0 | 0.5 | 0.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-14 09:00 | 2023-07-14 09:30 | Bene Ops, Contract Fitter | 23SD2
10721617 - 0110 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0110 | Turn Mill | 0 | Task Dependent | 2023-07-14 09:30 | 2023-07-14 10:00 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 09:30 | 2023-07-14 10:00 | Bene Ops | 23SD2
10721617 - 0120 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0120 | Drain Mill | 0 | Task Dependent | 2023-07-14 10:00 | 2023-07-14 11:30 |  | 0 | 1.5 | 1.5 | 4.5 | 4.5 | 0 |  |  | 2023-07-14 10:00 | 2023-07-14 11:30 | Contract Fitter, Bene Ops | 23SD2
10721617 - 0140 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0140 | Lift and Install Mill Liner Handler | 0 | Task Dependent | 2023-07-14 11:30 | 2023-07-14 13:30 |  | 0 | 2 | 2 | 8 | 8 | 0 |  |  | 2023-07-14 11:30 | 2023-07-14 13:30 | Contract Rigger, Crane Operator, 55t Crane, Contract Fitter | 23SD2
10721617 - 0180 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0180 | Changeout 3 shell rows & 2 end row | 0 | Task Dependent | 2023-07-14 13:30 | 2023-07-14 19:30 |  | 0 | 4 | 4 | 16 | 16 | 0 |  |  | 2023-07-14 13:30 | 2023-07-14 19:30 | Contract Rigger, Crane Operator, 55t Crane, Contract Fitter | 23SD2
10721617 - 0220 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0220 | Turn Mill | 0 | Task Dependent | 2023-07-14 19:30 | 2023-07-14 20:00 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 19:30 | 2023-07-14 20:00 | Bene Ops | 23SD2
10721617 - 0230 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0230 | Changeout 2 shell rows & 2 end rows | 0 | Task Dependent | 2023-07-14 20:00 | 2023-07-14 23:00 |  | 0 | 3 | 3 | 12 | 12 | 0 |  |  | 2023-07-14 20:00 | 2023-07-14 23:00 | Contract Rigger, Crane Operator, 55t Crane, Contract Fitter | 23SD2
10721617 - 0270 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0270 | Turn Mill | 0 | Task Dependent | 2023-07-14 23:00 | 2023-07-14 23:30 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 23:00 | 2023-07-14 23:30 | Bene Ops | 23SD2
10721617 - 0280 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0280 | Changeout 3 shell rows & 1 end rows | 0 | Task Dependent | 2023-07-14 23:30 | 2023-07-15 03:00 |  | 0 | 3.5 | 3.5 | 14 | 14 | 0 |  |  | 2023-07-14 23:30 | 2023-07-15 03:00 | Contract Rigger, Crane Operator, 55t Crane, Contract Fitter | 23SD2
10721617 - 0320 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0320 | Turn Mill | 0 | Task Dependent | 2023-07-15 03:00 | 2023-07-15 03:30 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 03:00 | 2023-07-15 03:30 | Bene Ops | 23SD2
10721617 - 0330 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0330 | Changeout 3 shell rows & 1 end rows | 0 | Task Dependent | 2023-07-15 03:30 | 2023-07-15 09:00 |  | 0 | 3.5 | 3.5 | 14 | 14 | 0 |  |  | 2023-07-15 03:30 | 2023-07-15 09:00 | Contract Rigger, Crane Operator, 55t Crane, Contract Fitter | 23SD2
10721617 - 0370 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0370 | Turn Mill | 0 | Task Dependent | 2023-07-15 09:00 | 2023-07-15 09:30 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 09:00 | 2023-07-15 09:30 | Bene Ops | 23SD2
10721617 - 0380 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0380 | Changeout 3 shell rows & 2 end rows | 0 | Task Dependent | 2023-07-15 09:30 | 2023-07-15 13:00 |  | 0 | 3.5 | 3.5 | 14 | 14 | 0 |  |  | 2023-07-15 09:30 | 2023-07-15 13:00 | Contract Rigger, Crane Operator, 55t Crane, Contract Fitter | 23SD2
10721617 - 0420 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0420 | Turn Mill | 0 | Task Dependent | 2023-07-15 13:00 | 2023-07-15 13:30 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 13:00 | 2023-07-15 13:30 | Bene Ops | 23SD2
10721617 - 0430 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0430 | Changeout 2 shell rows & 1 end rows | 0 | Task Dependent | 2023-07-15 13:30 | 2023-07-15 16:00 |  | 0 | 2.5 | 2.5 | 10 | 10 | 0 |  |  | 2023-07-15 13:30 | 2023-07-15 16:00 | Contract Rigger, Crane Operator, 55t Crane, Contract Fitter | 23SD2
10721617 - 0470 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0470 | Turn Mill | 0 | Task Dependent | 2023-07-15 16:00 | 2023-07-15 16:30 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 16:00 | 2023-07-15 16:30 | Bene Ops | 23SD2
10721617 - 0480 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0480 | Changeout 3 shell rows & 2 end rows | 0 | Task Dependent | 2023-07-15 16:30 | 2023-07-15 22:30 |  | 0 | 4 | 4 | 16 | 16 | 0 |  |  | 2023-07-15 16:30 | 2023-07-15 22:30 | Contract Rigger, Crane Operator, 55t Crane, Contract Fitter | 23SD2
10721617 - 0520 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0520 | Turn Mill | 0 | Task Dependent | 2023-07-15 22:30 | 2023-07-15 23:00 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 22:30 | 2023-07-15 23:00 | Bene Ops | 23SD2
10721617 - 0530 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0530 | Changeout 2 shell rows & 2 end rows | 0 | Task Dependent | 2023-07-15 23:00 | 2023-07-16 01:30 |  | 0 | 2.5 | 2.5 | 10 | 10 | 0 |  |  | 2023-07-15 23:00 | 2023-07-16 01:30 | Contract Rigger, Crane Operator, 55t Crane, Contract Fitter | 23SD2
10721617 - 0570 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0570 | Turn Mill | 0 | Task Dependent | 2023-07-16 01:30 | 2023-07-16 02:00 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 01:30 | 2023-07-16 02:00 | Bene Ops | 23SD2
10721617 - 0580 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0580 | Changeout 2 shell rows & 2 end rows | 0 | Task Dependent | 2023-07-16 02:00 | 2023-07-16 04:30 |  | 0 | 2.5 | 2.5 | 10 | 10 | 0 |  |  | 2023-07-16 02:00 | 2023-07-16 04:30 | Contract Rigger, Crane Operator, 55t Crane, Contract Fitter | 23SD2
10721617 - 0620 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0620 | Turn Mill | 0 | Task Dependent | 2023-07-16 04:30 | 2023-07-16 05:00 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 04:30 | 2023-07-16 05:00 | Bene Ops | 23SD2
10721617 - 0630 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0630 | Changeout 2 shell rows & 1 end row | 0 | Task Dependent | 2023-07-16 07:00 | 2023-07-16 09:30 |  | 0 | 2.5 | 2.5 | 10 | 10 | 0 |  |  | 2023-07-16 07:00 | 2023-07-16 09:30 | Contract Rigger, Crane Operator, 55t Crane, Contract Fitter | 23SD2
10721617 - 0670 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0670 | Turn Mill | 0 | Task Dependent | 2023-07-16 09:30 | 2023-07-16 10:00 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 09:30 | 2023-07-16 10:00 | Bene Ops | 23SD2
10721617 - 0680 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0680 | Changeout 1 shell row & 1 end row | 0 | Task Dependent | 2023-07-16 10:00 | 2023-07-16 11:30 |  | 0 | 1.5 | 1.5 | 6 | 6 | 0 |  |  | 2023-07-16 10:00 | 2023-07-16 11:30 | Contract Rigger, Crane Operator, 55t Crane, Contract Fitter | 23SD2
10721617 - 0720 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0720 | Turn Mill | 0 | Task Dependent | 2023-07-16 11:30 | 2023-07-16 12:00 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 11:30 | 2023-07-16 12:00 | Bene Ops | 23SD2
10721617 - 0730 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0730 | Changeout 1 shell row & 1 end row | 0 | Task Dependent | 2023-07-16 12:00 | 2023-07-16 13:00 |  | 0 | 1 | 1 | 4 | 4 | 0 |  |  | 2023-07-16 12:00 | 2023-07-16 13:00 | Contract Rigger, Crane Operator, 55t Crane, Contract Fitter | 23SD2
10721617 - 0770 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0770 | Move feed chute back to jobsite | 0 | Task Dependent | 2023-07-16 12:00 | 2023-07-16 13:00 |  | 0 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-16 12:00 | 2023-07-16 13:00 | Contract Rigger, Crane Operator, Franna | 23SD2
10721617 - 0800 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0800 | Remove Mill Liner Handler | 0 | Task Dependent | 2023-07-16 13:00 | 2023-07-16 15:00 |  | 0 | 2 | 2 | 8 | 8 | 0 |  |  | 2023-07-16 13:00 | 2023-07-16 15:00 | Contract Rigger, Crane Operator, 55t Crane, Contract Fitter | 23SD2
10721617 - 0840 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0840 | Install Trunnion Liner and Feed Spout | 0 | Task Dependent | 2023-07-16 15:00 | 2023-07-16 16:30 |  | 0 | 1.5 | 1.5 | 6 | 6 | 0 |  |  | 2023-07-16 15:00 | 2023-07-16 16:30 | Contract Rigger, Crane Operator, 55t Crane, Contract Fitter | 23SD2
10721617 - 0880 | Not Started | GLSTest-01.BENE.MAINT.2132 | DAWSON1 | Beneficiation | 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 10721617 | 0880 | Close Permit - 10721617 - 2Y Mech Insp Ball Mill Reline/Crack Shut | 0 | Task Dependent | 2023-07-16 16:30 | 2023-07-16 17:00 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 16:30 | 2023-07-16 17:00 | Bene Permit Issuer | 23SD2
BENE.DEISO.5050 | Not Started | GLSTest-01.BENE.DE-ISO | PHOS | Beneficiation | De-Isolations |  |  | De-Isolate Deslime Cyclone Overflow Pump | 0 | Task Dependent | 2023-07-16 17:00 | 2023-07-16 18:00 |  | 5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-16 17:00 | 2023-07-16 18:00 | Bene Ops | 22SD1
BENE.DEISO.5070 | Not Started | GLSTest-01.BENE.DE-ISO | PHOS | Beneficiation | De-Isolations |  |  | De-Isolate Agitator Slurry Storage | 0 | Task Dependent | 2023-07-16 20:00 | 2023-07-16 21:00 |  | 5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-16 20:00 | 2023-07-16 21:00 | Bene Ops | 22SD1
BENE.DEISO.5010 | Not Started | GLSTest-01.BENE.DE-ISO | PHOS | Beneficiation | De-Isolations |  |  | De-Isolate Slurry Storage Fd Pumps | 0 | Task Dependent | 2023-07-15 18:30 | 2023-07-15 19:30 |  | 23.5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-15 18:30 | 2023-07-15 19:30 | Bene Ops | 22SD1
BENE.DEISO.5100 | Not Started | GLSTest-01.BENE.DE-ISO | PHOS | Beneficiation | De-Isolations |  |  | De-Isolate Feeder - ROM | 0 | Task Dependent | 2023-07-16 23:30 | 2023-07-17 00:30 |  | 0 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-16 23:30 | 2023-07-17 00:30 | Bene Ops | 22SD1
BENE.DEISO.5090 | Not Started | GLSTest-01.BENE.DE-ISO | PHOS | Beneficiation | De-Isolations |  |  | De-Isolate Coarse Ore & Stockpiling | 0 | Task Dependent | 2023-07-16 23:00 | 2023-07-16 23:30 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 23:00 | 2023-07-16 23:30 | Bene Ops | 22SD1
ISOL5020 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations |  |  | Isolate Delivery Pumps to Phos Acid | 0 | Task Dependent | 2023-07-14 23:00 | 2023-07-15 01:00 |  | 39 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-14 23:00 | 2023-07-15 01:00 | Phos Acid Isolator | 22SD1
DE-ISOL5020 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Services |  |  | De-Isolate Delivery Pumps to Phos Acid | 0 | Task Dependent | 2023-07-16 10:00 | 2023-07-16 12:00 |  | 26.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-16 10:00 | 2023-07-16 12:00 | Phos Acid Isolator | 22SD1
PHOS.ISO.2130 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Hemihydrate Reaction |  |  | Isolate Reactor Skid Pump | 0 | Task Dependent | 2023-07-14 23:00 | 2023-07-14 23:30 |  | 31 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-14 23:00 | 2023-07-14 23:30 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5010 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Hemihydrate Reaction |  |  | De-Isolate Reactor Skid Pump | 0 | Task Dependent | 2023-07-15 01:30 | 2023-07-15 02:30 |  | 44 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-15 01:30 | 2023-07-15 02:30 | Phos Acid Isolator | 22SD1
PHOS.ISO.2340 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Product Filtration |  |  | Isolate Return Acid Tank A Agitator | 0 | Task Dependent | 2023-07-15 18:30 | 2023-07-15 19:00 |  | 31.1 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-15 18:30 | 2023-07-15 19:00 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5050 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Product Filtration |  |  | De-Isolate Return Acid Tank A Agitator | 0 | Task Dependent | 2023-07-15 21:54 | 2023-07-15 22:24 |  | 52.1 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 21:54 | 2023-07-15 22:24 | Phos Acid Isolator | 22SD1
PHOS.ISO.2290 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Product Filtration |  |  | Isolate Return Acid Tank B Agitator | 0 | Task Dependent | 2023-07-15 10:00 | 2023-07-15 10:30 |  | 29.5 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-15 10:00 | 2023-07-15 10:30 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5170 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Product Filtration |  |  | De-Isolate Return Acid Tank B Agitator | 0 | Task Dependent | 2023-07-16 15:30 | 2023-07-16 16:00 |  | 23 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 15:30 | 2023-07-16 16:00 | Phos Acid Isolator | 22SD1
PHOS.ISO.2310 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Product Filtration |  |  | Isolate Product Acid Pump B | 0 | Task Dependent | 2023-07-15 10:30 | 2023-07-15 11:00 |  | 29.5 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-15 10:30 | 2023-07-15 11:00 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5150 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Product Filtration |  |  | De-Isolate Product Acid Pump B | 0 | Task Dependent | 2023-07-16 15:00 | 2023-07-16 15:30 |  | 23 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-16 15:00 | 2023-07-16 15:30 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5030 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Product Filtration |  |  | De-Isolate Vacuum pump A seal water | 0 | Task Dependent | 2023-07-15 19:30 | 2023-07-15 21:30 |  | 39 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-15 19:30 | 2023-07-15 21:30 | Phos Acid Isolator | 22SD1
PHOS.ISO.2300 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Product Filtration |  |  | Isolate Vacuum pump A seal water | 0 | Task Dependent | 2023-07-15 10:00 | 2023-07-15 10:30 |  | 39 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-15 10:00 | 2023-07-15 10:30 | Phos Acid Isolator | 22SD1
PHOS.ISO.2010 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Product Storage |  |  | Isolate Intermediate Acid Pump Manifold | 0 | Task Dependent | 2023-07-14 06:00 | 2023-07-14 07:00 |  | 66 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-14 06:00 | 2023-07-14 07:00 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5000 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Product Storage |  |  | De-Isolate Intermediate Acid Pump Manifold | 0 | Task Dependent | 2023-07-14 17:30 | 2023-07-14 18:30 |  | 68 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-14 17:30 | 2023-07-14 18:30 | Phos Acid Isolator | 22SD1
BENE.ISO.2110 | Not Started | GLSTest-01.BENE.ISO | PHOS | Beneficiation | Isolations |  |  | Isolate Process Water to Process Water Tank | 0 | Task Dependent | 2023-07-15 21:00 | 2023-07-15 23:00 |  | 15 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-15 21:00 | 2023-07-15 23:00 | Bene Ops | 22SD1
BENE.DEISO.5020 | Not Started | GLSTest-01.BENE.DE-ISO | PHOS | Beneficiation | De-Isolations |  |  | De-Isolate Process Water to Process Water Tank | 0 | Task Dependent | 2023-07-16 08:00 | 2023-07-16 10:00 |  | 13 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-16 08:00 | 2023-07-16 10:00 | Bene Ops | 22SD1
10692425 - 0095 | Not Started | GLSTest-01.BENE.MAINT.2122 | DAWSON2 | Beneficiation | 10692425 - cyclone cluster product downleg holed | 10692425 | 0090 | Replace mining hose | 0 | Task Dependent | 2023-07-16 13:30 | 2023-07-16 15:30 |  | 0 | 2 | 2 | 8 | 8 | 0 |  |  | 2023-07-16 13:30 | 2023-07-16 15:30 | 55t Crane, Crane Operator, Rigger, Fitter | 23SD2
10797950 - 0021 | Not Started | GLSTest-01.GRAN.MAINT.4622 | CLEAN 1 | Granulation | 10797950 - 15W HPWB Cln GranSD 46CK2401 | 10797950 | 0020 | HPWB Dryer screw conveyor | 0 | Task Dependent | 2023-07-12 22:30 | 2023-07-13 02:30 |  | 3.5 | 4 | 4 | 12 | 12 | 0 |  |  | 2023-07-12 22:30 | 2023-07-13 02:30 | Waterblast Truck, Cleaning Ops | 23SD2
BENE.MS.1050 | Not Started | GLSTest-01.MLSTN.BENE | BENE |  | Key Dates |  |  | Bene Feed On 12 hr Weather Contingency | 0 | Task Dependent | 2023-07-17 02:00 | 2023-07-17 14:00 |  | 0 | 12 | 12 | 0 | 0 | 0 |  |  | 2023-07-17 02:00 | 2023-07-17 14:00
PAFON-100-WEATHER10 | Not Started | GLSTest-01.MLSTN.BENE | BENE |  | Key Dates |  |  | Bene Feed On (w/ Weather Contingency) | 0 | Finish Milestone |  | 2023-07-17 14:00 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-07-17 14:00 |  | 22SD1
10810277 - 0061 | Not Started | GLSTest-01.GRAN.MAINT.4622 | PROJECT | Granulation | 10810277 - Installation of Chute Nozzles | 10797919 | 0140 | Remove Northern Wall Liners for Chute Nozzles (CSE) | 0 | Task Dependent | 2023-07-14 01:00 | 2023-07-14 09:00 |  | 9 | 6 | 6 | 24 | 24 | 0 |  |  | 2023-07-14 01:00 | 2023-07-14 09:00 | Contract TA, Contract Fitter | 23SD2
10810277 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4622 | PROJECT | Granulation | 10810277 - Installation of Chute Nozzles | 10797919 | 0020 | Erect Scaffold platform inside chute (CSE) | 0 | Task Dependent | 2023-07-13 20:00 | 2023-07-14 |  | 9 | 4 | 4 | 16 | 16 | 0 |  |  | 2023-07-13 20:00 | 2023-07-14 | Contract TA, Scaffolder | 23SD2
10810277 - 0062 | Not Started | GLSTest-01.GRAN.MAINT.4622 | PROJECT | Granulation | 10810277 - Installation of Chute Nozzles | 10797919 | 0160 | Replace Northern Wall Liners (CSE) | 0 | Task Dependent | 2023-07-14 19:00 | 2023-07-15 01:00 |  | 9 | 6 | 6 | 24 | 24 | 0 |  |  | 2023-07-14 19:00 | 2023-07-15 01:00 | Contract TA, Contract Fitter | 23SD2
10810277 - 0100 | Not Started | GLSTest-01.GRAN.MAINT.4622 | PROJECT | Granulation | 10810277 - Installation of Chute Nozzles | 10797919 | 0150 | Strip internal scaff (CSE) | 0 | Task Dependent | 2023-07-15 01:00 | 2023-07-15 04:00 |  | 9 | 3 | 3 | 12 | 12 | 0 |  |  | 2023-07-15 01:00 | 2023-07-15 04:00 | Contract TA, Scaffolder | 23SD2
10810277 - 110 | Not Started | GLSTest-01.GRAN.MAINT.4622 | PROJECT | Granulation | 10810277 - Installation of Chute Nozzles | 10810277 | 0050 | Cut Holes and Weld Nozzles (CSE) | 0 | Task Dependent | 2023-07-14 09:00 | 2023-07-14 17:00 |  | 9 | 8 | 8 | 24 | 24 | 0 |  |  | 2023-07-14 09:00 | 2023-07-14 17:00 | Contract TA, Contract BMW | 23SD2
10787923 - 0065 | Not Started | GLSTest-01.GRAN.MAINT.4621 | BMW | Granulation | 10787923 - MF-Replace sulphuric acid pipe - PN | 10787923 | 0020 | Internal Scaff (CSE) | 0 | Task Dependent | 2023-07-13 22:30 | 2023-07-14 02:30 |  | 9.5 | 4 | 4 | 16 | 16 | 0 |  |  | 2023-07-13 22:30 | 2023-07-14 02:30 | T/A, Scaffolder | 23SD2
10811685 - 0005 | Not Started | GLSTest-01.BENE.MAINT.2142 | DAWSON2 | Beneficiation | 10811685 - FI-Main Slurry line,Tpiece to Surry tank | 10811685 | 0005 | Issue Permit - 10811685 - FI-Main Slurry line,Tpiece to Surry tank | 0 | Task Dependent | 2023-07-15 19:00 | 2023-07-15 19:30 |  | 11 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 19:00 | 2023-07-15 19:30 | Bene Permit Issuer | 23SD2EM1
10811685 - 0010 | Not Started | GLSTest-01.BENE.MAINT.2142 | DAWSON2 | Beneficiation | 10811685 - FI-Main Slurry line,Tpiece to Surry tank | 10811685 | 0010 | Change Out Pipe | 0 | Task Dependent | 2023-07-15 19:30 | 2023-07-16 00:30 |  | 11 | 5 | 5 | 10 | 10 | 0 |  |  | 2023-07-15 19:30 | 2023-07-16 00:30 | Fitter | 23SD2EM1
10811685 - 0040 | Not Started | GLSTest-01.BENE.MAINT.2142 | DAWSON2 | Beneficiation | 10811685 - FI-Main Slurry line,Tpiece to Surry tank | 10811685 | 0040 | Change Out Pipe | 0 | Task Dependent | 2023-07-15 19:30 | 2023-07-15 22:30 |  | 13 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-15 19:30 | 2023-07-15 22:30 | Rigger, Crane Operator, Franna | 23SD2EM1
10811685 - 0045 | Not Started | GLSTest-01.BENE.MAINT.2142 | DAWSON2 | Beneficiation | 10811685 - FI-Main Slurry line,Tpiece to Surry tank | 10811685 | 0045 | Close Permit - 10811685 - FI-Main Slurry line,Tpiece to Surry tank | 0 | Task Dependent | 2023-07-16 00:30 | 2023-07-16 01:00 |  | 11 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 00:30 | 2023-07-16 01:00 | Bene Permit Issuer | 23SD2EM1
10813635 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4420 | RUBBER | Phos Acid | 10813635 - RW belt change on reactor feed conveyor. | 10813635 | 0010 | Issue Permit - 10813635 - RW belt change on reactor feed conveyor. | 0 | Task Dependent | 2023-07-14 20:00 | 2023-07-14 20:30 |  | 23 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 20:00 | 2023-07-14 20:30 | Phos Permit Issuer | 23SD2EM1
10813635 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4420 | RUBBER | Phos Acid | 10813635 - RW belt change on reactor feed conveyor. | 10813635 | 0020 | Cleaning around feed chute at tail end a | 0 | Task Dependent | 2023-07-14 20:30 | 2023-07-14 23:30 |  | 23 | 3 | 3 | 9 | 9 | 0 |  |  | 2023-07-14 20:30 | 2023-07-14 23:30 | Waterblast Truck, Cleaning Ops | 23SD2EM1
10813635 - 0050 | Not Started | GLSTest-01.PHOS.MAINT.4420 | RUBBER | Phos Acid | 10813635 - RW belt change on reactor feed conveyor. | 10813635 | 0050 | Franna rigger Lift counter weight | 0 | Task Dependent | 2023-07-14 23:30 | 2023-07-15 01:30 |  | 23 | 2 | 2 | 6 | 6 | 0 |  |  | 2023-07-14 23:30 | 2023-07-15 01:30 | Franna, 45ft EWP, Crane Operator, T/A, Rigger | 23SD2EM1
10813635 - 0090 | Not Started | GLSTest-01.PHOS.MAINT.4420 | RUBBER | Phos Acid | 10813635 - RW belt change on reactor feed conveyor. | 10813635 | 0090 | RW belt change on reactor feed conveyor | 0 | Task Dependent | 2023-07-15 01:30 | 2023-07-15 13:30 |  | 23 | 10 | 10 | 30 | 30 | 0 |  |  | 2023-07-15 01:30 | 2023-07-15 13:30 | Rubber | 23SD2EM1
10813635 - 0100 | Not Started | GLSTest-01.PHOS.MAINT.4420 | RUBBER | Phos Acid | 10813635 - RW belt change on reactor feed conveyor. | 10813635 | 0100 | RW belt change on reactor feed conveyor. | 0 | Task Dependent | 2023-07-15 13:30 | 2023-07-16 01:30 |  | 23 | 10 | 10 | 30 | 30 | 0 |  |  | 2023-07-15 13:30 | 2023-07-16 01:30 | Rubber | 23SD2EM1
10813635 - 0120 | Not Started | GLSTest-01.PHOS.MAINT.4420 | RUBBER | Phos Acid | 10813635 - RW belt change on reactor feed conveyor. | 10813635 | 0120 | Franna rigger Lower counter weight | 0 | Task Dependent | 2023-07-16 01:30 | 2023-07-16 03:30 |  | 27 | 2 | 2 | 8 | 8 | 0 |  |  | 2023-07-16 01:30 | 2023-07-16 03:30 | 45ft EWP, Franna, Rigger, Crane Operator, T/A, Rigger | 23SD2EM1
10813635 - 0160 | Not Started | GLSTest-01.PHOS.MAINT.4420 | RUBBER | Phos Acid | 10813635 - RW belt change on reactor feed conveyor. | 10813635 | 0160 | Close Permit - 10813635 - RW belt change on reactor feed conveyor. | 0 | Task Dependent | 2023-07-16 03:30 | 2023-07-16 04:00 |  | 27 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 03:30 | 2023-07-16 04:00 | Phos Permit Issuer | 23SD2EM1
10813968 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10813968 - Replace bolts in sparger arm | 10813968 | 0010 | Issue permit - 10813968 - Replace bolts in sparger arm | 0 | Task Dependent | 2023-07-14 03:00 | 2023-07-14 03:30 |  | 11 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 03:00 | 2023-07-14 03:30 | Gran Permit Issuer | 23SD2EM1
10813968 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10813968 - Replace bolts in sparger arm | 10813968 | 0020 | Set up rigging equipment | 0 | Task Dependent | 2023-07-14 03:30 | 2023-07-14 04:30 |  | 11 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-14 03:30 | 2023-07-14 04:30 | Rigger | 23SD2EM1
10813968 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10813968 - Replace bolts in sparger arm | 10813968 | 0030 | Remove existing bolts in sparger arm (CSE) | 0 | Task Dependent | 2023-07-14 04:30 | 2023-07-14 09:30 |  | 11 | 3 | 3 | 9 | 9 | 0 |  |  | 2023-07-14 04:30 | 2023-07-14 09:30 | T/A, Fitter | 23SD2EM1
10813968 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10813968 - Replace bolts in sparger arm | 10813968 | 0040 | Split plate faces (CSE) | 0 | Task Dependent | 2023-07-14 09:30 | 2023-07-14 12:30 |  | 11 | 3 | 3 | 12 | 12 | 0 |  |  | 2023-07-14 09:30 | 2023-07-14 12:30 | T/A, Fitter, Rigger | 23SD2EM1
10813968 - 0060 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10813968 - Replace bolts in sparger arm | 10813968 | 0060 | Inspect & clean face surfaces (CSE) | 0 | Task Dependent | 2023-07-14 12:30 | 2023-07-14 20:30 |  | 11 | 6 | 6 | 18 | 18 | 0 |  |  | 2023-07-14 12:30 | 2023-07-14 20:30 | T/A, Fitter | 23SD2EM1
10813968 - 0070 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10813968 - Replace bolts in sparger arm | 10813968 | 0070 | Reconnect sparger (CSE) | 0 | Task Dependent | 2023-07-14 20:30 | 2023-07-14 23:30 |  | 11 | 3 | 3 | 12 | 12 | 0 |  |  | 2023-07-14 20:30 | 2023-07-14 23:30 | T/A, Fitter, Rigger | 23SD2EM1
10813968 - 0090 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10813968 - Replace bolts in sparger arm | 10813968 | 0090 | Torque bolts (CSE) | 0 | Task Dependent | 2023-07-14 23:30 | 2023-07-15 02:30 |  | 11 | 3 | 3 | 9 | 9 | 0 |  |  | 2023-07-14 23:30 | 2023-07-15 02:30 | T/A, Fitter | 23SD2EM1
10813968 - 0100 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10813968 - Replace bolts in sparger arm | 10813968 | 0100 | Remove rigging equipment | 0 | Task Dependent | 2023-07-15 02:30 | 2023-07-15 03:30 |  | 11 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-15 02:30 | 2023-07-15 03:30 | Rigger | 23SD2EM1
10813968 - 0110 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON2 | Granulation | 10813968 - Replace bolts in sparger arm | 10813968 | 0110 | Close permit - 10813968 - Replace bolts in sparger arm | 0 | Task Dependent | 2023-07-15 03:30 | 2023-07-15 04:00 |  | 11 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 03:30 | 2023-07-15 04:00 | Gran Permit Issuer | 23SD2EM1
10798126 - 0026 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 2 | Granulation | 10798126 - 15W HPWB Cln GranSD SU2801 | 10806721 | 0020 | HPWB Dryer Lobsterback | 0 | Task Dependent | 2023-07-13 01:00 | 2023-07-13 04:00 |  | 3 | 3 | 3 | 9 | 9 | 0 |  |  | 2023-07-13 01:00 | 2023-07-13 04:00 | Waterblast Truck, Cleaning Ops | 23SD2
10798125 - 0025 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 2 | Granulation | 10798125 - 15W HPWB Cln GranSD SU2802 | 10810928 | 0020 | HPWB RGV Lobsterback | 0 | Task Dependent | 2023-07-13 04:00 | 2023-07-13 09:00 |  | 3 | 3 | 3 | 9 | 9 | 0 |  |  | 2023-07-13 04:00 | 2023-07-13 09:00 | Waterblast Truck, Cleaning Ops | 23SD2
10798138 - 0016 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 2 | Granulation | 10798138 - 15W HPWB Cln GranSD 46SU2701 | 10810927 | 0020 | HPWB Pre-Scrubber Lobsterback | 0 | Task Dependent | 2023-07-13 04:00 | 2023-07-13 09:00 |  | 0 | 3 | 3 | 9 | 9 | 0 |  |  | 2023-07-13 04:00 | 2023-07-13 09:00 | Waterblast Truck, Cleaning Ops | 23SD2
10798138 - 0015 | Not Started | GLSTest-01.GRAN.MAINT.4628 | CLEAN 2 | Granulation | 10798138 - 15W HPWB Cln GranSD 46SU2701 | 10810927 | 0030 | HPWB PN Lobsterback | 0 | Task Dependent | 2023-07-13 01:00 | 2023-07-13 04:00 |  | 0 | 3 | 3 | 9 | 9 | 0 |  |  | 2023-07-13 01:00 | 2023-07-13 04:00 | Waterblast Truck, Cleaning Ops | 23SD2
10795474 - 0075 | Not Started | GLSTest-01.GRAN.MAINT.9999 | CLEAN 2 | Granulation | 10795474 - 30W HPWB Cln GranSD 46PP99DD01 | 10810931 | 0030 | HPWB Cooler Lobsterback | 0 | Task Dependent | 2023-07-13 09:00 | 2023-07-13 12:00 |  | 0 | 3 | 3 | 9 | 9 | 0 |  |  | 2023-07-13 09:00 | 2023-07-13 12:00 | Waterblast Truck, Cleaning Ops | 23SD2
10794028 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4425 | PROJECT | Phos Acid | 10794028 - Increase process water line diameter | 10794028 | 0010 | Issue Permit - 10794028 - Increase process water line diameter | 0 | Task Dependent | 2023-07-16 06:30 | 2023-07-16 07:00 |  | 4.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 06:30 | 2023-07-16 07:00 | Phos Permit Issuer | 23SD2
10794028 - 0035 | Not Started | GLSTest-01.PHOS.MAINT.4425 | PROJECT | Phos Acid | 10794028 - Increase process water line diameter | 10794028 | 0020 | Close Permit - 10794028 - Increase process water line diameter | 0 | Task Dependent | 2023-07-16 17:00 | 2023-07-16 17:30 |  | 18.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 17:00 | 2023-07-16 17:30 | Phos Permit Issuer | 23SD2
10794028 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4425 | PROJECT | Phos Acid | 10794028 - Increase process water line diameter | 10794028 | 0030 | Remove old pipework and install new line | 0 | Task Dependent | 2023-07-16 07:00 | 2023-07-16 17:00 |  | 4.5 | 10 | 10 | 30 | 30 | 0 |  |  | 2023-07-16 07:00 | 2023-07-16 17:00 | Contract BMW, Contract TA, 80ft EWP | 23SD2
10796671 - 0025 | Not Started | GLSTest-01.GRAN.MAINT.4625 | ENG | Granulation | 10796671 - 210W REng Insp GndFlrFan GranSD ProdClng | 10796671 | 0030 | Remove hatches | 0 | Task Dependent | 2023-07-13 01:00 | 2023-07-13 01:30 |  | 47 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-13 01:00 | 2023-07-13 01:30 | Fitter | 23SD2
10798378 - 0025 | Not Started | GLSTest-01.GRAN.MAINT.4622 | ELEC | Granulation | 10798378 - 30W Elec Rplc Brnr Mjr GranSD Grnltn | 10798378 | 0020 | Close Burner | 0 | Task Dependent | 2023-07-13 21:00 | 2023-07-13 22:00 |  | 20 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-13 21:00 | 2023-07-13 22:00 | Fitter | 23SD2
10787923 - 0066 | Not Started | GLSTest-01.GRAN.MAINT.4621 | BMW | Granulation | 10787923 - MF-Replace sulphuric acid pipe - PN | 10787923 | 0020 | Remove Internal Scaff (CSE) | 0 | Task Dependent | 2023-07-14 09:30 | 2023-07-14 11:30 |  | 9.5 | 2 | 2 | 8 | 8 | 0 |  |  | 2023-07-14 09:30 | 2023-07-14 11:30 | T/A, Scaffolder | 23SD2
PHOS.RD.1200 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Hemihydrate Reaction |  |  | Lower Reactor 1A by 1m | 0 | Task Dependent | 2023-07-14 21:00 | 2023-07-14 23:00 |  | 0 | 2 | 2 | 2 | 2 | 0 |  |  | 2023-07-14 21:00 | 2023-07-14 23:00 | Phos Ops | 22SD1
10789868 - 0025 | Not Started | GLSTest-01.PHOS.MAINT.4475 | PHOS | Phos Acid | 10789868 - 15W HPWB Cln PhosSD 44MS3008 | 10789868 | 0020 | Middle Trenches - Mini Excavator Digout | 0 | Task Dependent | 2023-07-15 19:00 | 2023-07-16 01:30 |  | 10.5 | 6.5 | 6.5 | 13 | 13 | 0 |  |  | 2023-07-15 19:00 | 2023-07-16 01:30 | T/A, Phos Ops, Mini Excavator, Bobcat | 23SD2
10789868 - 0026 | Not Started | GLSTest-01.PHOS.MAINT.4475 | PHOS | Phos Acid | 10789868 - 15W HPWB Cln PhosSD 44MS3008 | 10789868 | 0020 | Eastern Trenches - Mini Excavator Digout | 0 | Task Dependent | 2023-07-15 10:30 | 2023-07-15 17:00 |  | 10.5 | 6.5 | 6.5 | 13 | 13 | 0 |  |  | 2023-07-15 10:30 | 2023-07-15 17:00 | T/A, Phos Ops, Mini Excavator, Bobcat | 23SD2
PHOS.RD.1210 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Hemihydrate Reaction |  |  | Drain and purge discharge lines to R2 (H2S04) | 0 | Task Dependent | 2023-07-14 21:00 | 2023-07-14 23:00 |  | 28.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-14 21:00 | 2023-07-14 23:00 | Phos Ops | 22SD1
PHOS.RD.1000 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Product Filtration |  |  | C Side Plant Wash @ 80 Degrees | 0 | Task Dependent | 2023-07-12 04:00 | 2023-07-12 16:00 |  | 50 | 12 | 12 | 12 | 12 | 0 |  |  | 2023-07-12 04:00 | 2023-07-12 16:00 | Phos Ops | 22SD1
PWR4001 | Not Started | GLSTest-01.PWR.ISO | PWR | Power Station | Power Station Assistance |  |  | Thursday - Power Stations Ops Assistance | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 13:00 |  | 80.5 | 6 | 6 | 6 | 6 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 13:00 | Pwr Ops | 22SD1
PWR4002 | Not Started | GLSTest-01.PWR.ISO | PWR | Power Station | Power Station Assistance |  |  | Friday - Power Stations Ops Assistance | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 13:00 |  | 66.5 | 6 | 6 | 6 | 6 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 13:00 | Pwr Ops | 22SD1
PWR4003 | Not Started | GLSTest-01.PWR.ISO | PWR | Power Station | Power Station Assistance |  |  | Saturday - Power Stations Ops Assistance | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 13:00 |  | 52.5 | 6 | 6 | 6 | 6 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 13:00 | Pwr Ops | 22SD1
PWR4004 | Not Started | GLSTest-01.PWR.ISO | PWR | Power Station | Power Station Assistance |  |  | Sunday - Power Stations Ops Assistance | 0 | Task Dependent | 2023-07-16 07:00 | 2023-07-16 13:00 |  | 38.5 | 6 | 6 | 6 | 6 | 0 |  |  | 2023-07-16 07:00 | 2023-07-16 13:00 | Pwr Ops | 22SD1
10766816 - 0011 | Not Started | GLSTest-01.PWR.MAINT.MISC | PWR | Power Station | 10766816 - Generator Elec Stat Testing | 10766816 | 0010 | Generator Elec Stat Testing - Day 2 | 0 | Task Dependent | 2023-07-14 13:00 | 2023-07-14 16:00 |  | 72.5 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-14 13:00 | 2023-07-14 16:00 | Pwr Elec | 23SD2
10766816 - 0012 | Not Started | GLSTest-01.PWR.MAINT.MISC | PWR | Power Station | 10766816 - Generator Elec Stat Testing | 10766816 | 0010 | Generator Elec Stat Testing - Day 3 | 0 | Task Dependent | 2023-07-15 13:00 | 2023-07-15 16:00 |  | 55.5 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-15 13:00 | 2023-07-15 16:00 | Pwr Elec | 23SD2
10766816 - 0013 | Not Started | GLSTest-01.PWR.MAINT.MISC | PWR | Power Station | 10766816 - Generator Elec Stat Testing | 10766816 | 0010 | Generator Elec Stat Testing - Day 4 | 0 | Task Dependent | 2023-07-16 13:00 | 2023-07-16 16:00 |  | 38.5 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-16 13:00 | 2023-07-16 16:00 | Pwr Elec | 23SD2
GRAN.DEISO.5010 | Not Started | GLSTest-01.GRAN.DE-ISO | GRAN | Granulation | De-Isolations |  |  | De-Isolate Product Screen Conveyor | 0 | Task Dependent | 2023-07-13 20:30 | 2023-07-13 21:30 |  | 49 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-13 20:30 | 2023-07-13 21:30 | Gran Ops | 22SD1
GRAN.ISO.2140 | Not Started | GLSTest-01.GRAN.ISO | GRAN | Granulation | Isolations |  |  | Isolate Product Screen Conveyor | 0 | Task Dependent | 2023-07-13 15:30 | 2023-07-13 16:00 |  | 42 | 0.5 | 0.5 | 2 | 2 | 0 |  |  | 2023-07-13 15:30 | 2023-07-13 16:00 | Gran Ops | 22SD1
GRAN.ISO.2130 | Not Started | GLSTest-01.GRAN.ISO | GRAN | Granulation | Isolations |  |  | Isolate G69 Coating Oil Tank | 0 | Task Dependent | 2023-07-13 02:30 | 2023-07-13 04:30 |  | 34.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-13 02:30 | 2023-07-13 04:30 | Gran Ops | 22SD3
GRAN.DEISO.5020 | Not Started | GLSTest-01.GRAN.DE-ISO | GRAN | Granulation | De-Isolations |  |  | De-Isolate G69 Coating Oil Tank | 0 | Task Dependent | 2023-07-14 02:00 | 2023-07-14 03:00 |  | 43.5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-14 02:00 | 2023-07-14 03:00 | Gran Ops | 22SD3
GRAN.DEISO.5000 | Not Started | GLSTest-01.GRAN.DE-ISO | GRAN | Granulation | De-Isolations |  |  | De-Isolate Surge Hopper | 0 | Task Dependent | 2023-07-13 16:30 | 2023-07-13 17:00 |  | 49 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 16:30 | 2023-07-13 17:00 | Gran Ops | 22SD1
10796189 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4435 | PROJECT | Phos Acid | 10796189 - ELEC - Plant wash air actuated valves | 10796189 | 0010 | Install Plant wash air actuated valves | 0 | Task Dependent | 2023-07-16 08:00 | 2023-07-16 14:00 |  | 8.5 | 6 | 6 | 12 | 12 | 0 |  |  | 2023-07-16 08:00 | 2023-07-16 14:00 | Contract Fitter | 23SD2
10796189 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4435 | PROJECT | Phos Acid | 10796189 - ELEC - Plant wash air actuated valves | 10796189 | 0020 | Tube To Valves | 0 | Task Dependent | 2023-07-16 08:00 | 2023-07-16 14:00 |  | 8.5 | 6 | 6 | 6 | 6 | 0 |  |  | 2023-07-16 08:00 | 2023-07-16 14:00 | Contract Elec | 23SD2
10796189 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4435 | PROJECT | Phos Acid | 10796189 - ELEC - Plant wash air actuated valves | 10796189 | 0030 | Issue Permit - 10796189 - ELEC - Plant wash air actuated valves | 0 | Task Dependent | 2023-07-16 07:00 | 2023-07-16 08:00 |  | 8.5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-16 07:00 | 2023-07-16 08:00 | Phos Permit Issuer | 23SD2
10796189 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4435 | PROJECT | Phos Acid | 10796189 - ELEC - Plant wash air actuated valves | 10796189 | 0040 | Close Permit - 10796189 - ELEC - Plant wash air actuated valves | 0 | Task Dependent | 2023-07-16 14:00 | 2023-07-16 15:00 |  | 8.5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-16 14:00 | 2023-07-16 15:00 | Phos Permit Issuer | 23SD2
10733670 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4440 | PROJECT | Phos Acid | 10733670 - HF Fume Dctng Syst Supply Cam B Hatches | 10733670 | 0010 | Issue Permit - 10733670 - HF Fume Dctng Syst Supply Cam B Hatches | 0 | Task Dependent | 2023-07-15 03:00 | 2023-07-15 03:30 |  | 6.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 03:00 | 2023-07-15 03:30 | Phos Permit Issuer | 23SD2
10733670 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4440 | PROJECT | Phos Acid | 10733670 - HF Fume Dctng Syst Supply Cam B Hatches | 10733670 | 0020 | Cut and install hatch. loc 1 | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 10:00 |  | 5 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 10:00 | Contract Fibreglasser | 23SD2
10733670 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4440 | PROJECT | Phos Acid | 10733670 - HF Fume Dctng Syst Supply Cam B Hatches | 10733670 | 0030 | Cut and install hatch. loc 2 | 0 | Task Dependent | 2023-07-15 10:00 | 2023-07-15 13:00 |  | 5 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-15 10:00 | 2023-07-15 13:00 | Contract Fibreglasser | 23SD2
10733670 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4440 | PROJECT | Phos Acid | 10733670 - HF Fume Dctng Syst Supply Cam B Hatches | 10733670 | 0040 | Cut and install hatch. loc 3 | 0 | Task Dependent | 2023-07-15 13:00 | 2023-07-15 16:00 |  | 5 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-15 13:00 | 2023-07-15 16:00 | Contract Fibreglasser | 23SD2
10733670 - 0050 | Not Started | GLSTest-01.PHOS.MAINT.4440 | PROJECT | Phos Acid | 10733670 - HF Fume Dctng Syst Supply Cam B Hatches | 10733670 | 0050 | Cut and install hatch. loc 4 | 0 | Task Dependent | 2023-07-15 16:00 | 2023-07-16 09:00 |  | 5 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-15 16:00 | 2023-07-16 09:00 | Contract Fibreglasser | 23SD2
10733670 - 0060 | Not Started | GLSTest-01.PHOS.MAINT.4440 | PROJECT | Phos Acid | 10733670 - HF Fume Dctng Syst Supply Cam B Hatches | 10733670 | 0060 | Cut and install hatch. loc 5 | 0 | Task Dependent | 2023-07-16 09:00 | 2023-07-16 12:00 |  | 5 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-16 09:00 | 2023-07-16 12:00 | Contract Fibreglasser | 23SD2
10733670 - 0070 | Not Started | GLSTest-01.PHOS.MAINT.4440 | PROJECT | Phos Acid | 10733670 - HF Fume Dctng Syst Supply Cam B Hatches | 10733670 | 0070 | Close Permit - 10733670 - HF Fume Dctng Syst Supply Cam B Hatches | 0 | Task Dependent | 2023-07-16 12:00 | 2023-07-16 12:30 |  | 12.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 12:00 | 2023-07-16 12:30 | Phos Permit Issuer | 23SD2
10742291 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4425 | PROJECT | Phos Acid | 10742291 - Reactor Sump Acid Wash Man | 10742291 | 0010 | Issue Permit - 10742291 - Reactor Sump Acid Wash Man | 0 | Task Dependent | 2023-07-16 07:00 | 2023-07-16 08:00 |  | 7.5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-16 07:00 | 2023-07-16 08:00 | Phos Permit Issuer | 23SD2
10742291 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4425 | PROJECT | Phos Acid | 10742291 - Reactor Sump Acid Wash Man | 10742291 | 0020 | install FG line | 0 | Task Dependent | 2023-07-16 08:00 | 2023-07-16 14:00 |  | 7.5 | 6 | 6 | 12 | 12 | 0 |  |  | 2023-07-16 08:00 | 2023-07-16 14:00 | Contract Fitter | 23SD2
10742291 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4425 | PROJECT | Phos Acid | 10742291 - Reactor Sump Acid Wash Man | 10742291 | 0030 | Close Permit - 10742291 - Reactor Sump Acid Wash Man | 0 | Task Dependent | 2023-07-16 14:00 | 2023-07-16 15:00 |  | 7.5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-16 14:00 | 2023-07-16 15:00 | Phos Permit Issuer | 23SD2
10811458 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4629 | ELEC | Granulation | 10811458 - MOD - Replace MCCB on 4629PC2902 | 10811458 | 0010 | Issue Permit - 10811458 - MOD - Replace MCCB on 4629PC2902 | 0 | Task Dependent | 2023-07-14 06:00 | 2023-07-14 06:30 |  | 6 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 06:00 | 2023-07-14 06:30 | Gran Permit Issuer | 23SD2EM1
10811458 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4629 | ELEC | Granulation | 10811458 - MOD - Replace MCCB on 4629PC2902 | 10811458 | 0020 | MOD - Replace MCCB on 4629PC2902 | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 11:00 |  | 5.5 | 4 | 4 | 4 | 4 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 11:00 | Elec 3 | 23SD2EM1
10811458 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4629 | ELEC | Granulation | 10811458 - MOD - Replace MCCB on 4629PC2902 | 10811458 | 0030 | Close Permit - 10811458 - MOD - Replace MCCB on 4629PC2902 | 0 | Task Dependent | 2023-07-14 11:00 | 2023-07-14 11:30 |  | 5.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 11:00 | 2023-07-14 11:30 | Gran Permit Issuer | 23SD2EM1
10814859 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4485 | PROJECT | Phos Acid | 10814859 - SPP23010: Civil/Structural Labour | 10814859 | 0020 | Carry out required lifts | 0 | Task Dependent | 2023-07-16 07:30 | 2023-07-16 11:30 |  | 20 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-16 07:30 | 2023-07-16 11:30 | Franna, Rigger, Crane Operator | 23SD2
10813640 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | BMW | Granulation | 10813640 - Weld strips over pre-scrubber flanges | 10813640 | 0010 | Issue Permit - 10813640 - Weld strips over pre-scrubber flanges | 0 | Task Dependent | 2023-07-13 00:30 | 2023-07-13 01:00 |  | 15 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 00:30 | 2023-07-13 01:00 | Gran Permit Issuer | 23SD2EM1
10813640 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4628 | BMW | Granulation | 10813640 - Weld strips over pre-scrubber flanges | 10813640 | 0020 | Unbox | 0 | Task Dependent | 2023-07-13 01:00 | 2023-07-13 03:00 |  | 15 | 2 | 2 | 6 | 6 | 0 |  |  | 2023-07-13 01:00 | 2023-07-13 03:00 | BMW, Fitter | 23SD2EM1
10813640 - 0050 | Not Started | GLSTest-01.GRAN.MAINT.4628 | BMW | Granulation | 10813640 - Weld strips over pre-scrubber flanges | 10813640 | 0050 | Erect scaffold (CSE) | 0 | Task Dependent | 2023-07-13 22:00 | 2023-07-14 08:00 |  | 0 | 8 | 8 | 32 | 32 | 0 |  |  | 2023-07-13 22:00 | 2023-07-14 08:00 | T/A, Scaffolder | 23SD2EM1
10813640 - 0070 | Not Started | GLSTest-01.GRAN.MAINT.4628 | BMW | Granulation | 10813640 - Weld strips over pre-scrubber flanges | 10813640 | 0070 | Dyepen testing(CSE) | 0 | Task Dependent | 2023-07-14 08:00 | 2023-07-14 12:00 |  | 0 | 4 | 4 | 4 | 4 | 0 |  |  | 2023-07-14 08:00 | 2023-07-14 12:00 | Static Engineer | 23SD2EM1
10813640 - 0080 | Not Started | GLSTest-01.GRAN.MAINT.4628 | BMW | Granulation | 10813640 - Weld strips over pre-scrubber flanges | 10813640 | 0080 | Weld strips over pre-scrubber flanges 1 (CSE) | 0 | Task Dependent | 2023-07-14 12:00 | 2023-07-15 |  | 0 | 10 | 10 | 30 | 30 | 0 |  |  | 2023-07-14 12:00 | 2023-07-15 | T/A, BMW | 23SD2EM1
10813640 - 0100 | Not Started | GLSTest-01.GRAN.MAINT.4628 | BMW | Granulation | 10813640 - Weld strips over pre-scrubber flanges | 10813640 | 0100 | Weld strips over pre-scrubber flanges 2 (CSE) | 0 | Task Dependent | 2023-07-14 12:00 | 2023-07-15 |  | 0 | 10 | 10 | 30 | 30 | 0 |  |  | 2023-07-14 12:00 | 2023-07-15 | T/A, BMW | 23SD2EM1
10813640 - 0102 | Not Started | GLSTest-01.GRAN.MAINT.4628 | BMW | Granulation | 10813640 - Weld strips over pre-scrubber flanges | 10813640 | 0102 | Inspection of repairs (CSE) | 0 | Task Dependent | 2023-07-15 | 2023-07-15 02:00 |  | 0 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-15 | 2023-07-15 02:00 | T/A, Static Engineer | 23SD2EM1
10813640 - 0120 | Not Started | GLSTest-01.GRAN.MAINT.4628 | BMW | Granulation | 10813640 - Weld strips over pre-scrubber flanges | 10813640 | 0120 | dismantle scaffold (CSE) | 0 | Task Dependent | 2023-07-15 02:00 | 2023-07-15 10:00 |  | 0 | 6 | 6 | 24 | 24 | 0 |  |  | 2023-07-15 02:00 | 2023-07-15 10:00 | T/A, Scaffolder | 23SD2EM1
10813640 - 0140 | Not Started | GLSTest-01.GRAN.MAINT.4628 | BMW | Granulation | 10813640 - Weld strips over pre-scrubber flanges | 10813640 | 0140 | Box up | 0 | Task Dependent | 2023-07-15 10:00 | 2023-07-15 12:00 |  | 0 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-15 10:00 | 2023-07-15 12:00 | BMW | 23SD2EM1
10813640 - 0150 | Not Started | GLSTest-01.GRAN.MAINT.4628 | BMW | Granulation | 10813640 - Weld strips over pre-scrubber flanges | 10813640 | 0150 | Close Permit - 10813640 - Weld strips over pre-scrubber flanges | 0 | Task Dependent | 2023-07-15 12:00 | 2023-07-15 12:30 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 12:00 | 2023-07-15 12:30 | Gran Permit Issuer | 23SD2EM1
10814859 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4485 | PROJECT | Phos Acid | 10814859 - SPP23010: Civil/Structural Labour | 10814859 | 0020 | Issue Permit - 10814859 - SPP23010: Civil/Structural Labour | 0 | Task Dependent | 2023-07-16 07:00 | 2023-07-16 07:30 |  | 20 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 07:00 | 2023-07-16 07:30 | Phos Permit Issuer | 23SD2
10814859 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4485 | PROJECT | Phos Acid | 10814859 - SPP23010: Civil/Structural Labour | 10814859 | 0020 | Issue Permit - 10814859 - SPP23010: Civil/Structural Labour | 0 | Task Dependent | 2023-07-16 11:30 | 2023-07-16 12:00 |  | 20 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 11:30 | 2023-07-16 12:00 | Phos Permit Issuer | 23SD2
PHOS.RD.1170 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Hemihydrate Reaction |  |  | Flush Recirculation Pump | 0 | Task Dependent | 2023-07-14 19:00 | 2023-07-14 19:30 |  | 34 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 19:00 | 2023-07-14 19:30 | Phos Ops | 22SD1
10812593 - 0000 | Not Started | GLSTest-01.PHOS.MAINT.4411 | PROJECT | Phos Acid | 10812593 - MOD - Replace Spare Cell MCCB [SPP23020] | 10812593 | 0030 | Local Power Outage - Cooling Water | 0 | Level of Effort | 2023-07-15 06:30 | 2023-07-15 18:00 |  | 31.5 | 11.5 | 11.5 | 0 | 0 | 0 |  |  | 2023-07-15 06:30 | 2023-07-15 18:00 |  | 23SD2
10815919 - 0010 | Not Started | GLSTest-01.PWR.MAINT.5400 | PWR | Power Station | 10815919 - STAT TESTING - Power station protection | 10815919 | 0010 | STAT TESTING - Power station protection Shift 1 | 0 | Task Dependent | 2023-07-12 07:00 | 2023-07-12 17:00 |  | 78 | 10 | 10 | 20 | 20 | 0 |  |  | 2023-07-12 07:00 | 2023-07-12 17:00 | Contract Elec | 23SD2
10815919 - 0070 | Not Started | GLSTest-01.PWR.MAINT.5400 | PWR | Power Station | 10815919 - STAT TESTING - Power station protection | 10815919 | 0020 | Close Permit - 10815919 - STAT TESTING - Power station protection | 0 | Task Dependent | 2023-07-16 16:30 | 2023-07-16 17:00 |  | 38 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 16:30 | 2023-07-16 17:00 | Pwr Ops | 23SD2
10818142 - 0010 | Not Started | GLSTest-01.BENE.MAINT.2142 | LUBE | Beneficiation | 10818142 - LU-Change-out Oil | 10818142 | 0010 | LU-Change-out Oil Western Drive gearbox | 0 | Task Dependent | 2023-07-15 19:30 | 2023-07-16 03:30 |  | 11 | 8 | 8 | 8 | 8 | 0 |  |  | 2023-07-15 19:30 | 2023-07-16 03:30 | Lube | 23SD2EM1
10818252 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10818252 - EI 4628FV28031 opening issues | 10818252 | 0010 | Issue Permit - 10818252 - EI 4628FV28031 opening issues | 0 | Task Dependent | 2023-07-13 21:30 | 2023-07-13 22:00 |  | 11 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 21:30 | 2023-07-13 22:00 | Gran Permit Issuer | 23SD2EM1
10818252 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10818252 - EI 4628FV28031 opening issues | 10818252 | 0020 | Replace valve | 0 | Task Dependent | 2023-07-13 22:00 | 2023-07-14 02:00 |  | 11 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-13 22:00 | 2023-07-14 02:00 | Fitter, Elec 3 | 23SD2EM1
10818252 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10818252 - EI 4628FV28031 opening issues | 10818252 | 0040 | Close Permit - 10818252 - EI 4628FV28031 opening issues | 0 | Task Dependent | 2023-07-14 02:00 | 2023-07-14 02:30 |  | 11 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 02:00 | 2023-07-14 02:30 | Gran Permit Issuer | 23SD2EM1
10818142 - 0005 | Not Started | GLSTest-01.BENE.MAINT.2142 | LUBE | Beneficiation | 10818142 - LU-Change-out Oil | 10818142 | 0010 | Issue Permit - 10818142 - LU-Change-out Oil | 0 | Task Dependent | 2023-07-15 19:00 | 2023-07-15 19:30 |  | 11 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 19:00 | 2023-07-15 19:30 | Phos Permit Issuer | 23SD2EM1
10818142 - 0020 | Not Started | GLSTest-01.BENE.MAINT.2142 | LUBE | Beneficiation | 10818142 - LU-Change-out Oil | 10818142 | 0010 | Close Permit - 10818142 - LU-Change-out Oil | 0 | Task Dependent | 2023-07-16 03:30 | 2023-07-16 04:00 |  | 11 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 03:30 | 2023-07-16 04:00 | Phos Permit Issuer | 23SD2EM1
10815919 - 0005 | Not Started | GLSTest-01.PWR.MAINT.5400 | PWR | Power Station | 10815919 - STAT TESTING - Power station protection | 10815919 | 0020 | Issue Permit - 10815919 - STAT TESTING - Power station protection | 0 | Task Dependent | 2023-07-12 07:00 | 2023-07-12 07:30 |  | 78 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 07:00 | 2023-07-12 07:30 | Pwr Ops | 23SD2
10815919 - 0020 | Not Started | GLSTest-01.PWR.MAINT.5400 | PWR | Power Station | 10815919 - STAT TESTING - Power station protection | 10815919 | 0010 | STAT TESTING - Power station protection Shift 2 | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 17:00 |  | 68 | 10 | 10 | 20 | 20 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 17:00 | Contract Elec | 23SD2
10815919 - 0030 | Not Started | GLSTest-01.PWR.MAINT.5400 | PWR | Power Station | 10815919 - STAT TESTING - Power station protection | 10815919 | 0010 | STAT TESTING - Power station protection Shift 3 | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 17:00 |  | 58 | 10 | 10 | 20 | 20 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 17:00 | Contract Elec | 23SD2
10815919 - 0040 | Not Started | GLSTest-01.PWR.MAINT.5400 | PWR | Power Station | 10815919 - STAT TESTING - Power station protection | 10815919 | 0010 | STAT TESTING - Power station protection Shift 4 | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 17:00 |  | 48 | 10 | 10 | 20 | 20 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 17:00 | Contract Elec | 23SD2
10815919 - 0050 | Not Started | GLSTest-01.PWR.MAINT.5400 | PWR | Power Station | 10815919 - STAT TESTING - Power station protection | 10815919 | 0010 | STAT TESTING - Power station protection Shift 5 | 0 | Task Dependent | 2023-07-16 07:00 | 2023-07-16 17:00 |  | 38 | 10 | 10 | 20 | 20 | 0 |  |  | 2023-07-16 07:00 | 2023-07-16 17:00 | Contract Elec | 23SD2
PSOFF | Not Started | GLSTest-01.MLSTN.PWR | PWR |  | Key Dates |  |  | Power Station Maintenance Start | 0 | Start Milestone | 2023-07-12 06:00 |  |  | 66 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-12 06:00 |  |  | 22SD1
10812898 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | PROJECT | Granulation | 10812898 - HVS ELEC - Install Breaker for upcoming pump replacement | 10812898 | 0010 | Issue Permit - 10812898 - HVS ELEC - Install Breaker for upcoming pump replacement | 0 | Task Dependent | 2023-07-14 06:00 | 2023-07-14 06:30 |  | 32.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 06:00 | 2023-07-14 06:30 | Gran Permit Issuer | 23SD2
10812898 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4628 | PROJECT | Granulation | 10812898 - HVS ELEC - Install Breaker for upcoming pump replacement | 10812898 | 0020 | FWD HV Switching | 0 | Task Dependent | 2023-07-14 06:00 | 2023-07-14 07:00 |  | 32.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-14 06:00 | 2023-07-14 07:00 | HV Elec | 23SD2
10812898 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4628 | PROJECT | Granulation | 10812898 - HVS ELEC - Install Breaker for upcoming pump replacement | 10812898 | 0030 | Replace MCCB | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 08:00 |  | 32.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 08:00 | Elec | 23SD2
10812898 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4628 | PROJECT | Granulation | 10812898 - HVS ELEC - Install Breaker for upcoming pump replacement | 10812898 | 0040 | REV HV Switching | 0 | Task Dependent | 2023-07-14 08:00 | 2023-07-14 09:00 |  | 32.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-14 08:00 | 2023-07-14 09:00 | HV Elec | 23SD2
10812898 - 0050 | Not Started | GLSTest-01.GRAN.MAINT.4628 | PROJECT | Granulation | 10812898 - HVS ELEC - Install Breaker for upcoming pump replacement | 10812898 | 0050 | Finish Upgrade | 0 | Task Dependent | 2023-07-14 09:00 | 2023-07-14 13:00 |  | 32.5 | 4 | 4 | 4 | 4 | 0 |  |  | 2023-07-14 09:00 | 2023-07-14 13:00 | Elec | 23SD2
10667285 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4425 | ELEC | Phos Acid | 10667285 - Repair/replace corroded cable tray | 10667285 | 0030 | Replace corroded Cable tray - Shift 1 | 0 | Task Dependent | 2023-07-16 03:00 | 2023-07-16 13:00 |  | 14 | 10 | 10 | 20 | 20 | 0 |  |  | 2023-07-16 03:00 | 2023-07-16 13:00 | 80ft EWP, Elec 4 | 23SD2
10667285 - 0040 | Not Started | GLSTest-01.PHOS.MAINT.4425 | ELEC | Phos Acid | 10667285 - Repair/replace corroded cable tray | 10667285 | 0040 | Riggers to Assist | 0 | Task Dependent | 2023-07-16 03:00 | 2023-07-16 06:00 |  | 21 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-16 03:00 | 2023-07-16 06:00 | Rigger | 23SD2
10819362 - 0010 | Not Started | GLSTest-01.BENE.MAINT.2142 | ELEC | Beneficiation | 10819362 - MOD Replace Thickener Bed Pressure Tx | 10819362 | 0010 | Replace Thickener Bed Pressure Tx | 0 | Task Dependent | 2023-07-15 19:30 | 2023-07-15 23:30 |  | 5 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-15 19:30 | 2023-07-15 23:30 | Elec 1 | 23SD2
10814903 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10814903 - HVS - Replace rusted IRIS Derivation box | 10814903 | 0010 | HV Switch | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 10:30 |  | 17.5 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 10:30 | HV Elec | 23SD2
10814903 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10814903 - HVS - Replace rusted IRIS Derivation box | 10814903 | 0020 | Install IRIS Derivation box | 0 | Task Dependent | 2023-07-13 10:30 | 2023-07-13 12:30 |  | 17.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-13 10:30 | 2023-07-13 12:30 | Elec 2 | 23SD2
10814904 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10814904 - HVS - Replace rusted IRIS Derivation box | 10814904 | 0010 | Install IRIS Derivation box | 0 | Task Dependent | 2023-07-13 12:30 | 2023-07-13 14:30 |  | 17.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-13 12:30 | 2023-07-13 14:30 | Elec 2 | 23SD2
10812898 - 0060 | Not Started | GLSTest-01.GRAN.MAINT.4628 | PROJECT | Granulation | 10812898 - HVS ELEC - Install Breaker for upcoming pump replacement | 10812898 | 0010 | Close Permit - 10812898 - HVS ELEC - Install Breaker for upcoming pump replacement | 0 | Task Dependent | 2023-07-14 13:00 | 2023-07-14 13:30 |  | 32.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 13:00 | 2023-07-14 13:30 | Gran Permit Issuer | 23SD2
10814903 - 0005 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10814903 - HVS - Replace rusted IRIS Derivation box | 10814903 | 0010 | Issue Permit - 10814903 - HVS - Replace rusted IRIS Derivation box | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 07:30 |  | 17.5 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 07:30 | Gran Permit Issuer | 23SD2
10814903 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10814903 - HVS - Replace rusted IRIS Derivation box | 10814903 | 0010 | Close Permit - 10814903 - HVS - Replace rusted IRIS Derivation box | 0 | Task Dependent | 2023-07-13 12:30 | 2023-07-13 13:00 |  | 19.5 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-13 12:30 | 2023-07-13 13:00 | Gran Permit Issuer | 23SD2
10814904 - 0005 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10814904 - HVS - Replace rusted IRIS Derivation box | 10814904 | 0010 | Issue Permit - 10814904 - HVS - Replace rusted IRIS Derivation box | 0 | Task Dependent | 2023-07-13 12:00 | 2023-07-13 12:30 |  | 17.5 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-13 12:00 | 2023-07-13 12:30 | Gran Permit Issuer | 23SD2
10814904 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10814904 - HVS - Replace rusted IRIS Derivation box | 10814904 | 0010 | Close Permit - 10814904 - HVS - Replace rusted IRIS Derivation box | 0 | Task Dependent | 2023-07-13 14:30 | 2023-07-13 15:00 |  | 17.5 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-13 14:30 | 2023-07-13 15:00 | Gran Permit Issuer | 23SD2
10819362 - 0005 | Not Started | GLSTest-01.BENE.MAINT.2142 | ELEC | Beneficiation | 10819362 - MOD Replace Thickener Bed Pressure Tx | 10819362 | 0010 | Issue Permit - 10819362 - MOD Replace Thickener Bed Pressure Tx | 0 | Task Dependent | 2023-07-15 19:00 | 2023-07-15 19:30 |  | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 19:00 | 2023-07-15 19:30 | Gran Permit Issuer | 23SD2
10819362 - 0020 | Not Started | GLSTest-01.BENE.MAINT.2142 | ELEC | Beneficiation | 10819362 - MOD Replace Thickener Bed Pressure Tx | 10819362 | 0010 | Close Permit - 10819362 - MOD Replace Thickener Bed Pressure Tx | 0 | Task Dependent | 2023-07-15 23:30 | 2023-07-16 |  | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 23:30 | 2023-07-16 | Gran Permit Issuer | 23SD2
10667285 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4425 | ELEC | Phos Acid | 10667285 - Repair/replace corroded cable tray | 10667285 | 0010 | Issue Permit - 10667285 - Repair/replace corroded cable tray | 0 | Task Dependent | 2023-07-16 02:30 | 2023-07-16 03:00 |  | 14 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 02:30 | 2023-07-16 03:00 | Phos Permit Issuer | 23SD2
10667285 - 0050 | Not Started | GLSTest-01.PHOS.MAINT.4425 | ELEC | Phos Acid | 10667285 - Repair/replace corroded cable tray | 10667285 | 0010 | Close Permit - 10667285 - Repair/replace corroded cable tray | 0 | Task Dependent | 2023-07-16 23:00 | 2023-07-16 23:30 |  | 14 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 23:00 | 2023-07-16 23:30 | Phos Permit Issuer | 23SD2
10813022 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON3 | Granulation | 10813022 - Replace Combustion Air Fan Impeller | 10813022 | 0010 | Issue Permit - 10813022 - Replace Combustion Air Fan Impeller | 0 | Task Dependent | 2023-07-13 01:00 | 2023-07-13 01:30 |  | 32.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 01:00 | 2023-07-13 01:30 | Gran Permit Issuer | 23SD2EM1
10813022 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON3 | Granulation | 10813022 - Replace Combustion Air Fan Impeller | 10813022 | 0020 | Unbolt fan casing and guarding | 0 | Task Dependent | 2023-07-13 01:30 | 2023-07-13 04:30 |  | 32.5 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-13 01:30 | 2023-07-13 04:30 | Fitter | 23SD2EM1
10813022 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON3 | Granulation | 10813022 - Replace Combustion Air Fan Impeller | 10813022 | 0030 | Remove fan casing and guarding | 0 | Task Dependent | 2023-07-13 01:30 | 2023-07-13 03:30 |  | 34.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-13 01:30 | 2023-07-13 03:30 | Crawler Crane, Rigger, Crane Operator | 23SD2EM1
10813022 - 0060 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON3 | Granulation | 10813022 - Replace Combustion Air Fan Impeller | 10813022 | 0060 | Unbolt Impeller assembly | 0 | Task Dependent | 2023-07-13 04:30 | 2023-07-13 07:30 |  | 32.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-13 04:30 | 2023-07-13 07:30 | Fitter | 23SD2EM1
10813022 - 0070 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON3 | Granulation | 10813022 - Replace Combustion Air Fan Impeller | 10813022 | 0070 | Remove Impeller assembly | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 08:30 |  | 32.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 08:30 | Crawler Crane, Rigger, Crane Operator | 23SD2EM1
10813022 - 0110 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON3 | Granulation | 10813022 - Replace Combustion Air Fan Impeller | 10813022 | 0110 | Install new Impeller assembly | 0 | Task Dependent | 2023-07-13 10:30 | 2023-07-13 11:30 |  | 32.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-13 10:30 | 2023-07-13 11:30 | Crawler Crane, Rigger, Crane Operator | 23SD2EM1
10813022 - 0130 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON3 | Granulation | 10813022 - Replace Combustion Air Fan Impeller | 10813022 | 0130 | Bolt up new Impeller assembly | 0 | Task Dependent | 2023-07-13 11:30 | 2023-07-13 13:00 |  | 32.5 | 1.5 | 1.5 | 3 | 3 | 0 |  |  | 2023-07-13 11:30 | 2023-07-13 13:00 | Fitter | 23SD2EM1
10813022 - 0150 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON3 | Granulation | 10813022 - Replace Combustion Air Fan Impeller | 10813022 | 0150 | Reinstate fan casing and guarding | 0 | Task Dependent | 2023-07-13 13:00 | 2023-07-13 15:00 |  | 32.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-13 13:00 | 2023-07-13 15:00 | Crawler Crane, Rigger, Crane Operator | 23SD2EM1
10813022 - 0170 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON3 | Granulation | 10813022 - Replace Combustion Air Fan Impeller | 10813022 | 0170 | Bolt up fan casing and guarding | 0 | Task Dependent | 2023-07-13 13:00 | 2023-07-13 17:00 |  | 32.5 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-13 13:00 | 2023-07-13 17:00 | Fitter | 23SD2EM1
10813022 - 0180 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON3 | Granulation | 10813022 - Replace Combustion Air Fan Impeller | 10813022 | 0180 | Run fan to test for baseline vibrations | 0 | Task Dependent | 2023-07-13 19:00 | 2023-07-13 21:00 |  | 32.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-13 19:00 | 2023-07-13 21:00 | Condition Monitor, Gran Ops | 23SD2EM1
10813022 - 0200 | Not Started | GLSTest-01.GRAN.MAINT.4622 | DAWSON3 | Granulation | 10813022 - Replace Combustion Air Fan Impeller | 10813022 | 0200 | Close Permit - 10813022 - Replace Combustion Air Fan Impeller | 0 | Task Dependent | 2023-07-13 21:00 | 2023-07-13 21:30 |  | 37.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 21:00 | 2023-07-13 21:30 | Gran Permit Issuer | 23SD2EM1
10810641 - 0015 | Not Started | GLSTest-01.PHOS.MAINT.4420 | ELEC | Phos Acid | 10810641 - Repair cable tray between rock filters | 10810641 | 0010 | Repair cable tray between rock filters - Shift 2 | 0 | Task Dependent | 2023-07-15 06:00 | 2023-07-15 16:00 |  | 14 | 10 | 10 | 20 | 20 | 0 |  |  | 2023-07-15 06:00 | 2023-07-15 16:00 | Elec 4 | 23SD2
10810641 - 0016 | Not Started | GLSTest-01.PHOS.MAINT.4420 | ELEC | Phos Acid | 10810641 - Repair cable tray between rock filters | 10810641 | 0010 | Repair cable tray between rock filters - Shift 3 | 0 | Task Dependent | 2023-07-15 16:00 | 2023-07-16 02:00 |  | 14 | 10 | 10 | 20 | 20 | 0 |  |  | 2023-07-15 16:00 | 2023-07-16 02:00 | Elec 4 | 23SD2
10667285 - 0045 | Not Started | GLSTest-01.PHOS.MAINT.4425 | ELEC | Phos Acid | 10667285 - Repair/replace corroded cable tray | 10667285 | 0030 | Replace corroded Cable tray - Shift 2 | 0 | Task Dependent | 2023-07-16 13:00 | 2023-07-16 23:00 |  | 14 | 10 | 10 | 20 | 20 | 0 |  |  | 2023-07-16 13:00 | 2023-07-16 23:00 | 80ft EWP, Elec 4 | 23SD2
10667285 - 0046 | Not Started | GLSTest-01.PHOS.MAINT.4425 | ELEC | Phos Acid | 10667285 - Repair/replace corroded cable tray | 10667285 | 0040 | Riggers to Assist | 0 | Task Dependent | 2023-07-16 13:00 | 2023-07-16 16:00 |  | 21 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-16 13:00 | 2023-07-16 16:00 | Rigger | 23SD2
GRAN.RD.1100 | Not Started | GLSTest-01.GRAN.RD | GRAN | Granulation | Ramp Down Activities |  |  | (2nd Wash) Hot Wash Granulator | 0 | Task Dependent | 2023-07-12 12:00 | 2023-07-12 13:30 |  | 0 | 1.5 | 1.5 | 3 | 3 | 0 |  |  | 2023-07-12 12:00 | 2023-07-12 13:30 | Gran Ops | 22SD3
10807995 - 0015 | Not Started | GLSTest-01.GRAN.MAINT.4629 | GRAN | Granulation | 10807995 - 15W Prod Rplc GranSD CE0001 | 10807995 | 0010 | Re-instate Replacement Chiller Bags | 0 | Task Dependent | 2023-07-14 20:00 | 2023-07-14 23:00 |  | 13 | 3 | 3 | 9 | 9 | 0 |  |  | 2023-07-14 20:00 | 2023-07-14 23:00 | Gran Ops | 23SD2
10812898 - 0015 | Not Started | GLSTest-01.GRAN.MAINT.4628 | PROJECT | Granulation | 10812898 - HVS ELEC - Install Breaker for upcoming pump replacement | 10812898 | 0010 | Local Power Outage - Scrubber Sump Pump | 0 | Level of Effort | 2023-07-14 06:30 | 2023-07-14 09:00 |  | 32.5 | 2.5 | 2.5 | 0 | 0 | 0 |  |  | 2023-07-14 06:30 | 2023-07-14 09:00 |  | 23SD2
10811458 - 0015 | Not Started | GLSTest-01.GRAN.MAINT.4629 | ELEC | Granulation | 10811458 - MOD - Replace MCCB on 4629PC2902 | 10811458 | 0020 | Local Outage - Tailgas Scrubber Pump 2 | 0 | Level of Effort | 2023-07-14 07:00 | 2023-07-14 11:00 |  | 5.5 | 4 | 4 | 0 | 0 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 11:00 |  | 23SD2EM1
GRAN.RU.6080 | Not Started | GLSTest-01.GRAN.RU | GRAN | Granulation | Ramp Up Activites |  |  | Start Dryer & Cooler Fans | 0 | Task Dependent | 2023-07-15 20:00 | 2023-07-15 20:30 |  | 2 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 20:00 | 2023-07-15 20:30 | Gran Ops | 22SD1
10812970 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4629 | PROJECT | Granulation | 10812970 - Complete Structural mods in the Chiller. | 10812970 | 0030 | Issue Permit - 10812970 - Complete Structural mods in the Chiller. | 0 | Task Dependent | 2023-07-13 07:00 | 2023-07-13 07:30 |  | 11 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-13 07:00 | 2023-07-13 07:30 | Phos Permit Issuer | 23SD2
10812970 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4629 | PROJECT | Granulation | 10812970 - Complete Structural mods in the Chiller. | 10812970 | 0040 | Chiller Structural Mods - Shift 1 | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 19:30 |  | 11 | 10 | 10 | 30 | 30 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 19:30 | Contract BMW | 23SD2
10812970 - 0050 | Not Started | GLSTest-01.GRAN.MAINT.4629 | PROJECT | Granulation | 10812970 - Complete Structural mods in the Chiller. | 10812970 | 0050 | Install Structural frame. Franna | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 09:30 |  | 39 | 2 | 2 | 0 | 0 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 09:30 | Franna | 23SD2
10812970 - 0060 | Not Started | GLSTest-01.GRAN.MAINT.4629 | PROJECT | Granulation | 10812970 - Complete Structural mods in the Chiller. | 10812970 | 0060 | Close Permit - 10812970 - Complete Structural mods in the Chiller. | 0 | Task Dependent | 2023-07-14 19:30 | 2023-07-14 20:00 |  | 11 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 19:30 | 2023-07-14 20:00 | Phos Permit Issuer | 23SD2
10812970 - 0045 | Not Started | GLSTest-01.GRAN.MAINT.4629 | PROJECT | Granulation | 10812970 - Complete Structural mods in the Chiller. | 10812970 | 0040 | Chiller Structural Mods - Shift 2 | 0 | Task Dependent | 2023-07-13 19:30 | 2023-07-14 07:30 |  | 11 | 10 | 10 | 30 | 30 | 0 |  |  | 2023-07-13 19:30 | 2023-07-14 07:30 | Contract BMW | 23SD2
10812970 - 0046 | Not Started | GLSTest-01.GRAN.MAINT.4629 | PROJECT | Granulation | 10812970 - Complete Structural mods in the Chiller. | 10812970 | 0040 | Chiller Structural Mods - Shift 3 | 0 | Task Dependent | 2023-07-14 07:30 | 2023-07-14 19:30 |  | 11 | 10 | 10 | 30 | 30 | 0 |  |  | 2023-07-14 07:30 | 2023-07-14 19:30 | Contract BMW | 23SD2
PHOS.ISO.2110 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Rock Filters |  |  | Isolate Process Water to Rock Filters | 0 | Task Dependent | 2023-07-14 21:00 | 2023-07-14 21:30 |  | 48.5 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-14 21:00 | 2023-07-14 21:30 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5240 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Rock Filters |  |  | De-Isolate Process Water to Rock Filters | 0 | Task Dependent | 2023-07-16 21:00 | 2023-07-16 21:30 |  | 14 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-16 21:00 | 2023-07-16 21:30 | Phos Acid Isolator | 22SD1
PHOS.ISO.2080 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Product Filtration |  |  | Isolate Plant Wash System A | 0 | Task Dependent | 2023-07-14 20:00 | 2023-07-14 21:00 |  | 41.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-14 20:00 | 2023-07-14 21:00 | Phos Acid Isolator | 22SD1
PHOS.ISO.2270 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Product Filtration |  |  | Isolate Plant Wash System B | 0 | Task Dependent | 2023-07-15 06:00 | 2023-07-15 07:00 |  | 32.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-15 06:00 | 2023-07-15 07:00 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5160 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Product Filtration |  |  | Isolate Plant Wash System A | 0 | Task Dependent | 2023-07-16 15:00 | 2023-07-16 16:00 |  | 21.5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-16 15:00 | 2023-07-16 16:00 | Phos Acid Isolator | 22SD1
PHOS.DEISO.5200 | Not Started | GLSTest-01.PHOS.DE-ISO | PHOS | Phos Acid | De-Isolations - Product Filtration |  |  | Isolate Plant Wash System B | 0 | Task Dependent | 2023-07-16 16:00 | 2023-07-16 17:00 |  | 21.5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-16 16:00 | 2023-07-16 17:00 | Phos Acid Isolator | 22SD1
10798223 - 0025 | Not Started | GLSTest-01.GRAN.MAINT.4628 | DAWSON1 | Granulation | 10798223 - 52W MFit Rplc Sprays GranSD 46SU2801 | 10798223 | 0020 | Install Sprays | 0 | Task Dependent | 2023-07-14 19:00 | 2023-07-14 23:00 |  | 11 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-14 19:00 | 2023-07-14 23:00 | Fitter | 23SD2
10793809 - 0015 | Not Started | GLSTest-01.PHOS.MAINT.4445 | DAWSON3 | Phos Acid | 10793809 - FI-Pump bypass line blocked | 10793809 | 0010 | Franna Team Assist | 0 | Task Dependent | 2023-07-16 11:00 | 2023-07-16 13:00 |  | 13 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-16 11:00 | 2023-07-16 13:00 | Rigger, Crane Operator, Franna | 23SD2
10800865 - 0060 | Not Started | GLSTest-01.BENE.COMM | ELEC | Beneficiation | 10800865 - EL change precision rollers jaw feed con | 10800865 | 0010 | Calibrate weightometer | 0 | Task Dependent | 2023-07-17 00:30 | 2023-07-17 02:00 |  | 0 | 1.5 | 1.5 | 3 | 3 | 0 |  |  | 2023-07-17 00:30 | 2023-07-17 02:00 | Elec 2 | 23SD2
10807389 - 0040 | Not Started | GLSTest-01.PHOS.COMM | ELEC | Phos Acid | 10807389 - Replace cable, include service loop | 10807389 | 0010 | Stroke Valve Check | 0 | Task Dependent | 2023-07-16 21:30 | 2023-07-16 22:00 |  | 17 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-16 21:30 | 2023-07-16 22:00 | Elec 3 | 23SD2
10799063 - 0040 | Not Started | GLSTest-01.PHOS.COMM | ELEC | Phos Acid | 10799063 - CMR-0009249 Install test switch | 10799063 | 0020 | Function test | 0 | Task Dependent | 2023-07-17 07:00 | 2023-07-17 07:30 |  | 7 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-17 07:00 | 2023-07-17 07:30 | Elec 3 | 23SD2
10799062 - 0040 | Not Started | GLSTest-01.PHOS.COMM | ELEC | Phos Acid | 10799062 - CMR-0009248 Install test switch | 10799062 | 0020 | Function test | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 07:30 |  | 27 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 07:30 | Elec 1 | 23SD2
10796254 - 0030 | Not Started | GLSTest-01.PHOS.COMM | ELEC | Phos Acid | 10796254 - Replace electrical box door and hinges | 10796254 | 0010 | Commissioning and Valve Stroke Checks | 0 | Task Dependent | 2023-07-17 02:30 | 2023-07-17 06:30 |  | 7 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-17 02:30 | 2023-07-17 06:30 | Elec 3 | 23SD2
10802913 - 0050 | Not Started | GLSTest-01.PHOS.COMM | ELEC | Phos Acid | 10802913 - Scope to replace solenoid panel. | 10802913 | 0020 | Commissioning and Valve Stroke Checks | 0 | Task Dependent | 2023-07-17 07:00 | 2023-07-17 08:00 |  | 6.5 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-17 07:00 | 2023-07-17 08:00 | Elec 2 | 23SD2
PHOS.RD.1100 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Hemihydrate Reaction |  |  | HPWB Lancing of Skid Pump | 0 | Task Dependent | 2023-07-14 08:00 | 2023-07-14 09:00 |  | 12 | 1 | 1 | 4 | 4 | 0 |  |  | 2023-07-14 08:00 | 2023-07-14 09:00 | Waterblast Truck, Cleaning Ops, Phos Ops | 22SD1
GRAN.RD.1140 | Not Started | GLSTest-01.GRAN.RD | GRAN | Granulation | Ramp Down Activities |  |  | Purge Sulphuric Acid Line | 0 | Task Dependent | 2023-07-12 21:30 | 2023-07-12 23:00 |  | 0 | 1.5 | 1.5 | 3 | 3 | 0 |  |  | 2023-07-12 21:30 | 2023-07-12 23:00 | Gran Ops | 22SD3
GRAN.ISO.2080 | Not Started | GLSTest-01.GRAN.ISO | GRAN | Granulation | Isolations |  |  | Isolate Slurry Lines at Back of Granulator | 0 | Task Dependent | 2023-07-12 13:30 | 2023-07-12 14:00 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-12 13:30 | 2023-07-12 14:00 | Gran Ops | 22SD3
10812970 - 0047 | Not Started | GLSTest-01.GRAN.COMM | PSSR | Granulation | 10812970 - Complete Structural mods in the Chiller. | 10812970 | 0040 | PSSR - Chiller Structural Mods | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 08:30 |  | 5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 08:30 | PSSR | 23SD2
10794028 - 0050 | Not Started | GLSTest-01.PHOS.COMM | PROJECT | Phos Acid | 10794028 - Increase process water line diameter | 10794028 | 0020 | PSSR - Process Water Line | 0 | Task Dependent | 2023-07-16 17:30 | 2023-07-16 19:00 |  | 18.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-16 17:30 | 2023-07-16 19:00 | PSSR | 23SD2
10789290 - 0030 | Not Started | GLSTest-01.PHOS.COMM | PSSR | Phos Acid | 10789290 - FI-Replace PSV 43PSV10009 | 10789290 | 0020 | PSSR - H2SO4 to Phos Delivery Pumps PSV | 0 | Task Dependent | 2023-07-16 08:30 | 2023-07-16 10:00 |  | 12.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-16 08:30 | 2023-07-16 10:00 | PSSR | 23SD2
10787923 - 0080 | Not Started | GLSTest-01.GRAN.COMM | PSSR | Granulation | 10787923 - MF-Replace sulphuric acid pipe - PN | 10787923 | 0060 | PSSR - PN Tank Sulphuric Acid Pipe | 0 | Task Dependent | 2023-07-14 12:00 | 2023-07-14 13:30 |  | 9 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-14 12:00 | 2023-07-14 13:30 | PSSR | 23SD2
10791744 - 0080 | Not Started | GLSTest-01.PHOS.COMM | PSSR | Phos Acid | 10791744 - FI-40% acid manifold valves V6 , V7, V11 | 10791744 | 0070 | PSSR - 40% Acid Manifold Valves | 0 | Task Dependent | 2023-07-14 16:00 | 2023-07-14 17:30 |  | 68 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-14 16:00 | 2023-07-14 17:30 | PSSR | 23SD2
10748609 - 0050 | Not Started | GLSTest-01.PHOS.COMM | PSSR | Phos Acid | 10748609 - A side clothwash tk steam valve | 10748609 | 0030 | PSSR - Clothwash Tank A Steam Valve | 0 | Task Dependent | 2023-07-16 07:00 | 2023-07-16 08:30 |  | 12.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-16 07:00 | 2023-07-16 08:30 | PSSR | 23SD2
10767555 - 0040 | Not Started | GLSTest-01.GRAN.COMM | PSSR | Granulation | 10767555 - 5Y MFit Repr GranSD Tail Gas Scbr | 10767555 | 0030 | PSSR - Tail Gas Scrubber H2SO4 NRV | 0 | Task Dependent | 2023-07-14 07:00 | 2023-07-14 08:30 |  | 15 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-14 07:00 | 2023-07-14 08:30 | PSSR | 23SD2
10818252 - 0050 | Not Started | GLSTest-01.GRAN.COMM | ELEC | Phos Acid | 10818252 - EI 4628FV28031 opening issues | 10818252 | 0040 | PSSR - H2SO4 Valve to Primary Scrubber Tank | 0 | Task Dependent | 2023-07-14 02:30 | 2023-07-14 04:00 |  | 11 | 1.5 | 1.5 | 1.5 | 1.5 | 0 |  |  | 2023-07-14 02:30 | 2023-07-14 04:00 | PSSR | 23SD2EM1
10811336 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10811336 - Replace Flash B Y-Piece Pipe | 10811336 | 0010 | Issue Permit - 10811336 - Replace Flash B Y-Piece Pipe | 0 | Task Dependent | 2023-07-15 15:30 | 2023-07-15 16:00 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 15:30 | 2023-07-15 16:00 | Phos Permit Issuer | 23SD2EM1
10811336 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10811336 - Replace Flash B Y-Piece Pipe | 10811336 | 0020 | Remove Flash B Y-Piece Pipe | 0 | Task Dependent | 2023-07-15 16:00 | 2023-07-15 23:00 |  | 0 | 5 | 5 | 25 | 25 | 0 |  |  | 2023-07-15 16:00 | 2023-07-15 23:00 | 130ft EWP, Franna, Crane Operator, Rigger, T/A, Fitter | 23SD2EM1
10811336 - 0070 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10811336 - Replace Flash B Y-Piece Pipe | 10811336 | 0070 | Close Permit - 10811336 - Replace Flash B Y-Piece Pipe | 0 | Task Dependent | 2023-07-17 20:30 | 2023-07-17 21:00 |  | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-17 20:30 | 2023-07-17 21:00 | Phos Permit Issuer | 23SD2EM1
10812903 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10812903 - Replace Flash B D/Leg Straight Spool | 10812903 | 0010 | Issue Permit - 10812903 - Replace Flash B D/Leg Straight Spool | 0 | Task Dependent | 2023-07-15 22:30 | 2023-07-15 23:00 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 22:30 | 2023-07-15 23:00 | Phos Permit Issuer | 23SD2EM1
10812903 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10812903 - Replace Flash B D/Leg Straight Spool | 10812903 | 0020 | Remove Flash B D/Leg Straight Spool | 0 | Task Dependent | 2023-07-15 23:00 | 2023-07-16 04:00 |  | 0 | 5 | 5 | 35 | 35 | 0 |  |  | 2023-07-15 23:00 | 2023-07-16 04:00 | 130ft EWP, Franna, Crane Operator, Rigger, T/A, Fitter | 23SD2EM1
10812903 - 0070 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10812903 - Replace Flash B D/Leg Straight Spool | 10812903 | 0070 | Close Permit - 10812903 - Replace Flash B D/Leg Straight Spool | 0 | Task Dependent | 2023-07-18 01:30 | 2023-07-18 02:00 |  | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-18 01:30 | 2023-07-18 02:00 | Phos Permit Issuer | 23SD2EM1
10820357 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4480 | DAWSON3 | Phos Acid | 10820357 - FIT-8001 suction valve replacement | 10820357 | 0010 | Issue Permit - 10820357 - FIT-8001 suction valve replacement | 0 | Task Dependent | 2023-07-16 07:00 | 2023-07-16 07:30 |  | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 07:00 | 2023-07-16 07:30 | Phos Permit Issuer | 23SD2EM1
10820357 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4480 | DAWSON3 | Phos Acid | 10820357 - FIT-8001 suction valve replacement | 10820357 | 0020 | Remove valve | 0 | Task Dependent | 2023-07-16 07:30 | 2023-07-16 09:30 |  | 5 | 2 | 2 | 8 | 8 | 0 |  |  | 2023-07-16 07:30 | 2023-07-16 09:30 | Rigger, Franna, Crane Operator, Fitter | 23SD2EM1
10820357 - 0060 | Not Started | GLSTest-01.PHOS.MAINT.4480 | DAWSON3 | Phos Acid | 10820357 - FIT-8001 suction valve replacement | 10820357 | 0060 | Overhaul valve | 0 | Task Dependent | 2023-07-16 09:30 | 2023-07-16 12:30 |  | 5 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-16 09:30 | 2023-07-16 12:30 | Fitter | 23SD2EM1
10820357 - 0070 | Not Started | GLSTest-01.PHOS.MAINT.4480 | DAWSON3 | Phos Acid | 10820357 - FIT-8001 suction valve replacement | 10820357 | 0070 | Reinstate valve | 0 | Task Dependent | 2023-07-16 12:30 | 2023-07-16 15:30 |  | 5 | 3 | 3 | 12 | 12 | 0 |  |  | 2023-07-16 12:30 | 2023-07-16 15:30 | Rigger, Franna, Crane Operator, Fitter | 23SD2EM1
10820357 - 0110 | Not Started | GLSTest-01.PHOS.MAINT.4480 | DAWSON3 | Phos Acid | 10820357 - FIT-8001 suction valve replacement | 10820357 | 0110 | Close Permit - 10820357 - FIT-8001 suction valve replacement | 0 | Task Dependent | 2023-07-16 15:30 | 2023-07-16 16:00 |  | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 15:30 | 2023-07-16 16:00 | Phos Permit Issuer | 23SD2EM1
10811336 - 0025 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10811336 - Replace Flash B Y-Piece Pipe | 10811336 | 0020 | Re-Instate Flash B Y-Piece Pipe | 0 | Task Dependent | 2023-07-17 13:30 | 2023-07-17 20:30 |  | 0 | 5 | 5 | 25 | 25 | 0 |  |  | 2023-07-17 13:30 | 2023-07-17 20:30 | 130ft EWP, Franna, Crane Operator, Rigger, T/A, Fitter | 23SD2EM1
10812903 - 0025 | Not Started | GLSTest-01.PHOS.MAINT.4425 | DAWSON3 | Phos Acid | 10812903 - Replace Flash B D/Leg Straight Spool | 10812903 | 0020 | Re-Instate Flash B D/Leg Straight Spool | 0 | Task Dependent | 2023-07-17 20:30 | 2023-07-18 01:30 |  | 0 | 5 | 5 | 35 | 35 | 0 |  |  | 2023-07-17 20:30 | 2023-07-18 01:30 | 130ft EWP, Franna, Crane Operator, Rigger, T/A, Fitter | 23SD2EM1
PHOS.ISO.2200 | Not Started | GLSTest-01.PHOS.ISO | PHOS | Phos Acid | Isolations - Services |  |  | Isolate Process Water to Product Storage | 0 | Task Dependent | 2023-07-15 03:00 | 2023-07-15 04:00 |  | 32.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-15 03:00 | 2023-07-15 04:00 | Phos Acid Isolator | 22SD1
PHOS.RD.1260 | Not Started | GLSTest-01.PHOS.RD | PHOS | Phos Acid | Ramp Down - Hemihydrate Reaction |  |  | Drain Waste Water Tank | 0 | Task Dependent | 2023-07-15 18:00 | 2023-07-15 21:00 |  | 13.5 | 3 | 3 | 3 | 3 | 0 |  |  | 2023-07-15 18:00 | 2023-07-15 21:00 | Phos Ops | 22SD1
GRAN.MS.1030 | Not Started | GLSTest-01.MLSTN.GRAN | GRAN |  | Key Dates |  |  | Granulation Start Emptying Wet-Side | 0 | Finish Milestone |  | 2023-07-12 23:00 |  | 136 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-07-12 23:00 |  | 22SD1
GRAN.MS.1050 | Not Started | GLSTest-01.MLSTN.GRAN | GRAN |  | Key Dates |  |  | Cone Tanks, PN Tank Cleaning Completed | 0 | Finish Milestone |  | 2023-07-13 22:00 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2023-07-13 22:00 |  | 22SD1
10798225 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | DAWSON3 | Granulation | 10798225 - 52W MFit Rplc Sprays GranSD 46SU2802 | 10798225 | 0010 | Issue permit - 10798225 - 52W MFit Rplc Sprays GranSD 46SU2802 | 0 | Task Dependent | 2023-07-14 08:30 | 2023-07-14 09:00 |  | 15 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 08:30 | 2023-07-14 09:00 | Gran Permit Issuer | 23SD2
10798225 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4628 | DAWSON3 | Granulation | 10798225 - 52W MFit Rplc Sprays GranSD 46SU2802 | 10798225 | 0020 | Remove sprays | 0 | Task Dependent | 2023-07-14 09:00 | 2023-07-14 12:00 |  | 15 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-14 09:00 | 2023-07-14 12:00 | Fitter | 23SD2
10798225 - 0030 | Not Started | GLSTest-01.GRAN.MAINT.4628 | DAWSON3 | Granulation | 10798225 - 52W MFit Rplc Sprays GranSD 46SU2802 | 10798225 | 0030 | Clean & inspect | 0 | Task Dependent | 2023-07-14 12:00 | 2023-07-14 13:00 |  | 15 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-14 12:00 | 2023-07-14 13:00 | Fitter | 23SD2
10798225 - 0040 | Not Started | GLSTest-01.GRAN.MAINT.4628 | DAWSON3 | Granulation | 10798225 - 52W MFit Rplc Sprays GranSD 46SU2802 | 10798225 | 0040 | Reinstate sprays | 0 | Task Dependent | 2023-07-14 13:00 | 2023-07-14 17:00 |  | 15 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-14 13:00 | 2023-07-14 17:00 | Fitter | 23SD2
10798225 - 0050 | Not Started | GLSTest-01.GRAN.MAINT.4628 | DAWSON3 | Granulation | 10798225 - 52W MFit Rplc Sprays GranSD 46SU2802 | 10798225 | 0050 | Close permit - 10798225 - 52W MFit Rplc Sprays GranSD 46SU2802 | 0 | Task Dependent | 2023-07-14 19:00 | 2023-07-14 19:30 |  | 15 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 19:00 | 2023-07-14 19:30 | Gran Permit Issuer | 23SD2
10820227 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10820227 - Cable gland loose RGV | 10820227 | 0010 | Cable gland loose RGV | 0 | Task Dependent | 2023-07-13 08:00 | 2023-07-13 09:00 |  | 43 | 1 | 1 | 1 | 1 | 0 |  |  | 2023-07-13 08:00 | 2023-07-13 09:00 | Projects Elec | 23SD2
10821561 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4440 | DAWSON1 | Phos Acid | 10821561 - Inner rubber lining damage | 10821561 | 0010 | Issue Permit - 10821561 - Inner rubber lining damage | 0 | Task Dependent | 2023-07-15 03:00 | 2023-07-15 03:30 |  | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 03:00 | 2023-07-15 03:30 | Phos Permit Issuer | 23SD2EM1
10821561 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4440 | DAWSON1 | Phos Acid | 10821561 - Inner rubber lining damage | 10821561 | 0020 | Remove bolts to elbow and bellows | 0 | Task Dependent | 2023-07-15 03:30 | 2023-07-15 07:30 |  | 4 | 2 | 2 | 8 | 8 | 0 |  |  | 2023-07-15 03:30 | 2023-07-15 07:30 | Crane Operator, Rigger, Franna, Fitter | 23SD2EM1
10821561 - 0060 | Not Started | GLSTest-01.PHOS.MAINT.4440 | DAWSON1 | Phos Acid | 10821561 - Inner rubber lining damage | 10821561 | 0060 | Remove bellows off elbow | 0 | Task Dependent | 2023-07-15 09:00 | 2023-07-15 10:00 |  | 18.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-15 09:00 | 2023-07-15 10:00 | Fitter | 23SD2EM1
10821561 - 0070 | Not Started | GLSTest-01.PHOS.MAINT.4440 | DAWSON1 | Phos Acid | 10821561 - Inner rubber lining damage | 10821561 | 0070 | Sandblast Cowling for Rubber Work | 0 | Task Dependent | 2023-07-15 10:00 | 2023-07-15 12:00 |  | 18.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-15 10:00 | 2023-07-15 12:00 | Sandblast, Cleaning Ops | 23SD2EM1
10821561 - 0090 | Not Started | GLSTest-01.PHOS.MAINT.4440 | DAWSON1 | Phos Acid | 10821561 - Inner rubber lining damage | 10821561 | 0090 | Repair Rubber in steel discharge cowling | 0 | Task Dependent | 2023-07-15 12:00 | 2023-07-16 |  | 18.5 | 10 | 10 | 10 | 10 | 0 |  |  | 2023-07-15 12:00 | 2023-07-16 | Rubber | 23SD2EM1
10821561 - 0100 | Not Started | GLSTest-01.PHOS.MAINT.4440 | DAWSON1 | Phos Acid | 10821561 - Inner rubber lining damage | 10821561 | 0100 | Fit new bellows to elbow | 0 | Task Dependent | 2023-07-16 | 2023-07-16 01:00 |  | 18.5 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-16 | 2023-07-16 01:00 | Fitter | 23SD2EM1
10821561 - 0140 | Not Started | GLSTest-01.PHOS.MAINT.4440 | DAWSON1 | Phos Acid | 10821561 - Inner rubber lining damage | 10821561 | 0140 | Bolt in bellows and elbow | 0 | Task Dependent | 2023-07-16 19:30 | 2023-07-16 22:30 |  | 4 | 3 | 3 | 12 | 12 | 0 |  |  | 2023-07-16 19:30 | 2023-07-16 22:30 | Crane Operator, Rigger, Franna, Fitter | 23SD2EM1
10821561 - 0150 | Not Started | GLSTest-01.PHOS.MAINT.4440 | DAWSON1 | Phos Acid | 10821561 - Inner rubber lining damage | 10821561 | 0150 | Close Permit - 10821561 - Inner rubber lining damage | 0 | Task Dependent | 2023-07-16 22:30 | 2023-07-16 23:00 |  | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 22:30 | 2023-07-16 23:00 | Phos Permit Issuer | 23SD2EM1
10820227 - 0005 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10820227 - Cable gland loose RGV | 10814903 | 0010 | Issue Permit - 10820227 - Cable gland loose RGV | 0 | Task Dependent | 2023-07-13 07:30 | 2023-07-13 08:00 |  | 43 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-13 07:30 | 2023-07-13 08:00 | Gran Permit Issuer | 23SD2
10820227 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4628 | ELEC | Granulation | 10820227 - Cable gland loose RGV | 10814903 | 0010 | Close Permit - 10820227 - Cable gland loose RGV | 0 | Task Dependent | 2023-07-13 09:00 | 2023-07-13 09:30 |  | 43 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-13 09:00 | 2023-07-13 09:30 | Gran Permit Issuer | 23SD2
10798223 - 0024 | Not Started | GLSTest-01.GRAN.MAINT.4628 | DAWSON1 | Granulation | 10798223 - 52W MFit Rplc Sprays GranSD 46SU2801 | 10798223 | 0020 | Clean & Inspect | 0 | Task Dependent | 2023-07-14 16:00 | 2023-07-14 17:00 |  | 11 | 1 | 1 | 2 | 2 | 0 |  |  | 2023-07-14 16:00 | 2023-07-14 17:00 | Fitter | 23SD2
10822340 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.9999 | CLEAN 2 | Phos Acid | 10822340 - Cloth Wash Booster lines HPWB C Side | 10822340 | 0010 | Issue Permit - 10822340 - Cloth Wash Booster lines HPWB C Side | 0 | Task Dependent | 2023-07-15 08:00 | 2023-07-15 08:30 |  | 26 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 08:00 | 2023-07-15 08:30 | Phos Permit Issuer | 23SD2EM1
10822340 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.9999 | CLEAN 2 | Phos Acid | 10822340 - Cloth Wash Booster lines HPWB C Side | 10822340 | 0020 | Remove end cap and pipework | 0 | Task Dependent | 2023-07-15 08:30 | 2023-07-15 11:00 |  | 26 | 2.5 | 2.5 | 5 | 5 | 0 |  |  | 2023-07-15 08:30 | 2023-07-15 11:00 | 45ft EWP, Fitter | 23SD2EM1
10822340 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.9999 | CLEAN 2 | Phos Acid | 10822340 - Cloth Wash Booster lines HPWB C Side | 10822340 | 0030 | HPWB Clothwash Booster lines | 0 | Task Dependent | 2023-07-16 01:00 | 2023-07-16 07:00 |  | 12 | 6 | 6 | 18 | 18 | 0 |  |  | 2023-07-16 01:00 | 2023-07-16 07:00 | 45ft EWP, Waterblast Truck, Cleaning Ops | 23SD2EM1
10822340 - 0050 | Not Started | GLSTest-01.PHOS.MAINT.9999 | CLEAN 2 | Phos Acid | 10822340 - Cloth Wash Booster lines HPWB C Side | 10822340 | 0050 | Reinstate end caps and pipework | 0 | Task Dependent | 2023-07-16 11:00 | 2023-07-16 14:30 |  | 22.5 | 3.5 | 3.5 | 7 | 7 | 0 |  |  | 2023-07-16 11:00 | 2023-07-16 14:30 | 45ft EWP, Fitter | 23SD2EM1
10822340 - 0060 | Not Started | GLSTest-01.PHOS.MAINT.9999 | CLEAN 2 | Phos Acid | 10822340 - Cloth Wash Booster lines HPWB C Side | 10822340 | 0060 | Close Permit - 10822340 - Cloth Wash Booster lines HPWB C Side | 0 | Task Dependent | 2023-07-16 14:30 | 2023-07-16 15:00 |  | 22.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 14:30 | 2023-07-16 15:00 | Phos Permit Issuer | 23SD2EM1
10794029 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4460 |  | Phos Acid | 10794029 - Fire Water Access Water to Tanks | 10794029 | 0020 | Cut header and install tie-ins x 3 | 0 | Task Dependent | 2023-07-15 07:00 | 2023-07-15 17:00 |  | 16 | 10 | 10 | 30 | 30 | 0 |  |  | 2023-07-15 07:00 | 2023-07-15 17:00 | Contract TA, Contract BMW | 23SD2
10794029 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4460 |  | Phos Acid | 10794029 - Fire Water Access Water to Tanks | 10794029 | 0020 | Install Permit - 10794029 - Fire Water Access Water to Tanks | 0 | Task Dependent | 2023-07-15 06:30 | 2023-07-15 07:00 |  | 30 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 06:30 | 2023-07-15 07:00 | Phos Permit Issuer | 23SD2
10794029 - 0030 | Not Started | GLSTest-01.PHOS.MAINT.4460 |  | Phos Acid | 10794029 - Fire Water Access Water to Tanks | 10794029 | 0020 | Install Permit - 10794029 - Fire Water Access Water to Tanks | 0 | Task Dependent | 2023-07-15 17:00 | 2023-07-15 17:30 |  | 44 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 17:00 | 2023-07-15 17:30 | Phos Permit Issuer | 23SD2
10822669 - 0010 | Not Started | GLSTest-01.BENE.MAINT.2141 | DAWSON2 | Beneficiation | 10822669 - Thickener feed suction valve | 10822669 | 0010 | Issue Permit - 10822669 - Thickener feed suction valve | 0 | Task Dependent | 2023-07-15 19:00 | 2023-07-15 19:30 |  | 2.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 19:00 | 2023-07-15 19:30 | Phos Permit Issuer | 23SD2EM3
10822669 - 0020 | Not Started | GLSTest-01.BENE.MAINT.2141 | DAWSON2 | Beneficiation | 10822669 - Thickener feed suction valve | 10822669 | 0020 | Remove Valve and transport to workshop | 0 | Task Dependent | 2023-07-15 21:30 | 2023-07-15 23:30 |  | 2.5 | 2 | 2 | 8 | 8 | 0 |  |  | 2023-07-15 21:30 | 2023-07-15 23:30 | Fitter, Franna, Crane Operator, Rigger | 23SD2EM3
10822669 - 0040 | Not Started | GLSTest-01.BENE.MAINT.2141 | DAWSON2 | Beneficiation | 10822669 - Thickener feed suction valve | 10822669 | 0040 | blast pump suction build up | 0 | Task Dependent | 2023-07-15 19:30 | 2023-07-15 21:30 |  | 2.5 | 2 | 2 | 6 | 6 | 0 |  |  | 2023-07-15 19:30 | 2023-07-15 21:30 | Waterblast Truck, Cleaning Ops | 23SD2EM3
10822669 - 0050 | Not Started | GLSTest-01.BENE.MAINT.2141 | DAWSON2 | Beneficiation | 10822669 - Thickener feed suction valve | 10822669 | 0050 | Close Permit - 10822669 - Thickener feed suction valve | 0 | Task Dependent | 2023-07-16 14:00 | 2023-07-16 14:30 |  | 2.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-16 14:00 | 2023-07-16 14:30 | Phos Permit Issuer | 23SD2EM3
10823298 - 0010 | Not Started | GLSTest-01.PHOS.MAINT.4485 | DAWSON3 | Phos Acid | 10823298 - Check/Replace coupling element | 10823298 | 0010 | Check/Replace coupling element | 0 | Task Dependent | 2023-07-15 03:30 | 2023-07-15 09:30 |  | 37.5 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-15 03:30 | 2023-07-15 09:30 | Fitter | 23SD2EM3
10823300 - 0010 | Not Started | GLSTest-01.BENE.MAINT.2121 | DAWSON2 | Beneficiation | 10823300 - 15WK Shut works - Tertiary Screen Crack | 10823300 | 0010 | repair/replace plates | 0 | Task Dependent | 2023-07-14 10:00 | 2023-07-14 20:00 |  | 36.5 | 8 | 8 | 16 | 16 | 0 |  |  | 2023-07-14 10:00 | 2023-07-14 20:00 | Fitter | 23SD2EM3
10823300 - 0020 | Not Started | GLSTest-01.BENE.MAINT.2121 | DAWSON2 | Beneficiation | 10823300 - 15WK Shut works - Tertiary Screen Crack | 10823300 | 0020 | Cut plate | 0 | Task Dependent | 2023-07-14 10:00 | 2023-07-14 20:00 |  | 36.5 | 8 | 8 | 8 | 8 | 0 |  |  | 2023-07-14 10:00 | 2023-07-14 20:00 | BMW | 23SD2EM3
10823300 - 0030 | Not Started | GLSTest-01.BENE.MAINT.2121 | DAWSON2 | Beneficiation | 10823300 - 15WK Shut works - Tertiary Screen Crack | 10823300 | 0030 | Build Internal Scaffold | 0 | Task Dependent | 2023-07-14 04:00 | 2023-07-14 10:00 |  | 36.5 | 4 | 4 | 16 | 16 | 0 |  |  | 2023-07-14 04:00 | 2023-07-14 10:00 | Scaffolder, Franna, Crane Operator, Rigger | 23SD2EM3
10823300 - 0050 | Not Started | GLSTest-01.BENE.MAINT.2121 | DAWSON2 | Beneficiation | 10823300 - 15WK Shut works - Tertiary Screen Crack | 10823300 | 0050 | dye pen inspection | 0 | Task Dependent | 2023-07-14 20:00 | 2023-07-15 |  | 36.5 | 4 | 4 | 4 | 4 | 0 |  |  | 2023-07-14 20:00 | 2023-07-15 | Maintenance Engineer | 23SD2EM3
10823396 - 0005 | Not Started | GLSTest-01.GRAN.MAINT.4611 | DAWSON2 | Granulation | 10823396 - re-bolt and re-clamp air cannon hose | 10823396 | 0010 | Issue Permit - 10823396 - re-bolt and re-clamp air cannon hose | 0 | Task Dependent | 2023-07-14 09:30 | 2023-07-14 10:00 |  | 18 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-14 09:30 | 2023-07-14 10:00 | Gran Permit Issuer | 23SD2EM3
10823422 - 0010 | Not Started | GLSTest-01.BENE.MAINT.2111 | BMW | Beneficiation | 10823422 - hole needs repair | 10823422 | 0010 | hole needs repair | 0 | Task Dependent | 2023-07-14 10:00 | 2023-07-14 16:00 |  | 42.5 | 6 | 6 | 12 | 12 | 0 |  |  | 2023-07-14 10:00 | 2023-07-14 16:00 | BMW | 23SD2EM3
10823422 - 0020 | Not Started | GLSTest-01.BENE.MAINT.2111 | BMW | Beneficiation | 10823422 - hole needs repair | 10823422 | 0020 | Build Scaffold | 0 | Task Dependent | 2023-07-14 04:00 | 2023-07-14 10:00 |  | 42.5 | 4 | 4 | 8 | 8 | 0 |  |  | 2023-07-14 04:00 | 2023-07-14 10:00 | Scaffolder | 23SD2EM3
10823298 - 0005 | Not Started | GLSTest-01.PHOS.MAINT.4485 | DAWSON3 | Phos Acid | 10823298 - Check/Replace coupling element | 10823298 | 0010 | Issue Permit -10823298 - Check/Replace coupling element | 0 | Task Dependent | 2023-07-15 03:00 | 2023-07-15 03:30 |  | 37.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 03:00 | 2023-07-15 03:30 | Gran Ops | 23SD2EM3
10823298 - 0020 | Not Started | GLSTest-01.PHOS.MAINT.4485 | DAWSON3 | Phos Acid | 10823298 - Check/Replace coupling element | 10823298 | 0010 | Close Permit -10823298 - Check/Replace coupling element | 0 | Task Dependent | 2023-07-15 09:30 | 2023-07-15 10:00 |  | 37.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 09:30 | 2023-07-15 10:00 | Gran Ops | 23SD2EM3
10822669 - 0025 | Not Started | GLSTest-01.BENE.MAINT.2141 | DAWSON2 | Beneficiation | 10822669 - Thickener feed suction valve | 10822669 | 0020 | Overhaul Valve in Workshop | 0 | Task Dependent | 2023-07-15 23:30 | 2023-07-16 12:00 |  | 2.5 | 10.5 | 10.5 | 21 | 21 | 0 |  |  | 2023-07-15 23:30 | 2023-07-16 12:00 | Fitter | 23SD2EM3
10822669 - 0026 | Not Started | GLSTest-01.BENE.MAINT.2141 | DAWSON2 | Beneficiation | 10822669 - Thickener feed suction valve | 10822669 | 0020 | Re-Instate Valve | 0 | Task Dependent | 2023-07-16 12:00 | 2023-07-16 14:00 |  | 2.5 | 2 | 2 | 8 | 8 | 0 |  |  | 2023-07-16 12:00 | 2023-07-16 14:00 | Fitter, Franna, Crane Operator, Rigger | 23SD2EM3
10823300 - 0005 | Not Started | GLSTest-01.BENE.MAINT.2121 | DAWSON2 | Beneficiation | 10823300 - 15WK Shut works - Tertiary Screen Crack | 10823300 | 0010 | Issue Permit - 10823300 - 15WK Shut works - Tertiary Screen Crack | 0 | Task Dependent | 2023-07-14 03:30 | 2023-07-14 04:00 |  | 36.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 03:30 | 2023-07-14 04:00 | Gran Permit Issuer | 23SD2EM3
10823300 - 0060 | Not Started | GLSTest-01.BENE.MAINT.2121 | DAWSON2 | Beneficiation | 10823300 - 15WK Shut works - Tertiary Screen Crack | 10823300 | 0010 | Close Permit - 10823300 - 15WK Shut works - Tertiary Screen Crack | 0 | Task Dependent | 2023-07-15 02:00 | 2023-07-15 02:30 |  | 36.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-15 02:00 | 2023-07-15 02:30 | Gran Permit Issuer | 23SD2EM3
10823300 - 0035 | Not Started | GLSTest-01.BENE.MAINT.2121 | DAWSON2 | Beneficiation | 10823300 - 15WK Shut works - Tertiary Screen Crack | 10823300 | 0030 | Remove Scaffold | 0 | Task Dependent | 2023-07-15 | 2023-07-15 02:00 |  | 36.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-15 | 2023-07-15 02:00 | Scaffolder | 23SD2EM3
10823396 - 0010 | Not Started | GLSTest-01.GRAN.MAINT.4611 | DAWSON2 | Granulation | 10823396 - re-bolt and re-clamp air cannon hose | 10823396 | 0010 | re-bolt and re-clamp air cannon hose | 0 | Task Dependent | 2023-07-14 10:00 | 2023-07-14 13:00 |  | 18 | 3 | 3 | 6 | 6 | 0 |  |  | 2023-07-14 10:00 | 2023-07-14 13:00 | Fitter | 23SD2EM3
10823396 - 0020 | Not Started | GLSTest-01.GRAN.MAINT.4611 | DAWSON2 | Granulation | 10823396 - re-bolt and re-clamp air cannon hose | 10823396 | 0010 | Close Permit - 10823396 - re-bolt and re-clamp air cannon hose | 0 | Task Dependent | 2023-07-14 13:00 | 2023-07-14 13:30 |  | 18 | 0.5 | 0.5 | 1 | 1 | 0 |  |  | 2023-07-14 13:00 | 2023-07-14 13:30 | Gran Permit Issuer | 23SD2EM3
10823422 - 0025 | Not Started | GLSTest-01.BENE.MAINT.2111 | BMW | Beneficiation | 10823422 - hole needs repair | 10823422 | 0020 | Remove Scaffold | 0 | Task Dependent | 2023-07-14 16:00 | 2023-07-14 20:00 |  | 42.5 | 2 | 2 | 4 | 4 | 0 |  |  | 2023-07-14 16:00 | 2023-07-14 20:00 | Scaffolder | 23SD2EM3
10823422 - 0005 | Not Started | GLSTest-01.BENE.MAINT.2111 | BMW | Beneficiation | 10823422 - hole needs repair | 10823422 | 0010 | Issue Permit - 10823422 - hole needs repair | 0 | Task Dependent | 2023-07-14 03:30 | 2023-07-14 04:00 |  | 42.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 03:30 | 2023-07-14 04:00 | Bene Permit Issuer | 23SD2EM3
10823422 - 0030 | Not Started | GLSTest-01.BENE.MAINT.2111 | BMW | Beneficiation | 10823422 - hole needs repair | 10823422 | 0010 | Close Permit - 10823422 - hole needs repair | 0 | Task Dependent | 2023-07-14 20:00 | 2023-07-14 20:30 |  | 42.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  |  | 2023-07-14 20:00 | 2023-07-14 20:30 | Bene Permit Issuer | 23SD2EM3
GRAN.RD.1000 | Not Started | GLSTest-01.GRAN.RD | GRAN | Granulation | Ramp Down Activities |  |  | Drain Coating Oil Tank | 0 | Task Dependent | 2023-07-11 18:00 | 2023-07-12 06:00 |  | 12 | 12 | 12 | 12 | 12 | 0 |  |  | 2023-07-11 18:00 | 2023-07-12 06:00 | Gran Ops | 22SD3
GRAN.MS.1010 | Not Started | GLSTest-01.MLSTN.GRAN | GRAN |  | Key Dates |  |  | Granulation Ramp Down Start | 0 | Start Milestone | 2023-07-11 18:00 |  |  | 12 | 0 | 0 | 0 | 0 | 0 |  |  | 2023-07-11 18:00 |  |  | 22SD1

## USERDATA
user_data
UserSettings Do Not Edit
DurationQtyType=QT_Hour ShowAsPercentage=0 SmallScaleQtyType=QT_Hour DateFormat=d/MM/yyyy CurrencyFormat=Dollar